## query (43)
Item ID | Item Name | Item Origin | CLT LxL Status | Must-Do-Can't-Fail | Driver | Work Type | LxL Priorities | Program-Portfolio | Accountable Branch | Application | CYSSC Strategic Direction | RACI - Responsible | RACI - Accountable | RACI - Consult | RACI - Inform | Support Needed | Requires ITS | Work Item Description | CMO Comments | Business Outcome | MDCF Criteria | Funding Source | SPP Item Name | Funding Confirmed | Progress Status | Approval Status | Comments | LxL Comments & Action Items | Anticipated Start Date | Anticipated End Date | Milestone 1 - Name | Milestone 1 - Status | Milestone 2 - Name | Milestone 2 - Status | Milestone 3 - Name | Milestone 3 - Status | Milestone 4 - Name | Milestone 4 - Status | Milestone 5 - Name | Milestone 5 - Status | Review Status | Planview ID | Item Link | Item Type | Path
| OIAD R1 - Assess Ministry IT security protocol compliance and protocols between Ministry and Service Delivery Partners for reporting and addressing IT Security Incidents in service delivery partners associated with interfacing Ministry applications. |  |  | FALSE | Audit Recommendation | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN;#mFTIS |  | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35;#Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19;#Torrance, Tyler (MCCSS);#37;#Pawlowski, Walter (MCCSS);#36 |  |  |  | CYIS - Child and Youth I&IT Solutions;#CWOB - Child Welfare Operations Branch | FALSE | MCCSS: To address the recommendations directed towards the Ministry of Children, Community and Social Services (MCCSS), the Child Welfare Operations Branch, the I&T Cluster, and the MGCS Cyber Security Division will meet and work together to determine: - The work that has already been undertaken relating to cyber security generally, and specifically for/in the child welfare sector - The opportunities that might exist to leverage ministry and OPS resources or knowledge - The opportunities for sector-led initiatives that may be brought forward Having the time to properly consult internally will allow us to engage our sector partners to develop a work plan, and define next steps, that can address the issues and recommendations presented during future OIAD follow-up activities. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
| OIAD R2 - Identify lessons learned and potential opportunities for strengthening I&IT processes to prevent recurrence. |  |  | FALSE | Audit Recommendation | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions |  |  | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35;#Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19;#Pawlowski, Walter (MCCSS);#36;#Torrance, Tyler (MCCSS);#37 |  |  |  | CWOB - Child Welfare Operations Branch;#CYIS - Child and Youth I&IT Solutions | FALSE | Based on a sample of municipal/ service delivery partners this may include, where feasible, reviewing recent security incidents and cyberattacks to assess risks and impacts on information systems and interruptions to ministry program service delivery. Identify lessons learned and potential opportunities for strengthening I&IT processes to prevent recurrence. MCCSS: To address the recommendations directed towards the Ministry of Children, Community and Social Services (MCCSS), the Child Welfare Operations Branch, the I&T Cluster, and the MGCS Cyber Security Division will meet and work together to determine: - The work that has already been undertaken relating to cyber security generally, and specifically for/in the child welfare sector - The opportunities that might exist to leverage ministry and OPS resources or knowledge - The opportunities for sector-led initiatives that may be brought forward Having the time to properly consult internally will allow us to engage our sector partners to develop a work plan, and define next steps, that can address the issues and recommendations presented during future OIAD follow-up activities. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
| OIAD R13 - AI Assessment to discover PI Data flows |  |  | FALSE |  | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19;#Torrance, Tyler (MCCSS);#37;#Acuna, Oscar (MCCSS);#35;#Pawlowski, Walter (MCCSS);#36 |  |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | As part of a longer strategy, Children and Youth I&IT Solutions Branch will start an assessment of implementing AI that may be able to discover PI data flows and anticipate, detect and prevent invasive privacy events, following the Curam upgrade scheduled for May 2020. Specific recommendations from the assessment will be reported back by December 2023. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
| OPS Web Accessibility Compliance Plan |  |  | TRUE | Legislation | Grow (Enhancements) |  | Enterprise I&IT | IOB - I&IT Operations Branch |  | Evolve How We Work | Dabideen, Mala (MCCSS);#30 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CAC - Central Agencies Cluster;#ITS - Infrastructure Technology Services;#TBS - Treasury Board Secretariat;#OCIO - Office of the Chief Information Officer;#ODS - Ontario Digital Service;#GovTechON | TRUE | The goal of the OPS Web Accessibility Compliance plan is to bring OPS into compliance with the Accessibility for Ontarians with Disabilities Act (AODA) Integrated Accessibility Standards Regulation (IASR) by December 2024. Focus areas to complete by December 31, 2023: 1.Non-compliant Internet/Extranet Sites 2.Standardization Focus areas to complete by December 31, 2024: 1.Corporate & Enterprise Web Applications 2.Document Accessibility 3.Video Remediation 4. Cultural Transformation |  | OPS will be compliant with the Accessibility for Ontarians with Disabilities Act (AODA) Integrated Accessibility Standards Regulation (IASR) by December 2024. | Legislation | Enterprise Funding |  | Tentative | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A001 | ITGC - eBill | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Requirement | Run - Applications | Audit | CYSSC - Cluster-wide | CMO - Cluster Management Office | eBill |  | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (MCCSS) |  |  | CMO - Cluster Management Office;#SCSI - Shared & Community Services I&IT Solutions;#Audit Team | FALSE | Conduct ITGC design effectiveness testing for eBill. |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A006 | Audit - Data Leakage Prevention Program Phase 1 - Assessment | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Requirement | Run - Applications | Audit | CYSSC - Cluster-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) | Jason Persaud (Cyber Security Division) - MPBSD |  | CMO - Cluster Management Office;#Audit Team;#CYIS - Child and Youth I&IT Solutions | FALSE | Assess the feasibility of implementing automated technologies to prevent data leakage. |  | Feasibility analysis on DLP implementation to address audit findings and best practices in implementing safe guards. As a result, to come up with recommendations on DLP implementation for Phase 2 |  | Other |  | Confirmed | In Progress | Confirmed | There is agreement by Ministry to carry out this work. Funding for cluster to use but Ministry will account for this pressure. |  | 2023-03-06 | 2023-06-02 | RFS to be shared with vendors | Complete/Operationalized | RFS submissions to be evaluated and finalized | Complete/Operationalized | RFS vendor kick-start work | In Progress | Vendor completes deliverables as per SOW | Pending |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A010 | ACWI, CAR, CPIN Dev Migration from KDC | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Applications | Run | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | ACW/I;#CAR;#CPIN |  | Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Support the migration of applications out of KDC. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A011 | SDWG-EHWW: CPIN Auto-Deploy | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Applications | Run | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN CM |  | Wang, Cedric (MCCSS);#15;#Kugendran, Shanmugathasan (MCCSS);#19 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Set up an automated process for auto code deployment in the lower environments. Planning phase. May overlap into next fiscal 24/25 to complete ALL components of CPIN. (CM, FM, QA, Automation). | [8 empty] | Part of the SDWG Countermeasures | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A014 | Quality Standards Framework (QSF) - Phase 1 | Carried forward from 22/23 OpPlan | Approved | FALSE | Ministry Request | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) |  |  | CWOB - Child Welfare Operations Branch;#IOB - I&IT Operations Branch | FALSE | Legislated changes to provide additional safety factors for out of home care of children. | Can we create a more descriptive name? And is this different from the QSF? Maybe "CPIN Reporting Quality Framework"? |  |  | SPP/MYP |  |  |  |  | QSF will be released in 2 -3 phases. Phase 1 will deploy in to production on July 1, 2023 | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A015 | OACIS & PEIS Releases (OAP reconciliation) | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Grow (Enhancements) | Grow | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | OACIS;#PEIS |  | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division | FALSE | Develop application releases from backlog prioritization by the business to support Autism program redesign and transition to an independent intake organization (IIO). Work include: IIO: CRT Operation: CB, IOT, CCS expenses reconciliation, IOT and IOT renewal after EBBS ends, Incidents and service requests |  |  |  | Cluster Base Budget | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A016 | FCIS-KIDS Sustainment (CPRI) | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | FCIS-KIDS |  | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Provide business continuity / keeping-the-lights-on support for FCIS-KIDS, which has reached end of life and for which there is no vendor support. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A017 | Ideasweb Sustainment (CPRI) | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | Ideasweb |  | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Monitor the application and provide maintenance work only to provide business continuity until a replacement software is implemented. In conjunction with KIDS | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A018 | HCD ISCIS Application Sustainment | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | HCD ISCIS |  | Cunningham, Nicki (MCCSS);#20;#Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Keep lights on while modernization activities are underway. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A020 | CPRI Pharmacy Application Sustainment | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | CPRI Pharmacy Application |  | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | Other | FALSE | Provide keeping-the-lights-on production support, including coordinating with CPRI and vendor to implement application-related patches and bug fixes. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A021 | SchedulePRO Sustainment | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | SchedulePRO |  | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Provide keeping-the-lights-on, maintenance-only production support. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A023 | Application Support & Maintenance For All Child Welfare Applications | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN;#mFTIS;#ACW;#ACW/I;#CAR |  | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17;#Acuna, Oscar (MCCSS);#35;#Kugendran, Shanmugathasan (MCCSS);#19;#Torrance, Tyler (MCCSS);#37;#Pawlowski, Walter (MCCSS);#36 | Obias, Joven (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch | FALSE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, database maintenance, and testing activities to support maintenance and anticipated enhancements. Inclusive of A002 and A004 | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A024 | Elasticsearch, Logstash and Kibana (ELK) Enterprise Tool Implementation (Project) | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Requirement;#Security Compliance | Grow (Enhancements) | Audit | CW - Child Welfare & Protection;#FRO - Family Responsibility Office | IOB - I&IT Operations Branch | CPIN;#FCMS | Advance Our Technology Platforms | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) | Peter Wright, Cedric Wang |  | CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#EAO - Enterprise Architecture Office | FALSE | Lead implementation of ELK as central logging tool for CPIN and FCMS to comply with TRA recommendations. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | The completion of this work item is a carry over from 2022-23 with most of the remaining work for solution DEV teams to test and confirm functionality of the tool. There will be ongoing cost for the hosting of the Logstash VM server to be setup to support each of the application solutions |  |  |  | Complete Logstash server setup | In Progress | [8 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A025 | Operational Support for CYSSC Windows & .NET based applications & solutions | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | ACW;#DAD;#Fieldworker;#CAR;#PEIS;#PSSAH;#DDI;#ESMS;#SMIS;#OACIS | Evolve How We Work | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) | Patel, Jesal |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Provide operational support to cluster solution branches; servers and OS availability for Windows and SQL; performance, monitoring, capacity, licensing, SSL, evergreen process, release. OACIS, PEIS, PSSAH, ACW, IdeasWeb, DAD, FWDS, ISCIS, CARS, DDI, MRM, ESMS&ESMS-SPM, ChatBot, ALM, SMIS). Incoming: CR, VRTR, FCISKids) | Please clarify (at the summary level) what work is being done and to which applications. change done as suggested above |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A026 | Upgrades/patches to development, testing and DevOps tools | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Evergreening | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Keep the CYSSC DevOps toolkits on support and maintenance path; Jenkins Upgrade; potential RTC upgrade if required beyond Q3 2023 |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A027 | Performance Tuning | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Conduct infrastructure hardware/operating system/software (middleware) component health checks, tuning, and efficiency improvements. OS, DB, middleware, applications, scripting, systems health checks. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A028 | Application Support and Maintenance for other MCCSS Applications | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | PSSAH;#SALIS;#DAD;#DAS;#PEIS;#Compliance Sheriff;#mFTIS;#HCD ISCIS | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21;#Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. | List the apps |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A029 | CYSSC Platform Support Services | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Evolve How We Work | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Provide CYSSC platform services related to: - server & network provisioning (WIA), OS patching, capacity, monitoring & alerting; cost estimations and projects execution oversight; - Vendor support priority engagement - IBM , Oracle, Microsoft - Solution on-boarding and service management design (KAs/KRs, support model...) - Vulnerabilities assessment and remediation; provide updated data on vulnerabilities and location; | Is it possible to summarize this into 1-3 sentences? done |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A030 | Applications Monitoring and Alerting (e.x. Nagios, Prometheus, Azure Monitoring & Insight, ControlM, OEM) | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | TRUE | Provide alert notifications and support for CYSSC server and applications monitoring, as well as dashboard capability to support capacity management and planning and trending analysis. In some cases application monitoring scope will be expanded. | Is it possible to summarize this into 1-3 sentences? |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A032 | Migrate Source Code Repository from SAMS RTC to GitLab (Project) SAIS A080 | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Evergreening | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | SAMS | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Migrate SAMS source code, SAMS builds process, pipelines, from Rational Team Concert to GitLab & Jenkins on modern DevOps toolkits. Decommission RTC, avoid extended support cost, save on hosting costs, reduce VM server footprint. SAMS is the remaining solution using RTC. The current version of RTC used is on extended support until October 2023. The cost of the extended support is approx $22K. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | Includes SAIS item A080: Move SAMS builder from KDC to GDC. |  |  | 2023-05-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A033 | System Patching | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Includes patching such as but not limited to; Operating System, web server software, applications software stack, DBs, Curam and others |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A034 | ITS Exadata patching support | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | CPIN;#HCD ISCIS;#mFTIS;#FCMS;#SAMS;#SALIS | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | TRUE | Exadata patching occurs twice a year; one in March and the other in September. This is an ITS facilitated work with Oracle and requires planning and communication. The testing phase immediately following the patching requires solution branch teams to help validate functionalities of their respective supported applications. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A035 | SAIS A086: Transition to Operations (TTO) of Digital Applications to IOB | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | SADA;#MyBenefits | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) | Sanjeev Bordoloi, Michael Lau |  | SAIS - Social Assistance I&IT Solutions | FALSE | Transition operational support for the remaining SA Digital applications (SADA, and MyBenefits) from SAIS to Operations |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A036 | Support IBM Authorized Software Program (IASP) Reporting | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Become a Trusted Advisor | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | The IASP report-back is an ITS-led work item that is reported twice a year (in September and in March) and requires the support from all clusters. The report provides an estate-level picture of IBM product licenses within the Topaz agreement that is utilized by clusters/ministries and for entitlement compliance. IOB provides input to IASP discussions in terms of software entitlement compliance at the server level. | Please clarify whether biannually here means twice per year or once every two years? Clarified that it's twice a year. |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A037 | Server Capacity Right-Sizing | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | CPIN;#FCMS;#HCD ISCIS;#mFTIS;#SAMS | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Following the successful migration of all CCP hosted applications from the AIX to the OPCS platform, IOB will continue to monitor and implement right-sizing activities (through CRQs) on OPCS virtual servers with the solution teams to better manage capacity demands and save on hosting costs. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A039 | BIPD: Move to an MCCSS Data Platform | Carried forward from 22/23 OpPlan | Approved | FALSE | Minister Commitment | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | CPIN;#FCMS;#HCD ISCIS;#SAMS | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Support BIPD data extraction requirements for reporting/analytics. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A040 | Support for Identity and Access Management (IAM) Modernization (Migrate to OPS/BPS Secure) | Carried forward from 22/23 OpPlan | Approved | FALSE | Business Modernization/Transformation | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | CAMS;#CPIN CM;#CPIN Reporting;#CPIN FM;#FCMS;#mFTIS;#SAMS;#VQRP+ | Advance Our Technology Platforms | Iqbal, Azhar (MCCSS);#24;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Support all application migration to the new modernized Identity and Access Management service (BPS Secure and OPS Secure) following the migration to X509 pre-requisite. |  |  |  | Cluster Base Budget |  | Tentative | In Progress | Tentative - pending funding | Need to schedule all the work so IOB can support properly. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A042 | Kingston Data Centre Migration/Decommissioning Windows & Linux-based applications (Project) | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Transform | Transform | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | ACW;#ACW/I;#CAR;#OACIS;#SMIS;#Toronto Region Visitor Registration;#Counter Registration | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | - Coordinate by Q3 2023-24 the migration of all remaining CYSSC applications out of KDC (CR, VRTR, SPSS, SMIS, CARS, ACWI, OACIS/PEIS and IFIS Payfile). -Decommission all CYSSC KDC servers before end of Q4 2023-24 |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A043 | Account Administration/Access Management | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | FCMS;#PKI | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Provide account administration for: - User account admin on FED EI application, MTO, NCBS, RBC, OSAP. - PKI user account admin 20k users (SAMS, ESMS, CPIN, mFTIS) - FCMS user account and role administration - RACF user administration - Third Party Access Management |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A046 | CMO A151: 2023 OAGO VFM Audit of the OCCIO | Carried forward from 22/23 OpPlan | Approved - with changes | FALSE | Keeping the Lights On;#Security Compliance;#Audit Requirement | Run - Cluster Services | Audit | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | CPIN;#HCD ISCIS;#mFTIS;#FCMS;#SAMS |  | Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Provide operations support for 2023 OAGO Value-for-Money Audit |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed |  | The title needs to be corrected to say 2023 not 2022. | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A047 | Application Support and Maintenance for Developmental Services Applications | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | DS - Developmental Services | IOB - I&IT Operations Branch | DS;#Fieldworker;#Ideasweb | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. | List the apps |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A048 | Application Support and Maintenance for FRO applications | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | FRO - Family Responsibility Office | IOB - I&IT Operations Branch | FCMS;#FRO Online | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A049 | Operational Support and Maintenance for cloud-based SA applications | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS;#SADA;#MyBenefits;#EST | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, dev-ops and monitoring, release to production and testing activities to support maintenance and anticipated enhancements. Apps: DDDP, EQFX-Bil, EST, EAP, IRCC-Bil, Messaging, EA. Incoming: MyBenefits, SADA |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A050 | Application Support and Maintenance for all Special Needs applications | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SN - Special Needs | IOB - I&IT Operations Branch | HCD ISCIS;#CPRI Pharmacy Application;#OACIS | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. | List the apps |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A052 | Implement Fieldworker DS TP Ontario Transition Site Module Integration | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Applications | Run | DS - Developmental Services | SCSI - Shared & Community Services I&IT Solutions | Fieldworker |  | Dawoud, Safaa (MCCSS);#27 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Changes required for FW due to TPON implementation | Please provide a short description of the work required, rather than a rationale for it. | [21 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A054 | FRO Digital TruePass to OPS Secure Migration | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Grow | FRO - Family Responsibility Office | SCSI - Shared & Community Services I&IT Solutions | FCMS | Advance Our Technology Platforms | Wright, Peter (MCCSS);#28 | Awad, Mohamed (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | To migrate from the legacy True-Pass authentication service to OPS Secure the Identity & Access Management corporate preferred service for authenticating OPS users. |  | To transition FRO users onto the preferred service for authenticating ensuring the security of high-sensitivity information |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-01 | 2023-09-30 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A056 | Fieldworker DS Business & Maintenance Releases | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions | Fieldworker |  | Dawoud, Safaa (MCCSS);#27 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Normal maintenance for Fieldworker DS. | Please confirm the program/portfolio here. This item was carried forward from the 22/23 OpPlan. | [21 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A057 | Fieldworker CESCR Business & Maintenance Releases | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions | Fieldworker |  | Dawoud, Safaa (MCCSS);#27 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Normal maintenance for Fieldworker CESCR. | Please confirm the program/portfolio here. This item was carried forward from the 22/23 OpPlan. | [21 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A059 | Decommission SMIS | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Applications | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions | SMIS |  | Dawoud, Safaa (MCCSS);#27 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Planview ID: 100018345 SMIS is a legacy system to be replaced by Transfer Payment (TP) Ontario enterprise solution​ As of April 1st, 2020, regional staff started using TP Ontario Enterprise System for TP budget submissions​ The TP Ontario team is working to enable functionality to allow Site and Service administration for Wave 2 ​(timelines TBD) ​SMIS is currently hosted in Kingston Data Center (KDC)​. As part of the Cloud Adoption Journey, all applications hosted in KDC have to be moved to another hosting environment or decommissioned by FY 2022- 2023​- Q4 | Please provide a description of the work rather than a rationale. | [21 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A060 | Implement DSCIS-TPON Integration | Carried forward from 22/23 OpPlan | Approved | FALSE | Business Modernization/Transformation | Grow (Enhancements) | Grow | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions | DSCIS;#TPON |  | Chan, Harry (MCCSS);#26 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Integrate DSCIS with TPON through DDI. Includes changes to DSCIS as well as validation of DS data for implementation of Site Module in TPON. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A061 | Implement Dynamic Data and TPON Integration | Carried forward from 22/23 OpPlan | Approved | FALSE | Business Modernization/Transformation | Grow (Enhancements) | Grow | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions | DSCIS;#SOR-RL;#Fieldworker |  | Dawoud, Safaa (MCCSS);#27 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Data feed from TPON to DSCIS, SOR-RL, Fieldworker | Please provide a more detailed description of the work (aim for 1-3 sentences). | [21 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A065 | SAMS - Core and Technical Enhancements | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS |  | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | TRUE | Budget: 4.255M • Large number of SAMS business and technical enhancements and fixes for complex production known errors. • Business Analysis and architectural support for SAMS releases and Intake activities • SAMS release Integration and End to End test planning, coordination and execution as well as regression testsuite upgrades and automation | Can description field be accurately summarized into 1-3 sentences? If so, that would be ideal. DONE | Deliver defect fixes and enhancements for various SAMS functional areas in a flexible and responsive way jointly prioritized with business |  | Ministry LOA | N/A | Confirmed | On Backlog |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A066 | SA Digital: SAMS-RBED (1.0 and 2.0) Enhancements and Maintenance | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS |  | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | TRUE | Enhancements and defect fixes to the RBED (1.0-Intake, 2.0) capabilities that have been built so far. This includes: - Addition of new small non complex information sources for RBED 1.0 - RBED 1.0 rules refinement (e.g., expand rules to put through additional case types through auto-grant without manual intervention) - PTRA and Trigger Solution |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed | On Backlog |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A067 | SA Digital: SAMS-EDM Maintenance, Enhancements and Support | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS-EDM |  | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division;#I&IT Technical Delivery Division | TRUE | Covers non-functional enhancements such as performance and scalability challenges (search screen, etc.) as well as fixing known issues and small enhancements |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed | On Backlog |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A068 | Curam 8 Upgrade Implementation | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance;#Security Compliance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS;#EA;#EST;#MyBenefits;#SADA;#SALIS;#2WAYMessaging | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | CMO - Cluster Management Office;#IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division | TRUE | Upgrade SAMS from the current version (7) to version 8. | Please provide a more detailed description of the work (aim for 1-3 sentences). | Create opportunity to embrace new Curam 8 functionality. Potentially extend the life of the technology asset. | Not specified | Cluster Base Budget |  | Confirmed | In Progress | Confirmed |  | Removed MDCF indicator (Meg) | 2023-01-24 | 2023-11-30 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A069 | SA Digital: EST Maintenance & Support | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | EST | N/A | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division;#MLTSD Cluster | FALSE | Support and maintain Employment Service Transformation (EST) application. |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A070 | SA Digital: MyBenefits Maintenance & Support | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | MyBenefits | N/A | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | Support and maintain MyBenefits |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A071 | SA Digital: SADA Maintenance & Support | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SADA | N/A | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | Support and maintain SADA. |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A072 | SA Digital: Messaging Maintenance & Support | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | 2WAYMessaging | N/A | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#GSIC - Government Services Integration Cluster;#BIPD - Business Intelligence & Practice Division | FALSE | Support and maintain Messaging. |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A073 | SA Digital: Digital DDP maintenance | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | DDDP | N/A | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#HSC - Health Services Cluster | FALSE | Maintain DDDP. |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A074 | Emergency Assistance Maintenance and Support | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | EA | N/A | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Maintain EA. |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A075 | SAMS Chrome Extension Manifest V3 upgrade | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS |  | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division;#BIIB - Business Innovation & Implementation Branch | FALSE | For all SAMS OPS and BPS users, upgrade their computers' Chrome Extension to the Manifest V3 supported version, before Manifest V2 reaches end of life in 2023. | [6 empty] | Complete/Operationalized | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A076 | SAMS CPP cost of living increase activities (annual) | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On;#Ongoing Business Operations | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | N/A | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Adjust cost of living increases in SAMS annually, including the mock run and actual implementation. |  | Yearly activity to ensure CPP cost of living increases are reflected against social assistance recipients entitlements. |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  | Removed MDCF indicator (Meg) | 2023-10-01 | 2024-01-01 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A077 | SAMS December pay-run date changes (annual) | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On;#Ongoing Business Operations | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | N/A | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE |  |  |  | Legislation | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  |  | 2023-12-01 | 2023-12-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A078 | SAMS T5 issuance (annual) | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On;#Ongoing Business Operations | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | N/A | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE |  |  |  | Legislation | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  |  | 2023-08-01 | 2024-02-01 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A079 | SAMS TCB annual reconciliation process (annual) | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On;#Ongoing Business Operations | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | N/A | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE |  |  |  | Legislation | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-01 | 2023-07-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A080 | Move SAMS builder from KDC to GDC | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33;#Stoicescu, Valentin (MCCSS);#23 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | Move the SAMS builder from the Kingston infrastructure to the Guelph Data Centre infrastructure. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed |  |  | 2022-07-01 | 2023-07-01 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A081 | Environment coordination and third-party testing | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | N/A | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | Manage the coordination of third part testing activities as well as lower level environments for SAMS. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A082 | ITGC - Debt Administration Service (DAS) | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Requirement | Run - Applications | Audit;#Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | DAS |  |  | Syed, Aleem (MCCSS) |  |  | CMO - Cluster Management Office;#Audit Team | FALSE | ITGC design effectiveness testing - Debt Administration System (DAS) | [6 empty] | Complete/Operationalized | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A083 | DAS, SD-Calc, CAMS, SAS, Office Locator, DAD maintenance and support | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SD-Calc;#CAMS;#SAS;#Office Locator;#DAD | N/A | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Provide standard support for DAS, SD-Calc, CAMS, SAS, Office Locator, DAD. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A085 | Enhance existing SAMS dev and deployment pipeline | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Continue to improve the maturity of the SAMS production deployment pipeline for example automated front end validation and pipe line to pipe line integration with SA Mod application. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A086 | Transition to Operations (TTO) of Digital Applications to IOB | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | Digital Applications |  | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Transition to operations of Digital Applications to IOB. | [22 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A089 | Emergency Assistance Migration to GoCloud | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | EA | Advance Our Technology Platforms | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Migrate EA hosting from on-prem to public cloud. |  | * Scalability of public cloud hosting platform to any surge in user demand * Higher stability and availability of public cloud hosting platform * Scaling of hosting cost based on usage * Alignment of EA application hosting architecture with other SA digital applications enabling leveraging of resource pool for application support |  | Other | N/A | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A090 | Options analysis for alternative to Pivotal Cloud Foundry (PCF) for Digital Applications | Carried forward from 22/23 OpPlan | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | Digital Applications | Advance Our Technology Platforms | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | Analyze options for an alternative to Pivotal Cloud Foundry (PCF) for Digital Applications. |  |  |  | Other | [6 empty] | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A091 | ITGC - Digital Disability Determination Package | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Requirement | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | DDDP |  | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | CMO - Cluster Management Office;#Audit Team | FALSE | ITGC design effectiveness testing - DDDP. | [8 empty] | Need clarification from CMO | [13 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A093 | DSCIS OPS/BPS Secure Implementation | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Grow | DS - Developmental Services | SCSI - Shared & Community Services I&IT Solutions | DSCIS |  | Chan, Harry (MCCSS);#26 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Modernize existing secure access for DSCIS as part of the OPS Enterprise Identity and Access Management (EIAM) initiative. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A094 | CPIN/OPSDocs Bulk Upload | Carried forward from 22/23 OpPlan | Approved | TRUE |  | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Wang, Cedric (MCCSS);#15;#Kugendran, Shanmugathasan (MCCSS);#19 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | SPP OPSDocs bulk upload capability. | The ability to upload multiple attachments to CPIN to reduce administrative burden on sector staff |  |  | SPP/MYP | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A095 | Oracle eBS 12.2 Upgrade | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions |  |  | Wang, Cedric (MCCSS);#15;#Kugendran, Shanmugathasan (MCCSS);#19 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#CMO - Cluster Management Office;#EAO - Enterprise Architecture Office | FALSE | CPIN's current version of Oracle eBS (e-business suit v12.1) has expired from vendor support. Developed a business case and A3 presentation for the Oracle eBS Upgrade. Currently circulating the upgrade path through ministry approvals | Currently working towards 2023/24 Q4 implementation in to prod. |  |  | Other | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A097 | OIAD R12 - Limit Use and Safeguard PI - CPIN Data Masking Assessment | Carried forward from 22/23 OpPlan | On hold | FALSE | Audit Recommendation | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions |  |  | Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | Scoping for data masking for implementation in the training and test environments is underway. More specific recommendations on how data masking will be incorporated following the pilot project for data masking PSSAH in fiscal year 23/24. | a) is to provide CAS's with the ability to audit who has accessed case information. This has been completed b) is a larger project led by IOB, to mask data in lower level environments to protect private information | [5 empty] | On Backlog |  | a) is completed b) Part of a larger IOB initiative - data masking There should be a secondardy item to track Data Masking | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A098 | CPIN - Culturally Appropriate Language | Carried forward from 22/23 OpPlan | Approved | TRUE |  | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | SPP Sector requirement to update CPIN with culturally appropriate language that will be foundational work for Child Welfare Redesign. | CWOB is working with the sector to update terminology to be more culturally appropriate |  |  | SPP/MYP | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A099 | CPIN Automation Testing - CM | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Set up an automated process for all releases to significantly reduce the testing time during regression cycles for testing activities such as: projects, smoke testing, integration testing, bug fixes related to CM, FM and Reports | We are working on a project plan and implementation of devops to support work |  |  | Cluster Base Budget | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A100 | OPSDocs Migration Planning (CPRI) | Carried forward from 22/23 OpPlan | Approved - with changes | FALSE |  | Transform | Transform | SN - Special Needs | CYIS - Children & Youth I&IT Solutions |  |  | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) | Dan Grandchamp |  | SCSI - Shared & Community Services I&IT Solutions;#Other | FALSE | Plan the migration of CPRI file servers to OPSDocs. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A106 | CYSSC OPSdocs Pilot | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Grandchamp, Dan (MCCSS);#29 | Awad, Mohamed (MCCSS) |  |  | CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions | FALSE | Implement OPSdocs for the cluster to develop an efficient process and gain experience in deploying it | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A107 | Develop & Implement Manager's Accessibility Toolkit, Training & Workbook | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Grow (Enhancements) | Grow | ACOE - I&IT Accessibility Centre of Excellence | SCSI - Shared & Community Services I&IT Solutions |  |  | Dabideen, Mala (MCCSS);#30 | Awad, Mohamed (MCCSS) |  |  | CAC - Central Agencies Cluster;#TBS - Treasury Board Secretariat;#ITS - Infrastructure Technology Services | TRUE | Create a manager's guide to supporting their staff in understanding their Digital Accessibility obligations and available resources, supports and tools. | [22 empty] | Not approved |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A109 | ACOE: Chair & Lead Organizer of Digital Accessibility cross-Ministerial and cross-Cluster Committees and CoP | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Applications | Run | ACOE - I&IT Accessibility Centre of Excellence | SCSI - Shared & Community Services I&IT Solutions |  |  | Dabideen, Mala (MCCSS);#30 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Chair of Digital Accessibility Advisory Group (DAAG) compromised of business & technical representatives at Team Lead and Management levels; representation from CAB, ODS, ITS, CAC, TBS, ACOE, SOLGEN. Chair of Developers Accessibility Community of Practice (DACP) which hosts over 50 regular members of Developers and other Technical professionals across the OPS. | [9 empty] | Added ACOE to front of name | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A111 | Lead the development of MYAP OPS Web Literacy Plan | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Grow (Enhancements) | Grow | ACOE - I&IT Accessibility Centre of Excellence | SCSI - Shared & Community Services I&IT Solutions |  |  | Dabideen, Mala (MCCSS);#30 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | As part of the new MYAP, OAO has requested ACOE parternship on the OPS Web Literacy Plan Comittment. | Please provide a description of the work to be done (aim for 1-3 sentences). | [21 empty] | Not approved |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A112 | Implement Comprehensive and Timely PIAs to Support Privacy Management and Decision-Making | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Requirement | Grow (Enhancements) | Grow | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions |  |  | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office | FALSE | Final SAMS PIA Report and Mitigation plan to be developed. | Is the work to develop the final plan? If so, can we change the wording to say "Develop the final SAMS PIA report and mitigation plan"? | [21 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A113 | Limit Use and Safeguard PI in Systems, Test Environments and Minimize Access to PI | Carried forward from 22/23 OpPlan | On hold | FALSE |  | Grow (Enhancements) | Grow | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS |  | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | TRUE | Assess opportunity to build reports within core systems to meet user needs instead of extracting the data. | [6 empty] | On Backlog | Tentative - pending funding | [14 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A115 | CAMS - IAM (BPS Secure) Integration Assessment | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Applications | Run | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CAMS |  | Wang, Cedric (MCCSS);#15;#Pawlowski, Walter (MCCSS);#36;#Acuna, Oscar (MCCSS);#35;#Kugendran, Shanmugathasan (MCCSS);#19;#Torrance, Tyler (MCCSS);#37 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Assess migration from Go Secure to BPS Secure | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A116 | Decommission Old Child Abuse Register | Carried forward from 22/23 OpPlan | On hold | TRUE | CYSSC Strategy;#Business Modernization/Transformation | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CAR | Advance Our Technology Platforms | Pawlowski, Walter (MCCSS);#36;#Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) | Bryce, Don (MCCSS) |  | CMO - Cluster Management Office;#EAO - Enterprise Architecture Office | FALSE | SPP Create a complete, net-new solution to replace the current CAR system using modern, cloud-enabled technology and Java tool set or decommission the CAR system. |  |  |  | SPP/MYP |  | Tentative |  |  | Part of SPP ask Also, waiting to hear what the direction of CAR should be We need to work on moving the server from KDC to GDC | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A117 | Assessment of Consolidation of Non-Indigenous CASs into the Province's Consolidated Financial Statements | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions |  |  |  | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | Chart of Accounts Consolidation | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A118 | Adoption and Crown Ward Imaging System (ACWI) - Replacement | Carried forward from 22/23 OpPlan | On hold | TRUE |  | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | ACW/I |  | Wang, Cedric (MCCSS);#15;#Pawlowski, Walter (MCCSS);#36 | Kabiawu, Joachim (MCCSS) |  |  | CMO - Cluster Management Office;#EAO - Enterprise Architecture Office | FALSE | SPP Replace the legacy ACW/I document management system with an enterprise service offering through OPSDocs. |  |  |  | SPP/MYP |  | Tentative |  |  | Part of SPP ask | Consider renaming this one because "decommission" might be misleading | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A119 | Adoption Crown Ward System (ACW) - Replacement | Carried forward from 22/23 OpPlan | On hold | TRUE |  | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | ACW |  | Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) |  |  | CMO - Cluster Management Office;#EAO - Enterprise Architecture Office | FALSE | SPP Replace the legacy ACW system with a complete, net-new solution, using modern cloud-enabled technology and Java tool sets. |  |  |  | SPP/MYP |  | Tentative |  |  | Part of SPP ask | Consider renaming this one because "decommission" might be misleading | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A129 | Customary Care Changes in CPIN | Carried forward from 22/23 OpPlan | Approved | TRUE |  | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | SPP Ensure CPIN is reflective of customary care services for Indigenous and FNIM communities. | To ensure that CPIN functionality and terminology aligns with Customary Care requirements and spirit |  |  | SPP/MYP |  | Tentative | [16 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A132 | Operational sustainment for OAP with AccessOAP (Data migration) | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions |  |  | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | Support OAP in the assessment of technology transition to Independent Intake Organization. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A133 | CPRI FCIS KIDS/ IDEASWEB Software Replacement Strategy and Planning | Carried forward from 22/23 OpPlan | Approved | TRUE |  | Transform | Transform | SN - Special Needs | CYIS - Children & Youth I&IT Solutions |  |  | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#TBS - Treasury Board Secretariat | FALSE | Develop a strategy to replace CPRI's client information system and to transfer multiple legacy applications through a new, integrated solution, particularly FCIS KIDS and Ideasweb. | Can we make the Work Item Name a bit clearer? Maybe "Software Replacement Strategy for CPRI Client Information System and Other Legacy Applications" |  | Not specified;#MYP/SPP/TB approved | [5 empty] | In year TB submission, risk managed by Ministry in the event of TBS not funded | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A134 | HCD-ISCIS Modernization Project Phase 2 (IH Forms and API) | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Transform | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | HCD ISCIS | Advance Our Technology Platforms | Cunningham, Nicki (MCCSS);#20;#Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) | Enterprise Architecture Office | Operational Branch | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#GSIC - Government Services Integration Cluster | TRUE | Digitize Universal Newborn Hearing Screen (UNHS), Build external Interfaces | 22/23 OpPlan had ETD-SUS for support required. Can you confirm what ETD-SUS stands for please? Enterprise Technology Division - Shared Utility Service | Reduce Redundant Data Entry: Digitizing the UNHS will reduce manual data entry. Reduce Fax Transmission: A digitized UNHS will enable direct upload into HCD-ISCIS and will eliminate the need for faxing (except as used as a back-up). Meet Early Intervention Targets: Data transmission in almost real-time will enable staff to provide faster access to services and interventions and help meet the goals of early intervention. Cost and Time Reduction: Currently, the cost associated with a paper-based system for UNHS is approximately $280,000 per year. This is inclusive of the cost of one year’s supply of paper, the cost of faxing, and the administrative cost of entering the results into HCD-ISCIS. In addition to cost savings, a digitized UNHS form would save IHP Lead Agencies an estimated 8,500 hours of administrative time per year. HCD-ISCIS modernization has been focused on the Infant Hearing Program in 2021-22 and 2022-23. One of the original objectives of the HCD-ISCIS Modernization initiative is to reduce duplicate data entry and decrease indirect client time for all of the programs administered in HCD-ISCIS. | MYP/SPP/TB approved | SPP/MYP | 22/23 – Early Intervention and Special Needs Modernized Technology Foundation | Confirmed |  |  | This is part 2 of phase 2 of project. | [13 empty] | Approved by director | 100018797 |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A137 | Addressing Anti-Black Racism in GovTechON Action Plan | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Garant, Kelly (MCCSS);#12;#Tolentino, Abigail (She/Her) (MCCSS);#54 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#OCIO - Office of the Chief Information Officer;#GovTechON | FALSE | Action, monitor and report on the GovTechON Anti-Black Racism Action Plan Metrics |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A141 | CYSSC Achieving Equity Working Group and Action Plan | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Garant, Kelly (MCCSS);#12;#Tolentino, Abigail (She/Her) (MCCSS);#54 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#OCIO - Office of the Chief Information Officer | FALSE | The Achieving Equity Working Group is working to make CYSSC an organization free from racism and systemic barriers. Using media, events, and training, we seek to educate each member of CYSSC and ensure that each member of CYSSC understands that they are of value |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A142 | FRO Digital Statement of Arrears and Interest Calculator - Phase 2 | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Transform | FRO - Family Responsibility Office | SCSI - Shared & Community Services I&IT Solutions | FRO Online | Advance Our Technology Platforms | Wright, Peter (MCCSS);#28 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Expand on the minimum viable product (MVP) we currently have in place: -Further iterate on the SOA Calculator's MVP -Build out the digital framework to scale and support other digital forms -Develop further digital integration to minimize manual processing | [9 empty] | Marked as MDCF (Meg) |  | 2023-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A143 | SA Digital: SAMS - RBED 2.0: Alert Solution + Automated Loss Prevention | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Must-Do-Can't-Fail;#Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | Advance Our Technology Platforms | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | TRUE | Enhance SAMS to support ongoing eligibility, including: - Alert Solution (Enhanced eligibility verification process) - Automated loss prevention framework |  | Enhanced Eligibility Verification Process (Alert Solution): to complement and further strengthen ongoing eligibility monitoring and program integrity by repurposing and enhancing the current EVP risk assessment model​ Loss Prevention Framework: to complement and strengthen the acceleration of risk-based, technology enabled and client-focused program | MYP/SPP/TB approved | SPP/MYP | 23/24 – Social Assistance Digital Delivery | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A144 | SA Digital: SAMS - Electronic Document Management (EDM): Transform Scope | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Must-Do-Can't-Fail;#Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS-EDM | Advance Our Technology Platforms | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#I&IT Technical Delivery Division;#BIPD - Business Intelligence & Practice Division | TRUE | a. Digital Integrations (scale EDM service); b. Expansion of E-forms Capabilities; c. Expansion to OW and Centralized Services; and d. Document Assignment Logic Refinement. |  | Project allows for digitization of a client’s file and new incoming mail for retention, including imaging, electronic storage, and retrieval of documentation for ODSP and OW partners. EDM reduces the amount of data entry and paper handling time and enables staff to access files without needing to search through a file room or internal mail system. EDM includes Digital Day 1, which allows staff to scan documents that have been dropped off by clients. Files are immediately digitized and connected to the client’s file, improving response time to client inquires.​ | MYP/SPP/TB approved | SPP/MYP | 23/24 – Social Assistance Digital Delivery | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A145 | SA Digital: EST Product Backlog Enhancements | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Must-Do-Can't-Fail;#Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | EST | Advance Our Technology Platforms | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#LTC - Labour and Transportation I&IT Cluster;#BIPD - Business Intelligence & Practice Division | FALSE | Enhance Employment Service Transformation (EST) application. |  | * Common Assessment (CA) Re-administration: Tracks changes in a client’s life stabilization needs and outcomes over time in a consistent and measurable way. Helps identify gaps in life stabilization services and inform system-wide resource allocation across the broader human services system. * Expansion of the CA Tool and Action Plan: Enables the delivery of life stabilization services through the provision of case management tools to caseworkers. Rollout of the tools provincially will prepare sites for onboarding to Integrated Employment Services (IES) as EST sites are phased in. * Service Level Determination: Introduces capabilities to track client progress for those that are close to the labour market and may only need low touch or self-directed services from EO. * EST Provincial Rollout: Rollout three additional stages of EST, which include major sites, such as Toronto and Ottawa. Complexity will differ from earlier prototype implementations and may include additional integration work to provide data in a format for municipal peripheral systems. * Participation Benefits: Introduction of a new participation benefit which will provide more flexibility for life stabilization service delivery. * Life Stabilization Provider POC: This is renamed to Simplified e-Referrals for Stability Supports to match policy wording. This provides an electronic method for caseworkers and clients to access community service providers and send/receive referral requests for stability supports to ensure clients become ready for employment. Technical design and proof of concept will be completed with enhancements to EST technologies. * Case Management Tools to Support Decision-Making for Caseworkers: Automated decision-support tools for case workers to support service delivery (e.g. assessing employment readiness decisions; providing client profiles to review demographics and potential supports needed, etc.). | MYP/SPP/TB approved | SPP/MYP | 23/24 – Social Assistance Digital Delivery | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A146 | SA Digital: MyBenefits Product Backlog Enhancements | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Must-Do-Can't-Fail;#Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | MyBenefits | Advance Our Technology Platforms | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | Enhance MyBenefits application |  | * Integration with MyBenefits, Identity Verification Service, Public Secure: These integrations will enable a connected and seamless experience across different digital solutions for Ontarians. For social assistance clients, it will expedite the application process and access to benefits, and from a system perspective, it will improve infrastructure security. For example, MyBenefits integration with the enterprise Identity Verification Service (IVS) and Public Secure solutions, will enable social assistance applicants/recipients to leverage the samedigital ID & login across different govt. services. Similarly, the integration with MyBenefits will provide a seamless re-application process for eligible former recipients, completed directly through MyBenefits. Allows for workflow efficiencies for staff, greater transparency and accountability, and an easier re-application process for recipients. The integrations will reduce wait time, increase access to services and reduce the need for applicants to travel into local offices, among other benefits. * Trustee and Spousal Access:Providing access to trustees of one client, multiple clients, and clients who are also trustees, to be implemented iteratively through an MVP/co-design approach. Providing access to spouses (note, level of access is to be determined). There are over 50,000 social assistance recipients with trustees who will benefit from self-service access to support our most vulnerable recipients. * Application for Additional Benefits:Allows recipients to access, complete and submit high-volume benefit requests digitally via MyBenefits, reducing wait times for recipients and workload for staff. * E-forms: Enabling recipients to access high-volume forms directly from their MyBenefits account. Will reduce time required by staff to complete form requests. Auto-complete options within MyBenefits will ensure correct client identification information is recorded on eachform and further reduce client wait times from 72 hours to under 2 minutes. * Income Reporting Enhancements: Will allow clients to change employer information and report income against a new employer via MyBenefits. Information will update in SAMS through MyBenefits integration. Will eliminate need for client to contact caseworker to manuallycomplete update. Other features include reminding clients of ‘unreported income’ through MyBenefits notifications, which will improve on-time reporting of income, as well as reduce monthly benefit suspensions and follow-up work by staff. | MYP/SPP/TB approved | SPP/MYP | 23/24 – Social Assistance Digital Delivery | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A147 | SA Digital: SADA Product Backlog Enhancements | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Must-Do-Can't-Fail;#Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SADA | Advance Our Technology Platforms | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | FALSE | Enhance SA Digital Application (SADA) |  | * Expansion - Additional Social Assistance Applications: Expand service to include all applications currently available in the legacy online application (ODSP, Temporary Care and Assistance for Children with Severe Disabilities - ACSD), ensuring all programs are able to access the simplified online application, improving access to services and streamlining processes for staff. This also reduces the need for in-person office visits and phone calls * MyBenefits and Messaging Integration: Improves experience for re-applicants. Supports ODSP referrals from Ontario Works. * Document Upload: Gives applicants an opportunity to provide verification of information at the time of submission (i.e. improved access to services through digital features). Strengthens accountability without extending the amount of time it takes to apply. * Application Status Update: Reduces applicant’s anxiety by enabling self-serve option to check the status of their application online. Diverts calls from the central intake team and makes the process more transparent for client. * ODSP One-Door Entry: Improves experience, reduces barriers and creates efficiencies for ODSP applicants. Applicants can start with Ontario Works application and automatically be bridged to ODSP based on their situation. Supports SA vision and Ontario Digital Service recommendations to streamline & centralize access to services based on identified user need(s). * Emergency Assistance Integration: Supports program vision of streamlining and centralizing access to services. Enhances the client experience by automatically providing the best option for assistance based on an individual’s situation. * Simplified Re-applications: Provides a seamless re-application process for eligible former recipients (e.g. ability to confirm that existing info on file is accurate and only report new information or changes). Enables workflow efficiencies for staff (e.g. reduces time spent on handling duplicate evidence). | MYP/SPP/TB approved | SPP/MYP | 23/24 – Social Assistance Digital Delivery | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A148 | SA Digital: Messaging Product Backlog Enhancements | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Must-Do-Can't-Fail;#Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | 2WAYMessaging | Advance Our Technology Platforms | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#GSIC - Government Services Integration Cluster;#BIPD - Business Intelligence & Practice Division | FALSE | Enhance Messaging application |  | * Conversation View: Providing a simplified chain of communications between caseworkers and clients. Copying other communication formats (e.g. e-mail, messenger, etc.). Feature is estimated to improve digital uptake and usability of the service. * Message Forwarding: Allowing staff the capabilities to forward a message to another caseworker for actioning (note, this is a popular request from operations staff). Will streamline services, support staff better in decision-making, and allow for better coverage across case management (e.g. during vacations, sick days, etc.). * Broadcast Messaging: Enables corporate and local office staff to easily send mass communications to target audiences (e.g. to only clients seeking employment, or to only clients with children, etc.). Targeted messaging will improve responsiveness and reduce complexity of program for clients. * Contact Centre Queue Model: Leverages the Contact Centre to manage incoming messages & attachments in a queue and respond to low-level inquiries and forward complex inquiries to caseworkers/centralized processing teams. Integration opportunities with EDM & MyBenefits workflows to effectively manage evidence & document attachments * Digital Integrations (likely integration with SADA and Digital DDP) : Integration of SADA and MyBenefits will provide a seamless experience for applicants and clients through all stages of their social assistance journey. It will lay the groundwork for future features | MYP/SPP/TB approved | SPP/MYP | 23/24 – Social Assistance Digital Delivery | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A149 | Ontario Digital Service Digital Identity - Online ID Proofing | Carried forward from 22/23 OpPlan | Approved | TRUE | Business Modernization/Transformation | Transform | Must-Do-Can't-Fail;#Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SADA | Advance Our Technology Platforms | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ODS - Ontario Digital Service;#GovTechON | FALSE | Implement online ID proofing capability within SADA. Online ID proofing capability to be developed by CAC. |  |  | MYP/SPP/TB approved | SPP/MYP | 23/24 - Digital Identity: Integration of Social Assistance Digital Application (SADA) with the Identity Verification Module (IVM) | Confirmed |  |  |  |  | 2023-10-01 | 2025-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A151 | 2022 OAGO VFM Audit of the OCCIO | Carried forward from 22/23 OpPlan | On hold | FALSE | Audit Requirement | Run - Cluster Services | Audit;#Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#D'Annunzio, James (MCCSS);#95;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (MCCSS) |  |  | CMO - Cluster Management Office | FALSE | Coordinate CYSSC response to OCCIO Action Plans addressing the OAGO Audit Recommendations: 2022 VFM Audit of the OCCIO |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  | Progress status should actually be Pending. Added Audit Requirement as a driver. | 2023-04-03 | 2024-03-29 | Develop CYSSC Action Plans in Support of the OAGO Audit Recommendations: 2022 VFM Audit of the OCCIO | Pending | [8 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A152 | Mental Health Action Plan | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Kernohan, Neill (He/Him) (MCCSS);#41;#Whibley, Alex (MCCSS);#42 | Garant, Kelly (MCCSS) | MCCSS HRSBU |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Implement and maintain the cluster's Mental Health Action Plan, including countermeasures |  |  |  | Cluster Base Budget | N/A | Tentative | Ongoing Work | Confirmed | This is an ongoing piece of work that started in 2021 |  | 2021-01-04 | 2024-03-31 | Deliver mental health communications and discussions at events | Ongoing Work | Implement mental health countermeasures | In Progress | [6 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A153 | CYSSC Events | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Kernohan, Neill (He/Him) (MCCSS);#41;#Whibley, Alex (MCCSS);#42;#Robles, Jemmie (She/Her) (MCCSS);#83;#Tolentino, Abigail (She/Her) (MCCSS);#54 | Garant, Kelly (MCCSS) | CLT | Cluster EAs | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Curate and host bi-monthly all-staff meetings. Curate and deliver the annual Learning and Engagement Week. Curate and coordinate monthly CELTs with one in person quarterly. |  |  |  | Cluster Base Budget | N/A | Confirmed | Ongoing Work | Confirmed | This is year over year work |  | 2023-04-01 | 2024-03-31 | Deliver CYSSC All-staff meetings | Ongoing Work | Deliver CELT meetings | Ongoing Work | Deliver Learning & Engagement Conference | Pending |  |  |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A154 | Employee Experience Survey | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Kernohan, Neill (He/Him) (MCCSS);#41;#Whibley, Alex (MCCSS);#42;#Robles, Jemmie (She/Her) (MCCSS);#83 | Garant, Kelly (MCCSS) | CLT |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Review the CYSSC results from the EE survey; develop and host deep dive sessions with CLT and cross functional & specific teams (e.g, women management), identify areas for improvement and develop an action plan, make recommendations to CLT and Implement approved action plan. Prepare communications for OPS EE survey launch and when results available. |  |  |  | Cluster Base Budget | N/A | Confirmed | Ongoing Work | Confirmed | Ongoing work year over year |  | 2023-04-01 | 2024-03-31 | Manage ongoing communications about EES results | Ongoing Work | Participate on MCCSS EES working group | In Progress | Develop and implement action plans for EE survey results in CYSSC | In Progress |  |  |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A155 | 2023/24 Operational Plan | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Whibley, Alex (MCCSS);#42;#Jarvis, Meg (MCCSS);#10 | Garant, Kelly (MCCSS) | CLT | All staff | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Develop, update and maintain the 2023/24 Operational Plan. |  |  |  | Cluster Base Budget | N/A | Confirmed | In Progress | Confirmed |  |  | 2023-01-09 | 2024-03-31 | Deliver 2023/24 Operational Plan | In Progress | Maintain 2023/24 Operational Plan | Pending | Ongoing review of 2023/24 Operational Plan with CLT | Pending |  |  |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A156 | Review and Refresh Cluster Internal Governance Process | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Whibley, Alex (MCCSS);#42 | Garant, Kelly (MCCSS) |  |  | EAO - Enterprise Architecture Office | FALSE | Review and make continuous improvements to Cluster internal Governance Processes | This is a repeat with a countermeasure, should we remove it or keep and close the countermeasure at end of this fiscal? Or keep both? Will update this one once we agree. |  |  | Cluster Base Budget |  | Confirmed | [16 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A157 | CYSSC Performance Measurement | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Whibley, Alex (MCCSS);#42 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Develop and implement a cluster performance measurement and reporting framework. This includes work done on KIT and MDCF. (includes operational and strategic measurement side; e.g. A3 performance measuring, project, operational, etc.) | This is another one that is also a countermeasure so we should be consistent. | [21 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A158 | Governance Secretariat Support (CEOC) | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Whibley, Alex (MCCSS);#42;#Sparks, Sarah (MCCSS);#59 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE |  |  |  |  | Cluster Base Budget | N/A | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-01 | 2024-03-31 | Provide all secretariat support for CEOC | Ongoing Work | [8 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A159 | Planview Support and Operations | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Whibley, Alex (MCCSS);#42;#Sewcharran, Brandon (MCCSS);#92;#Fox, Jesse (MCCSS);#91 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Ongoing administrative support for Planview | [10 empty] | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A160 | Strategic Planning Process | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Cluster Services | Run | MCCSS - Ministry-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#Zhang, Jerry (MCCSS);#97;#Wong, Kenneth (MCCSS);#98 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Coordinate and support annual strategic planning process. | Carrie to create a new work item for Annual IT Funding Model and Adjustment. Digital Maturity piece of SPP to move over to EAO? |  | MYP/SPP/TB approved | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-09-01 | 2024-03-29 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A161 | Maintain and Support CYSSC Online, CMO SharePoint and Cluster SharePoint Requests | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | N/A | Whibley, Alex (MCCSS);#42;#Dogantzis, Rosie (MCCSS);#88;#Kelly, Danielle (MCCSS);#89;#Mayor, Hannah (She/Her) (MCCSS);#90 | Garant, Kelly (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE |  |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A162 | Develop and Support Ongoing Communications Products | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Whibley, Alex (MCCSS);#42;#Kelly, Danielle (MCCSS);#89;#Dogantzis, Rosie (MCCSS);#88;#Mayor, Hannah (She/Her) (MCCSS);#90 | Garant, Kelly (MCCSS) | OCIO | MCCSS CMB, GovTechON/OCCIO | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Develop and support ongoing communications products, including newsletter, training newsletter, annual report, CIO emails and videos, etc. |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A163 | Forecasting/Budgeting/TCO | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Develop and maintain the forecasts, KLTO, TCOs, including monitoring, forecasting, cashflow, year-end and financial updates to CLT. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A164 | Base Budget Review | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (MCCSS) |  |  |  | FALSE | Complete the Base Budget review exercise (January - June 2022). Ongoing process to be developed to determine IT Funding Model (ITFM) needs/make adjustments during MyP process. | This item is complete and should be removed from the 2023-24 Op Plan. |  |  | Cluster Base Budget |  | Confirmed | [6 empty] | Base Budget Review Completed | Complete/Operationalized | Process for ITFM Annual Adjustments | Complete/Operationalized | [6 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A165 | Transactional Processing | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office | eBill |  | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (MCCSS) |  |  |  | FALSE | Process transactions, including A/P, A/R, User Seat Billing, Client Recoveries |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A166 | Enterprise Risk Management Reporting | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Cluster Services | Run | MCCSS - Ministry-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#D'Annunzio, James (MCCSS);#95;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (MCCSS) |  |  |  | FALSE | Provide and coordinate quarterly updates to the MCCSS Risk Registry. |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-03 | 2024-03-29 | Q1 Report | Pending | Q2 Report | Pending | Q3 Report | Pending | Q4 Report | Pending |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A167 | Provide Audit Coordination and Support - Other Audits and Audit Supports | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Recommendation;#Audit Requirement | Run - Cluster Services | Audit;#Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#D'Annunzio, James (MCCSS);#95;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Provide coordination and support for all OAGO and OIAD audits which includes: working with branches to provide updates; monitoring progress; reporting, and; providing support to the OCIO for Sector Audit Committee meetings. Coordinates the annual Certificate of Assurance and OAGO Attestations. |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-03 | 2024-03-29 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A168 | Provide Ongoing Support for TB Submissions | Carried forward from 22/23 OpPlan | Approved | FALSE | Business Modernization/Transformation | Run - Cluster Services | Run | MCCSS - Ministry-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#Zhang, Jerry (MCCSS);#97;#Wong, Kenneth (MCCSS);#98 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Provide coordination and support for in-year Treasury Board submissions. | Carrie to create new work item on quarterly MPR and QSR to TB |  |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-03 | 2024-03-29 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A169 | Procurement Services | Carried forward from 22/23 OpPlan | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Nichol, Cindy (MCCSS);#43 | Garant, Kelly (MCCSS) | All Branches |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Coordinate and support all Cluster procurement and reporting requirements, including contribution to TB/MBC submissions where appropriate. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work |  | Ongoing work |  | 2023-02-07 | 2030-03-31 | N/A - ongoing work | [9 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A170 | Run the Student Recruitment Programs | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Panousis, Anita (MCCSS);#44 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE |  |  |  |  | Cluster Base Budget | N/A | Confirmed | Ongoing Work | [15 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A171 | Bargaining Agent Work | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Panousis, Anita (MCCSS);#44 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Coordinate and complete bargaining work for CYSSC. |  |  |  | Cluster Base Budget |  | Confirmed | [16 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A174 | Workforce Reporting | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Panousis, Anita (MCCSS);#44 | Garant, Kelly (MCCSS) |  |  |  | FALSE | Complete monthly workforce reporting. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | [15 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A175 | Business Continuity | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Panousis, Anita (MCCSS);#44 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Complete business continuity activities, including disaster recovery and call tree exercises. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | [15 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A176 | Joint Health and Safety | Carried forward from 22/23 OpPlan | Approved | FALSE | Legislation | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Panousis, Anita (MCCSS);#44 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Coordinate Joint Health and Safety for CYSSC at North York locations, including building leadership, management of fire warden and first aid training for the cluster and associated strategies. | [6 empty] | Ongoing Work | [15 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A177 | 23/24 Procurement Plan | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Nichol, Cindy (MCCSS);#43 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Develop, implement and maintain the 23/24 procurement plan for CYSSC. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress |  |  |  | 2023-02-07 | 2023-06-05 | Meet with SAIS Branch |  | Meet with CYIS Branch |  | Meet with SCSI Branch |  | Meet with IO Branch |  | Meet with EAO |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A181 | Software licence management | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Recommendation | Run - Cluster Services | Audit;#Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Kabiawu, Joachim (MCCSS);#14;#Syed, Aleem (MCCSS);#31;#Muñoz, Jairo (MCCSS);#18;#Obias, Joven (MCCSS);#21;#Nichol, Cindy (MCCSS);#43 | Garant, Kelly (MCCSS) |  |  |  | FALSE | CMO Procurement will work with Solution Branches and Operations Branch to strengthen the annual review of license usage to ensure licenses are reassigned or noted where staff have left the organization. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work |  |  |  | 2023-03-01 | 2024-03-31 | Outline current process for licence tracking and how licences are reassigned | Complete/Operationalized | Create tracker for Curam licences, including current term, cost and number of licences | In Progress | Create tracker for other licences, including current term, cost and number of licences | In Progress |  |  |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A187 | Cost centre and accounting code framework to ensure appropriate tracking of expenditures and capitalization | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Recommendation | Run - Cluster Services | Audit;#Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (MCCSS) |  |  |  | FALSE | CMO Controllership to develop a cost centre and accounting code framework to ensure appropriate tracking of expenditures and capitalization. CMO Controllership will work with branches to ensure that FFS timesheets and vendor invoices provide adequate detail to enable accurate classification. | Background: Vendor Risk Management Audit Recommendation - We recommend the ministry consider different classification for maintenance and enhancement costs to better track where the IT spend occurs and inform future business and procurement decisions. Appropriate classification to enable accurate capitalization of costs is also advised. The ministry should also consider allocating appropriate account codes and cost centres and ensure appropriate use of these codes in the SOWs, to enable tracking expense types for future use. Where applicable, the Ministry should consider obtaining vendor invoices which provide adequate detail to enable accurate classification. CMO Controllership to develop a cost centre and accounting code framework to ensure appropriate tracking of expenditures and capitalization. CMO Controllership will work with branches to ensure that FFS timesheets and vendor invoices provide adequate detail to enable accurate classification. February 2023 update - Work to begin in fiscal 2023-24. |  |  | Cluster Base Budget |  | Confirmed | On Backlog |  |  |  | 2023-09-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A189 | Recruitment strategy | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Panousis, Anita (MCCSS);#44 | Garant, Kelly (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | Includes ongoing recruitment assessment of ongoing recruitments and reporting, exploring options around future recruitments e.g., open location. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | [15 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A190 | CYSSC training strategy | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Panousis, Anita (MCCSS);#44 | Garant, Kelly (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | Develop and implement the 2023-24 CYSSC Training strategy inlcuding required procurements. This includes management of mandatory training and management of pluralsight licenses. This also includes leadership training and development. Has links to EHWW SO 1 & 2 countermeasures. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | [15 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A192 | Disaster Recovery Testing | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Panousis, Anita (MCCSS);#44 | Garant, Kelly (MCCSS) |  |  | IOB - I&IT Operations Branch;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Develop and conduct an approved Disaster Recovery Plan that includes roles and responsibilities, resource and facility requirements, key contact information and detailed step by step procedures pertaining to key applications including for all mission critical applications. Conduct annual Disaster Recovery Testing to validate the effectiveness of the Disaster Recovery Plan disaster. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | [15 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A193 | Gratitude and Recognition | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  | Evolve How We Work | Whibley, Alex (MCCSS);#42;#Robles, Jemmie (She/Her) (MCCSS);#83;#Mayor, Hannah (She/Her) (MCCSS);#90;#Kernohan, Neill (He/Him) (MCCSS);#41;#Fox, Jesse (MCCSS);#91 | Garant, Kelly (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | Develop an integrated program and implement the plan for gratitude and recognition in CYSSC |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | Work MCCSS on long service recognition catch up | In Progress | Develop a new approach to long service recognition in CYSSC | Pending | Develop and implement a recognition and possibly rewards program in CYSSC (gratitude project phase 2) | Pending | Make recommendation on future cadence of CIO emails (gratitude project phase 1) | In Progress |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A195 | Maturing CYSSC Vendor Management in the Cluster | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Recommendation | Run - Cluster Services | Audit;#Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Nichol, Cindy (MCCSS);#43 | Garant, Kelly (MCCSS) |  |  |  | FALSE | Manage policies and processes. Establish organizational governance and measure and report on vendor management performance, risk and knowledge transfer activities. |  |  |  | Cluster Base Budget |  | Confirmed |  |  | ongoing |  | 2023-03-01 | 2030-03-31 | CLT endorsement to establish working group to review current process and establish Cluster VM strategy | Complete/Operationalized | VM Working group to develop Cluster VM strategy | In Progress | Where applicable, incorporate risk assessments, KPIs and metrics into new tender documents and vendor contracts | Ongoing Work | Where KPIs and metrics applied, work with branches on reporting of key goals and etrics | Ongoing Work | Incorporate robust knowlege transfer deliverables with measurement into new tender documents and vendor contracts | Ongoing Work | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A196 | Engagement with Cyber Security | Carried forward from 22/23 OpPlan | Approved | FALSE | Security Compliance | Run - Cluster Services | Run | CYSSC - Cluster-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | Ongoing engagement with Cyber Security Division to align CYSSC and MCCSS needs with Enterprise Security policies and standards to help address potential cyber-threats. | Can this description be summarized into 1-3 sentences? | Lead and support the development of Security policies, standards, and procedures for CYSSC and MCCSS in conjunction with Cyber Security (CS) Division. Includes support of development and implementation of CS services. |  | Other | N/A | Tentative | Ongoing Work | Confirmed |  |  | 2023-04-03 | 2024-03-29 | Reaching out to Cyber-Security Division to provide input, guidance and assistance on matters related to Cyber-Security Threats | Ongoing Work | [8 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A197 | Enterprise Architecture Governance | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | EA - Enterprise Architecture | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | Review, endorse and approve projects through the Cluster Exec Operational Committee & Corporate Architecture Review processes; Participate in the OPS enterprise architecture governance committees (ARB) and architecture domain workgroups ; Provide review of Cluster and Corporate I&IT standards, policies and guidelines; Participate in EA Modernization planning and implementation; Provide early engagement on project solution architecture planning & guidance as needed | Can this description be summarized into 1-3 sentences? | Ensure Architecture design and deliverables align to OPS standard and industry best practices |  | Cluster Base Budget | N/A | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-03 | 2024-03-29 | Verify, validate and update EA intake forms | Ongoing Work | Perform AGP0 review on new initiatives | Ongoing Work | Perform AGP1, 2 and 3 review on initiatives | Ongoing Work | Updates to CEOC on AGP endorsement/approval for projects | Ongoing Work | Participation in Corporate ARB meetings for EA approvals of OPS projects | Ongoing Work | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A198 | CYSSC enterprise architecture program management | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Cluster Services | Run | CYSSC - Cluster-wide;#EA - Enterprise Architecture | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | Manage and oversee the CYSSC enterprise architecture program including Architecture Community of Practice | Can this description be summarized into 1-3 sentences? | Develop and maintain the EAO Mandate & Services profile, Cluster Architecture Principles, Advancing our Technology Platforms Strategic Direction. Ensure the ongoing operation of the Architecture Community of Practise (ACOP) for knowledge sharing, ongoing maintenance and promotion of architecture best practices, standards and training; Promote and raise awareness of architecture, roles and responsibilities, related tools and methodologies; Provide strategic advice to portfolio branches for Intake/feasibility analysis (e.g. SOAP) which includes review of conceptual solution scope, strategic alignment, potential solution option(s) and recommended option; Development of Cluster Enterprise Reference Architectures and usage patterns (as required) which are re-useable across solutions (e.g. mobile, BI/DA, cloud); Development of Cluster Architecture Baseline framework, plan and definition of roles and responsibilities to support Digital transformation roadmaps based on business strategy; Provide support & analysis for Application Portfolio Management and review against Ministry strategies /MYP & IT Roadmaps for horizontal opportunities |  | Cluster Base Budget | N/A | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-03 | 2024-03-29 | Regular monthly engagement with ACOP | Ongoing Work | Bi-weekly strategic direction working group (SDWG) meetings for ATP | Ongoing Work | Addressing countermeasures for SDWG-ATP | In Progress |  |  |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A199 | Corporate and Enterprise I+IT engagement and alignment | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Cluster Services | Run | Enterprise I&IT;#CYSSC - Cluster-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | Ensure cluster strategic alignment with Enterprise IT initiatives (TRIP Enterprise Technology Roadmap, ITS, CyberSecurity, IAM, ODS roadmaps) through ongoing engagement with enterprise stakeholder partners. |  | Ensure Ministry applications and solutions align with corporate I&IT guidelines and practices |  | Cluster Base Budget | N/A | Confirmed | Ongoing Work | Confirmed |  |  | 2023-04-03 | 2024-03-29 | Engagement with ODS on as-need basis based on project needs | Ongoing Work | Engagement with TRIP on as-need basis based on project needs | Ongoing Work | Engagement with Cyber-Security and ITS on as-need basis based on project needs | Ongoing Work |  |  |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A200 | OCIO Management and Operations | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | OCIO - Office of the Chief Information Officer |  |  | Carter, Ann (MCCSS);#45;#Derderian, Teena (MCCSS);#65 | Carter, Ann (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#CMO - Cluster Management Office | FALSE | Support the implementation of strategic, operational, and cultural divisional agenda, including timely advice and responses to internal and external divisional issues and requests. |  |  |  | Cluster Base Budget |  | Confirmed | [16 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A201 | SAMS Interactive Voice Response (IVR) support | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | SA - Social Assistance | SCSI - Shared & Community Services I&IT Solutions |  |  | Mackiewicz, Rick (MCCSS);#46 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Provide help desk support for IVR. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A202 | Consult & Implement of the Public Access Terminals (PAT) | Carried forward from 22/23 OpPlan | Approved | FALSE | Business Modernization/Transformation | Run - Cluster Services | Run | SA - Social Assistance | SCSI - Shared & Community Services I&IT Solutions |  |  | Mackiewicz, Rick (MCCSS);#46 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Provide consultation and implementation support services for implementation of the ODSP PAT. This is a client project that CSU is involved in support of IT component. The project was originally approved by Jan 17, 2017and was then put on hold due to the freeze of the whole OPS during 2017-18 and was re-started in May 2019. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A203 | ACOE Enterprise Supports & Services | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Run - Cluster Services | Run | ACOE - I&IT Accessibility Centre of Excellence | SCSI - Shared & Community Services I&IT Solutions |  |  | Dabideen, Mala (MCCSS);#30 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Providing Training, Consultations, Advice & Guidance, Accessibility Assessment best practice, newsletter and various digital accessibility events. Administration of ACOE InsideOPS site, Intake service and a suite of Testing Tools. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A204 | Tier-2 incident management and service fulfillment for 15 applications | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions | DSCIS;#ESMS;#ESMS-SPM;#KIDS-FCIS;#CPRI Pharmacy Application;#PEIS;#PSSAH;#TRVR;#MRM;#eBill;#SIS Reporting Tool Service;#Freedom of Information Request Management System;#Toronto Region Visitor Registration;#Counter Registration |  | Patrick, Christine (MCCSS);#47 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Tier 2+ service support for the following applications: Counter Registration, DSCIS, ESMS, ESMS-SPM, KIDS – FCIS, Pharmacy, PEIS, PSSAH, Toronto Region Visitor Registration application (TRVR), Freedom of Information (FOI) Request Management System, Ministry Resource Manager (MRM), eBill, SIS Reporting Tool Service | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A205 | Support accommodations | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Mackiewicz, Rick (MCCSS);#46 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | -Potential political Ministry re-organizations and/or office moves; - Co-location of future planned ODSP and OW offices; - MCCSS Realty accommodation plan. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A206 | Support telephony updates | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Mackiewicz, Rick (MCCSS);#46 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Planview ID: 100013849 | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A207 | Quarterly renewals of ministry computers | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Mackiewicz, Rick (MCCSS);#46 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Work with client to identify legacy assets, manage quarterly renewals. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A208 | Implement RM module in OPSDocs for RMU Phase 2 (regional offices ECM content) | Carried forward from 22/23 OpPlan | Approved | FALSE | Business Modernization/Transformation | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Grandchamp, Dan (MCCSS);#29 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Develop process, reporting requirements, complete pilot for subset of business function | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A209 | Support desktop modernization | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Grandchamp, Dan (MCCSS);#29 | Awad, Mohamed (MCCSS) |  |  | CMO - Cluster Management Office;#CWOB - Child Welfare Operations Branch;#CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#BIPD - Business Intelligence & Practice Division;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Oversee and co-ordinate activities related to end-user technology that is being upgraded, implemented or removed as part of the ITS Desktop technology road map. Testing of Windows 11 O/S with CYSSC Applications |  | Outcomes: Validation of the Widows 11 O/S being compatible with the CYSSC Applications | [10 empty] | Completing validation testing | In Progress | [8 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A211 | Advisory services: information management | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Grandchamp, Dan (MCCSS);#29 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Provide consultation, advice and guidance to the ministry as related to IM needs | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A212 | Develop IM tools to support IMU services | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Grandchamp, Dan (MCCSS);#29 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Developing IM tools/resources to support IMU services | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A214 | Email rationalization | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Mackiewicz, Rick (MCCSS);#46 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | OPS clean-up of unused emails to find efficiencies; reduce number of unnecessary accounts | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A215 | Support MCCSS implementation of enterprise applications/solutions | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Grandchamp, Dan (MCCSS);#29 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Enterprise Services Unit to provide guidance, consultation and onboarding support to OPS digital enterprise products for MCCSS programs when required. (e.g. eApprovals, BinderBrowser, OPSdocs eSignature) | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A217 | ACOE digital accessibility and testing modernization strategy | Carried forward from 22/23 OpPlan | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | ACOE - I&IT Accessibility Centre of Excellence | SCSI - Shared & Community Services I&IT Solutions |  |  | Dabideen, Mala (MCCSS);#30 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Streamline access to automated testing tools, checkers, and provide hands-on learning to conduct manual accessibility tests; simplify & standardize Accessibility Testing Report; enhance Testing service as a consultation - reduce time spent on conducting tests. Increase opportunities for engagement through Virtual Drop-in sessions with ACOE experts and training services / products. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A218 | Reduce dependence on consultants (SAMS VFM audit recommendation) | Carried forward from 22/23 OpPlan | Approved | FALSE | Audit Requirement | Run - Cluster Services | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions |  |  | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | SAMS VFM Audit 2015 Recommendation - To prevent unnecessary delays in bringing the Social Assistance Management System (SAMS) to full and effective functionality, and to ensure that the consultants still working on SAMS are held accountable for delivering quality results, the Ministry of Community and Social Services should on future projects, work towards reducing its dependence on consultants, and ensure consultants’ knowledge is transferred to ministry staff. Audit Tracker Recommendation VFM.17.15.03.12.02.03.2 OAGO recognize that the Ministry has completed the following: - has reduced its dependence on the consultants, - has developed the Knowledge Transfer framework, - has trained its staff on the Knowledge Transfer framework, - has made necessary changes to vendor contracts. - However, the Ministry has not provided documentation to support the use of KT framework (including, for example, any of the KT checklist, KT plan, knowledge share plan, KT tracking documentation and KT reporting) for knowledge transfer from a consultant to the Ministry’s staff. Based on the above, OAGO assesses this recommended action as “In process of being implemented” with an estimated implementation date of March 2021. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A219 | SDWG ATP - Architecture Intake and Review Engine (AIRE) | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | EA - Enterprise Architecture | EAO - Enterprise Architecture Office | AIRE | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | An automated BOT to generate EA intake forms based on the operational plan. Automates the initial review of Enterprise Architecture artifacts, produces a detailed compliance report which Enterprise Architects review and respond to. |  | Provides early visibility to the upcoming EA Governance pipeline and provide support at the right time for the Governance to projects. Also this helps solution teams to prioritize on the MDCF items |  | Cluster Base Budget | N/A | Confirmed | In Progress | Confirmed |  |  | 2022-04-01 | 2023-03-31 | Build initial version of AIRE to generate automated forms | Complete/Operationalized | Enhance product to look for changes on Operational Plan and UI | In Progress | [6 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
A220 | SDWG ATP - Lessons Learned Repository (ALDA) | Carried forward from 22/23 OpPlan | Approved | FALSE | CYSSC Strategy | Run - Cluster Services | Run | EA - Enterprise Architecture | EAO - Enterprise Architecture Office | ALDA | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | Build an automated bot to gather information from EA AGP3 documents on lessons learned and compile a knowledge exchange to be utilized by all teams in the cluster. Solutions teams will be required to reference ALDA information in all projects |  | Provides ability for project managers, managers, architects and other project staff to query on lessons learnt from various projects in the Cluster. Helps to prepare project plans for new initiatives or help to address issues that project teams might be facing with lessons learnt from past projects |  | Cluster Base Budget | N/A | Confirmed | In Progress | Confirmed |  |  | 2023-01-01 | 2023-03-31 | Build initial version of ALDA | Complete/Operationalized | Enhance project based on input and feedback from team | In Progress | [6 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B001 | PSSAH & PEIS Sustainment | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | PSSAH;#PEIS |  | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | TRUE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, database maintenance, and testing activities to support maintenance and anticipated enhancements of PSSAH & PEIS |  | Support continue operation of SSAH program |  | Cluster Base Budget |  | Confirmed |  |  | To be decommissioned once new application (TPON Phase 2) is online in next fiscal 2024-25 |  | 2023-04-03 | 2024-03-29 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B002 | Evergreening CYSSC Windows OS upgrades (Project) | New in 23/24 | Approved | FALSE | Application Evergreening;#Keeping the Lights On | Run - Applications | Run | CW - Child Welfare & Protection | IOB - I&IT Operations Branch | ACW/I;#CAR;#FCIS-KIDS | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | IOB to lead project. Multiple applications require OS upgrades up from 2012 by Oct 2023 - CARS, ACWi (and possibly others) |  |  |  | Cluster Base Budget |  | Confirmed | Pending | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B003 | OACIS & PEIS Migration to OPS Secure | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | OACIS;#PEIS |  | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#IAM - Identity and Access Management | FALSE | Migrate OACIS & PEIS IAM from current Go-Secure to the new Enterprise Solution OPS Secure | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B004 | FSI Modernization Project: PSSAH Data Cleansing and Migration | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Transform | Transform | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | PSSAH;#PEIS |  | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#Other | FALSE | Cleanse and Migrate required data from the existing PSSAH application to the new TPON application |  |  |  | Cluster Base Budget | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B005 | OAP Future state planning including OACIS decommissioning | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance;#Business Modernization/Transformation | Transform | Transform | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | OACIS |  | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division;#SCSI - Shared & Community Services I&IT Solutions;#EAO - Enterprise Architecture Office;#Other | FALSE | Planning for the next steps for OACIS & PEIS including roadmap planning, the eventual decommissioning and helping Autism Program with a view into historic files etc. |  |  |  | Cluster Base Budget | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B006 | SDWG - ATP Options Analysis, POC & SPP Business Case Development - CYSSC Service Mesh | New in 23/24 | Approved | TRUE | CYSSC Strategy | Grow (Enhancements) | Grow | CW - Child Welfare & Protection;#DS - Developmental Services;#FRO - Family Responsibility Office;#SA - Social Assistance;#SN - Special Needs | EAO - Enterprise Architecture Office | SAMS;#CPIN;#FCMS;#DSCIS | Advance Our Technology Platforms |  |  |  |  | BIPD - Business Intelligence & Practice Division;#CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#GSIC - Government Services Integration Cluster;#GovTechON | FALSE | Perform options analysis to determine SWOT of extending BIL as the Cluster's Service Mesh. ​ Complex applications are decomposed into a collection of small, independent services that communicate with each other through APIs.​ ​ Each service is focused on a specific business capability and can be developed, deployed, reused and maintained independently.​ ​ Minimal enhancement of existing applications e.g. SAMS, FCMS, CPIN, DSCIS ​Trace - Digital Transformation + Data Management Strategy |  | Horizontal IT systems integration to support CYSSC Portal - unified data ingestion + Life Course Approach + Tell Us Once | [5 empty] | Other | Resources required to complete this work | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B007 | SDWG ATP - Options Analysis, POC & SPP Business Case development - CYSSC Portal | New in 23/24 | Approved | TRUE | CYSSC Strategy | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  |  |  |  | CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#BIPD - Business Intelligence & Practice Division;#GSIC - Government Services Integration Cluster;#GovTechON | FALSE | Perform options analysis to determine SWOT of MyOntario Portal for CYSSC - MCCSS ​Trace - Digital Transformation + Data Management Strategy |  | Improve the experience of an Ontarian seeking MCCSS support and services.​ ​ Consistent User Experience: A standardized and consistent user interface for citizens to access services, regardless of the underlying technology or system being used.​ ​ Efficient Data Input: A simplify and streamline the process of entering and managing data by providing a centralized platform for data input, which can reduce errors and improve data quality.​ ​ Improved Citizen Engagement: Enhance the citizen experience by providing a single access point for all services and information, reducing frustration and improving engagement.​ ​ Increased Accessibility: Portals can provide easy and accessible information and services to citizens, regardless of their location or device, which can help organizations reach a wider audience and improve accessibility. | [6 empty] | Resources required to complete this work | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B008 | SDWG ATP - Options Analysis, POC & SPP Business Case development- ChatBot for IT Systems | New in 23/24 | Approved | TRUE | CYSSC Strategy | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  |  |  |  | CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#BIPD - Business Intelligence & Practice Division;#GovTechON | FALSE | Perform options analysis, POC to determine SWOT of implementing ChatBots to SAMS, CPIN, FCMS, DSCIS internally for staff ​Trace - Digital Transformation + Data Management Strategy |  | Increased efficiency: Automate routine tasks and provide quick and accurate responses to frequently asked questions, freeing up time for employees to focus on more complex tasks.​ ​ Improved customer experience: Provide 24/7 support and offer a convenient, user-friendly way for citizens to access government services, improving the overall customer experience.​ ​ Enhanced data collection: Collect data from citizens, such as feedback and survey responses, helping the government to better understand their needs and improve services.​ ​ Cost savings: Reduce the cost of providing services by reducing the need for manual labor, freeing up resources for other initiatives.​ ​ Improved access to information: Provide citizens with quick and easy access to information about government services and programs, reducing wait times and improving accessibility. | [6 empty] | Resources required to complete this work | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B009 | Analysis on Informatica Upgrade / v10.4 Extended Support (Project) | New in 23/24 | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | SAMS;#CPIN;#DAS;#HCD ISCIS | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CMO - Cluster Management Office;#SAIS - Social Assistance I&IT Solutions;#CYIS - Child and Youth I&IT Solutions | FALSE | The current Informatica v10.4 we use to provide data integration operations/data warehousing support for SAMS, CPIN, HCD ISCIS, DAS will expire on March 2024. |  |  |  | Cluster Base Budget |  | Confirmed | On Backlog | Confirmed | The vendor has provided an unofficial and high level estimate for a one year extended support cost of $85K (from April 1 2024 to March 31 2025). The cluster (through IOB's lead) has 2 options; (1) to project manage the Informatica upgrade in FY2023-24. The project might cause disruption to already planned cluster high priority projects in 23-24 requiring resource time from impacted solution teams, or (2) to buy the extended support for one year allowing the upgrade project sometime to plan and to avoid implementation conflicts with other priority initiatives. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B012 | EAO A192: Disaster Recovery Testing | New in 23/24 | Approved | FALSE | Keeping the Lights On | Run - Cluster Services | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | CPIN;#FCMS;#SAMS | Advance Our Technology Platforms | Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Disaster Recovery Exercises is an annual activity led by CMO Business Continuity unit to ensure that documented processes for resumption of services of mission-critical applications are tested and reported. In certain situations table top exercise is conducted in lieu of disaster recovery exercises. Either approach is supported by IOB. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B013 | SCSI B022: VQRP+ Transition Plan | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21;#Iqbal, Azhar (MCCSS);#24;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | This work item is contingent on SCSI leading the development of the plan to transition VQRP operational support from MAG to CYSSC. IOB will provide infrastructure and technology support expertise into the transition plans. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B014 | Lead the Social Assistance Extended Network Access (ENA) Decommissioning (Project) | New in 23/24 | Approved | FALSE | Keeping the Lights On;#Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Lead the decommission of the ENA circuits. Business Innovation & Implementation Branch, Social Assistance Policy, Planning & Innovation Division had asked for CYSSC to investigate the feasibility of decommissioning ENA circuits previously used by SAMS Case Workers in the municipalities following the successful SAMS migration to OPCS. SAMS is now accessible through the Internet (instead of the previous GoNET access only). The ENA circuits are now limited to providing only MCCSS-developed OSAP portal for Case Workers. |  |  |  | Ministry LOA |  | Unconfirmed |  | Tentative - pending ministry direction | Need support from SCSI (Rick M.) and SAIS. BIIB has requested to look into further savings by decommissioning the ENAs.&nbsp; If completed can save up to $500K/yr | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B015 | Cognos Fix Pack (FP) Upgrade (Project) | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | CPIN;#HCD ISCIS;#SAMS | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  | SAIS, CYIS solution teams | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Cognos v11.1.7 is used by HCD ISCIS, CPIN and SAMS applications. The current fix-pack 6 includes fixes to additional Log4j related vulnerability. Log4j is a high-severity vulnerability that needs to be remediated. Cognos infrastructure instances are separate between SAMS, CPIN and HCD ISCIS. This item will address the FP upgrade for all 3 application solutions at different times. |  |  |  | Cluster Base Budget |  | Confirmed | Pending | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B016 | CYIS A023: Application Support & Maintenance for all Child Welfare applications | New in 23/24 | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | CW - Child Welfare & Protection | IOB - I&IT Operations Branch | CAMS;#CPIN;#CPIN Reporting;#CPIN CM;#CPIN FM | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21;#Iqbal, Azhar (MCCSS);#24;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B017 | DSCIS Curam V8 Technical Upgrade | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Cluster Services | Grow | DS - Developmental Services | SCSI - Shared & Community Services I&IT Solutions | DSCIS | Advance Our Technology Platforms | Chan, Harry (MCCSS);#26 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Implementation of Curam V8, and supporting technologies (i.e. WebSphere, Oracle, Reporting Remediation) |  | Evergreening of the Curam Technology to retain support from the vendor. In turn, will help to reach industry standards for security and accessibility. |  | Cluster Base Budget |  | Confirmed |  |  |  | Changed Work Type to Grow (Meg) | 2022-12-01 | 2024-03-29 | Implementation | [9 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B018 | DSCIS Application Business & Maintenance Releases | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | DS - Developmental Services | SCSI - Shared & Community Services I&IT Solutions | DSCIS | N/A | Chan, Harry (MCCSS);#26 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Implementation of priortized Change Requests for the maintenanace to keep the application updated. |  | Multiple releases to ensure Policy and Business needs are aligned with the DSCIS application to support DSO programs and initiatives that provide effective programs for individuals and families | [8 empty] | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B019 | SharePoint Online: Delivery of corporate SharePoint services, website services intranet/extranet (support/maintenance/development) | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Cluster Services | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  | N/A | Patrick, Christine (MCCSS);#47 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | (1) Consultation and work to develop new intra-extranet sites in SharePoint Online that come in during the year via multiple Service Requests, including updates to functionality of existing sites (e.g. Diverse Interview Panel Program, Corporate Services Branch site, Indigenous Healing & Wellness Strategy (IHWS) site, etc.) (2) Responding to service requests to decommission unused sites throughout the fiscal |  |  |  | Cluster Base Budget |  | Confirmed | [16 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B020 | 2023-24 e-Bill Business & Maintenance Releases | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions | eBill | N/A | Patrick, Christine (MCCSS);#47 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Regular operational releases of prioritized items to support ongoing CMO operations. |  | Increased access to and management of information, resulting in improved business processes | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B021 | 2023-24 FOI Request Tracker (FRED) Business & Maintenance Releases | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions | Freedom of Information Request Management System |  | Patrick, Christine (MCCSS);#47 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Operational releases of prioritized items to support ongoing Access & Privacy Office, Business Planning and Corporate Services operations. |  | Increased access to and management of information, resulting in improved business processes | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B022 | VQRP+ Transition Plan | New in 23/24 | Approved | FALSE | Ministry Request | Grow (Enhancements) | Grow | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions | VQRP+ |  | Patrick, Christine (MCCSS);#47 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Victim Quick Response Program+ (VQRP) Database, is an application to support the program to fund services for eligible victims of crime, where no other recourse is available, in the immediate aftermath of a crime. The application is accessed through a network of approximately 50 Service Delivery Organizations (SDOs), nearly all of which are also funded through transfer payment agreements with MAG to deliver the Victim Crisis Assistance Ontario (VCAO) program. Program staff that use the application have transferred from MAG to MCCSS, but the application is currently being run by Justice Technology Services (JTS) The plan is to conduct an analysis to determine the suitability of transitioning the development and support of the tool from JTS to CYSSC. |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  | Changed Work Type to Grow (Meg) | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B023 | Develop Options Analysis Future of MRM | New in 23/24 | Approved | FALSE | Application Evergreening | Grow (Enhancements) | Grow | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions | MRM |  | Patrick, Christine (MCCSS);#47 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | Develop & Finalize the Options Analysis for MRM |  | MRM, a highly used legacy tool used for managing Ministry resources (meeting rooms, equipment, fleet vehicles, etc.) has been out of vendor support for a few years and is approaching end of life. Options analysis was started 2022/23 and will continue into Q1 of 2023/24 | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B024 | Chatbot as a Service | New in 23/24 | Approved | FALSE | Business Modernization/Transformation | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions | ChatBot |  | Dawoud, Safaa (MCCSS);#27 | Awad, Mohamed (MCCSS) |  |  | EAO - Enterprise Architecture Office | FALSE | To standardize chatbot service management across CYSSC Conduct option analysis for Chatbot Modernization Develop a POC to test and validate the recommended modernization option |  | Provide easy access with quick response time to key information resources to the CYSSC and MCCSS staff. Improve the interactive conversation with the cluster and ministry users ​ | [10 empty] | Options Analysis |  | POC for the recommended option | [7 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B025 | SAIS A068: Curam 8 Upgrade Implementation | New in 23/24 | Approved | FALSE | Application Evergreening | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21;#Iqbal, Azhar (MCCSS);#24;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Support the planning and implementation of SAMS Curam v8 upgrade. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B026 | SA Digital: SAMS-Match & Merge Enhancements and Maintenance | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS |  | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | TRUE | Maintain SAMS Automated Match and Merge functionality |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business |  | Ministry LOA | N/A | Confirmed | On Backlog |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B027 | SD Calc Refactoring | New in 23/24 | Approved | FALSE | Ongoing Business Operations | Grow (Enhancements) | Grow | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions |  | N/A | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | Refactoring the SD-Calc application to improve functionality and reduce technical complexity |  | Reduced manual work and improved system sustainment |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed |  |  | 2023-01-01 | [11 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B028 | Migrate Field Worker CESCR out of KDC | New in 23/24 | Approved | FALSE | Application Evergreening | Run - Applications | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Dawoud, Safaa (MCCSS);#27 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | As part of the Cloud Adoption Journey, the Kingston Data Centre (CAJ-KDC) project, the Kingston Data Centre is to be shut down. Applications hosted in KDC are required to move to new infrastructure by end of 2022/2023 fiscal year. FW DS are both hosted in KDC, so these two applications have to be moved to another infrastructure. |  | Solution will be moved to the Cloud | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B029 | Secure Letter Storage Service | New in 23/24 | Approved | FALSE | Audit Requirement | Grow (Enhancements) | Audit;#Grow | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#EAO - Enterprise Architecture Office | TRUE | Move SAMS letters into a secure storage solution in order to better protect client information and meet TRA cyber security requirements |  | More secure storage of client personal information linked to letters. |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed |  |  | 2023-01-24 | 2023-04-30 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B030 | 2019 TRA Recommendation | New in 23/24 | Approved | FALSE |  | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions |  | N/A | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | Implement 2 remaining TRA recommendation from the 2019 SAMS TRA 1. Create and onboarding program for new data consumers for SAMS 2. Document data segregation requirements |  | Improved security and data maintenance |  | Cluster Base Budget |  | Unconfirmed |  | Other | [14 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B031 | Feasibility Study for SAMS Data Archiving | New in 23/24 | Approved - with changes | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | TRUE | Complete a feasibility study of the rules for data archiving to determine options for SAMS data archiving. |  |  |  | Cluster Base Budget |  | Unconfirmed | On Backlog | Other |  | Aleem will let us know whether this should be included on the plan | [12 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B032 | OPS Secure Migration | New in 23/24 | Approved | FALSE | Security Compliance | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#GovTechON | FALSE | Migrate all SAMS users to OPS Secure |  |  |  | SPP/MYP |  | Unconfirmed | In Progress | Confirmed |  |  | 2023-02-01 | 2023-11-30 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B033 | Assessment and migration of VQRP+ to new IAM services (BPS Secure/OPS Secure) | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | MCCSS - Ministry-wide | SCSI - Shared & Community Services I&IT Solutions | VQRP+ |  | Patrick, Christine (MCCSS);#47 | Awad, Mohamed (MCCSS) |  |  |  | FALSE | VQRP+ IAM Migration - Assessment and Migration to new IAM services |  | Assessment and migration to new IAM services (targeted for Q3 2023/24) | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B034 | Support Ministry with Boardroom Technology Modernization | New in 23/24 | Approved | FALSE | Ongoing Business Operations | Run - Cluster Services | Run | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions |  |  | Mackiewicz, Rick (MCCSS);#46 | Grandchamp, Dan (MCCSS) |  |  |  | FALSE | Evaluate the site and make recommendations with ITS. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B035 | Support development of MYAP OPS Digital Accessibility Standard | New in 23/24 | Approved | FALSE | Policy Change | Grow (Enhancements) | Grow | ACOE - I&IT Accessibility Centre of Excellence | SCSI - Shared & Community Services I&IT Solutions |  | Evolve How We Work | Dabideen, Mala (MCCSS);#30 | Awad, Mohamed (MCCSS) |  | OPS Accessibility Office (OAO), ITS, GovTechON, ODS | GovTechON;#CAC - Central Agencies Cluster;#TBS - Treasury Board Secretariat;#ITS - Infrastructure Technology Services;#ODS - Ontario Digital Service | FALSE | MYAP Commitment for ODS to lead and implement an OPS Digital Accessibility Standard; ACOE will be a key partner in developing the plan, standard and change management strategy |  | Standard digital accessibility practices, processes, reporting and tools across the OPS. Development and implementation of web accessibility plan. |  | Enterprise Funding |  | Confirmed | Pending | Tentative - pending ministry direction |  |  | 2023-04-03 | 2023-12-29 | [10 empty] | Not approved |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B036 | Develop and launch eLearning Courses for Digital Accessibility | New in 23/24 | Approved | FALSE | Ongoing Business Operations | Grow (Enhancements) | Grow | ACOE - I&IT Accessibility Centre of Excellence | SCSI - Shared & Community Services I&IT Solutions |  | Evolve How We Work | [5 empty] | FALSE | New eLearning Modules to be developed on: Document Accessibility, Digital Accessibility for Developers, Web Accessibility, Mobile Accessibility |  | Create self-paced, self-directed and accessible learning and development opportunities for all OPS | [20 empty] | Not approved |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B037 | SDWG-EHWW: DevOps Maturity Implementation | New in 23/24 | Approved | FALSE | CYSSC Strategy | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch | CAMS;#CPIN;#CPIN Reporting;#CPIN FM;#SAMS;#MyBenefits;#mFTIS;#HCD ISCIS;#FCMS | Evolve How We Work | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | The high level implementation plan was completed in late January 2023 as agreed to by 17 solution support teams. The execution of the tasks has started with the quick wins. This Ops Plan item will require cluster funding for up to 6 months for a PM to sustain the coordination of the activities and to report back on implementation status on a regular basis. SCSI - FCMS CM, FCMS FM, DSCIS, SASS,CSSD. CYIS - CPIN CM, CPIN FM, CPIN CAMS, CPIN Reporting, mFTIS, HCD-ISCIS, OACIS SAIS - SAMS, SADA, MyBenefits, Messaging, EST |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | CYIS has committed to provide any additional resources (1 Middleware and 1 DBA for 16 weeks each) to support their portion of the work. Linked to SAIS A085: Enhance existing SAMS dev and deployment pipeline. | Added prefix SDWG (Meg) | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B038 | E-Writs in FCMS-Phase 2 | New in 23/24 | Approved | FALSE | CYSSC Strategy | Grow (Enhancements) | Grow | FRO - Family Responsibility Office | SCSI - Shared & Community Services I&IT Solutions |  | Advance Our Technology Platforms | Wright, Peter (MCCSS);#28 | Awad, Mohamed (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Implementation of electronic data transfers: Process to create and transmit outgoing giles Process to retrieve and consume return files from Teranet |  | Supporting FRO’s strategic plan and satisfying one of their strategic priorities of optimizing system integration |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-02-01 | 2023-07-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B039 | SCSI DevOps Improvements | New in 23/24 | Approved | FALSE | Security Compliance | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions | FCMS;#DSCIS;#FRO Online;#eBill;#Freedom of Information Request Management System | Evolve How We Work | Wright, Peter (MCCSS);#28 | Awad, Mohamed (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | As part of the CYSSC Agile and DevOps Improvement initiative, FRO Digital has identified areas of improvement in both Agile and DevOps |  | Faster time to market, continuous collaboration, high release visibility, more automation, shorter release cycles, improved monitoring and observability |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-29 | Visualising all work in JIRA (Dev & Ops) |  | Product development pipeline automation |  | Leveraging ELK for observability | [5 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B040 | FRO Digital Business Releases | New in 23/24 | Approved | FALSE | CYSSC Strategy | Run - Applications | Run | FRO - Family Responsibility Office | SCSI - Shared & Community Services I&IT Solutions |  |  | Wright, Peter (MCCSS);#28 | Awad, Mohamed (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Regular business releases based on business priority and the product backlog. |  | Enhancements and defect fixes to improve business functionalities and processes. | [8 empty] | 2023-04-01 | 2024-03-29 | Roadmap Q1 | [9 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B041 | CYIS A095: Oracle eBS 12.2 Upgrade | New in 23/24 | Approved | FALSE | Application Evergreening | Run - Applications | Run | CW - Child Welfare & Protection | IOB - I&IT Operations Branch | CPIN;#CPIN FM | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | CPIN's current version of Oracle eBS (e-business suite v12.1) has expired from vendor support. This work is required to support the project to upgrade eBS to vendor supported version, avoid legacy related issues with the current version, and avoid the cost of 'market driven support' to keep the current eBS version. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B042 | SAIS B029: Secure Letter Storage Service | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance;#Audit Requirement | Run - Applications | Audit;#Run | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Support SAIS-led project to move SAMS letters into a secure storage solution in order to better protect client information and meet TRA cyber security requirements |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B043 | Vulnerability management, assessment and remediation | New in 23/24 | Approved | FALSE | Audit Requirement;#Security Compliance;#Keeping the Lights On | Run - Applications | Audit;#Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21;#Iqbal, Azhar (MCCSS);#24;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | - Assess, remediate solutions/systems impacted by CVEs communicated by Cyber - Implement patching cycles (O/S, software stack, DBs) - Implement TRA/PenTest report recommended vulnerability fixes/mitigations |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B044 | Accounts Payable Modernization | New in 23/24 | Approved | TRUE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | TPON | Advance Our Technology Platforms | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Provide a self-service option for Vision Care Service Provides to submit and track invoices online. |  | * Improved service experience and client satisfaction by providing timely payments and status updates through the TPON portal for vendors. Vendors will save time by not having to call the ministry to get an update regarding delayed payments. * Reduce reliance on additional temporary resources and paid overtime by reducing manual, administrative work (e.g., handling, scanning and storage of documents and data entry) * Reduce the risk of vendors refusing to serve ODSP clients due to outstanding repayment for invoices payments * Pave the way for additional SA benefits to be direct-billed to the province through TPON |  | SPP/MYP | 23/24 – Social Assistance Digital Delivery | Confirmed |  |  |  | Added MDCF indicator (Meg) | 2023-05-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B045 | Coordinate KDC Mainframe functionality migration (Project) | New in 23/24 | Approved | FALSE | Application Evergreening | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | TRUE | Coordinate by Q3 2023-24 the migration of any KDC mainframe functionality to GDC mainframe |  |  |  | Cluster Base Budget |  | Confirmed | Pending | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B046 | BIPD - Implement Data Quality Standards and checklist for existing/new applications | New in 23/24 | Approved - with changes | FALSE |  | Run - Cluster Services | Run | CYSSC - Cluster-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  |  |  | All branch areas to reference data quality checklist and adhere to guidelines. | BIPD - Business Intelligence & Practice Division;#CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | Implement a data quality checklist for all projects reviewed during Cluster Architecture Intake. Data quality checklist will reference BIPD's data quality guidelines |  | Improve quality of data on data input by ensuring data quality standards up front |  | Cluster Base Budget | N/A | Confirmed | Pending | Other |  | Modify the title to be more descriptive | 2023-06-05 | 2023-08-31 | Gather input and material from BIPD on existing data quality standards and practices | Pending | Gather input and material from other OPS/Corporate entities on existing data quality standards and practices | Pending | Perform analysis and prepare draft checklist | Pending | Validate and finalize checklist with CYSSC branches | Pending |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B047 | DAD Replacement (Business Case Development) | New in 23/24 | Approved - with changes | FALSE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | DAD | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ODS - Ontario Digital Service;#TBS - Treasury Board Secretariat | TRUE | Creation of the business case and additional work for replacement of the existing DAD system which supports the SA DAU functions |  | Modernize technology solution to improve service for citizen applying for ODSP benefits. |  | Other |  | Unconfirmed | In Progress | Confirmed | Work on business case for in year submission has started.. | Added "(Business Case Development)" to Item Name | 2023-01-01 | [11 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B048 | CAMS Replacement | New in 23/24 | Approved | FALSE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | CAMS | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | CMO - Cluster Management Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#ODS - Ontario Digital Service | TRUE | CAMS Replacement business case to support collection of overpayments for Social Assistance |  | Replacement of tool used to collect overpayments for client who have left SA. |  | Other |  | Unconfirmed | On Backlog | Tentative - pending funding | Business case must be developed working with SACSB to determine timing. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B049 | PSSAH Data Masking | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance;#Audit Requirement | Run - Applications | Audit;#Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | PSSAH | Become a Trusted Advisor | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Anonymized PSSAH Production data for UAT environment to support data migration to new TPON solution, production support, and testing. | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B050 | Implement PIM/PAM and related access monitoring (Project) | New in 23/24 | Approved | FALSE | Security Compliance | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) | Mohamed Awad; Aleem Syed; Joachim Kabiawu |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | TRUE | Improve security of applications at CYSSC OPCS & AWS to mitigate Corporate Security TRA related to unauthorized access tries. Privileged identity management (PIM) and privileged access management (PAM) are subsets of IAM (identity and access mgmt.) | [5 empty] | Unconfirmed | Pending | Confirmed | Need cost-recovery model to be defined by Corporate Security. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B051 | Recordkeeping readiness assessment for CYSSC application projects | New in 23/24 | Approved | FALSE |  | Run - Applications | Run | CYSSC - Cluster-wide | SCSI - Shared & Community Services I&IT Solutions |  | Evolve How We Work | Grandchamp, Dan (MCCSS);#29 | Awad, Mohamed (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division;#CMO - Cluster Management Office;#CWOB - Child Welfare Operations Branch;#CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | A Self Assessment tool that will define the RM maturity level and possible changes required in an application/solution to increase that maturity. |  | The application service owner will have a better sense of the RM gaps in their application. | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B052 | HCD-ISCIS Modernization Phase 3 Strategy | New in 23/24 | Approved | TRUE | Business Modernization/Transformation | Transform | Must-Do-Can't-Fail;#Transform | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | HCD ISCIS | Advance Our Technology Platforms | Cunningham, Nicki (MCCSS);#20;#Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#EAO - Enterprise Architecture Office;#Other | TRUE | Re-write old thick-client application into a web solution |  | This redesign will allow HCD-ISCIS to run on a web-browser eventually replacing the HCD-ISCIS desktop application. A web-based application has a number of advantages over the traditional desktop application. Accessible anywhere: The system provides users who travel across multiple locations with immediate access to HCD-ISCIS. Greater availability of information: Users can refer to multiple additional systems simultaneously when delivering or administering the programs. No installation and easy maintenance: A web-based HCD-ISCIS will simplify deployment of updates and fixes to the application. This is because all updates to the application would be done remotely, in the back-end, and without the involvement of Lead Agency users. Additionally, users will no longer be required to install software with each update to the applications. Easy data sharing and collaboration: Users can access and share authorized data as required easily. Centralized security: Users will be able to login securely using an enterprise-wide service called BPS Secure. Device agnostic: Users can switch between mobile devices and laptops as required. Increased efficiency: Direct entry into HCD-ISCIS reduces redundant data entry, improves time of data availability and helps meet early intervention targets. Additionally, there will be a reduction in the reliance on fax transmissions. Benefits to Partner Agencies: A web-based and digitized HCD-ISCIS will lead to the reduction of manual data entry by Lead Agencies and partner agencies like NSO. When additional components of HCD-ISCIS are digitized, direct upload of documentation will eliminate the need for faxing. | Not specified | SPP/MYP | 22/23 – Early Intervention and Special Needs Modernized Technology Foundation | Confirmed |  |  | HCD-ISCIS GUI Re-design to web-based portal work this year, will include o Workshop and analysis o Breakdown of work & activities planning o Change management & training needs o Development work estimates and plans to kick of depending on resource availability | [13 empty] | Approved by director | 100018797 |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B053 | HCD-IRSS Sustainment | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | HCD ISCIS | N/A | Cunningham, Nicki (MCCSS);#20;#Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) | CW Team, Cognos resources |  | CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division | FALSE | Keep the lights on for IRSS (Reporting) |  | Keeping the lights on, while IRSS is being modernized by BIPD | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B054 | Rocky Bay Child and Family Services (RBCFS) onboarding | New in 23/24 | Approved | FALSE | Legislation;#Ongoing Business Operations | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CAMS;#CAR;#CPIN;#CPIN Reporting;#CPIN CM;#CPIN FM;#mFTIS | Become a Trusted Advisor | Hamilton, Jennifer (MCCSS);#17 |  |  |  |  | FALSE | RBCFS is a newly designating indigenous agency located outside of Thunder Bay, Ontario. They were deployed to CPIN provider module in January 2023 following their provider designation. Phase 2 will be a full agency deployment following their full agency designation as a child protection agency |  | For Rocky Bay to provide provider and protection services to members of their community | [6 empty] | date TBC for phase 2: Full agency designation was slated for April 1, 2023 and then changed to a tentative date of July 1, 2023. CWOB advised that they will likely not desigante on this date. |  |  | 2023-07-01 | [10 empty] | Approved by director | 100018030 |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B055 | Ogwadeni:deo FM Deployment (OGD) | New in 23/24 | Approved | FALSE | Legislation;#Ongoing Business Operations | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CAMS;#CPIN;#CPIN FM | Become a Trusted Advisor | Hamilton, Jennifer (MCCSS);#17 |  |  |  |  | FALSE | Ogwadeni:deo (OGD) FM Deployment is a current designated indigenous agency in 6 nations. OGD does not currently use CPIN as their casemanagement system, but need to start capturing their FM information as the band is releaseing this responsibility to the agency. OGD decided they would like to deploy to CPIN for FM and eventually shift from their current case management system to CPIN. Phase 1: FM deployment is planned to occur on April 1, 2023 |  | OGD will be able to capture FM data following April 1, 2023 |  | Cluster Base Budget | [18 empty] | Approved by director | 100020155 |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B057 | Quality Standards Framework (QSF) Phase 2 | New in 23/24 | Approved | FALSE | Legislation | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN;#CPIN CM;#CPIN Reporting |  | Hamilton, Jennifer (MCCSS);#17 |  |  |  |  | FALSE | Developing and implementing enhanced requirements to reduce administrative burden on workers |  | Enhanced features to support QSF work |  | Cluster Base Budget |  |  |  |  | We have the list of backlog items, developed with the sector using co-design. Items were prioritized for phase 1 and 2 | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B058 | Enhanced LA ( Local Admin) role | New in 23/24 | Approved | TRUE | Ongoing Business Operations | Transform | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CAMS;#CPIN | Advance Our Technology Platforms | Hamilton, Jennifer (MCCSS);#17 |  |  |  |  | FALSE | SPP Sector has requested creating a new role to support agencies being able to fix some internal data errors |  | Business would like to have more control over being able to correct some data |  | Cluster Base Budget | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B060 | Ongoing support for SA Digital Applications | New in 23/24 | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | Digital Applications;#DDDP;#EST;#EA;#MyBenefits;#SADA;#2WAYMessaging | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21;#Iqbal, Azhar (MCCSS);#24;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Provide ongoing support for digital applications, including: 1. DDDP (Digital Disability Determination Package) 2. EQFX-BIL (Equifax-Business Integration Layer) 3. EST (Employment Services Transformation) 4. EAP (Employment Action Plan) 5. IRCC-BIL (Immigration, Refugee and Citizenship Canada – Business Integration Layer) 6. Messaging (formerly 2 Way Messaging) 7. EA (Emergency Assistance) 8. MyBenefits - scheduled for April 24 2023 9. SADA (Social Assistance Digital Application - scheduled for May 22, 2023 |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B061 | Ongoing support for MCCSS Data Platform | New in 23/24 | Approved | FALSE | Minister Commitment | Run - Applications | Run | MCCSS - Ministry-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | Support BIPD data extraction requirements for Reporting/Analytics. |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B062 | SAIS B031: Feasibility Study for SAMS Data Archiving | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Grow (Enhancements) | Grow | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Support SAIS's Feasibility Study for SAMS Data Archiving project | [5 empty] | Unconfirmed |  | Tentative - pending funding | Waiting for project scope and resource definition. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B063 | SCSI A142: FRO Digital Statement of Arrears Calculator - Phase 2 | New in 23/24 | Approved | FALSE | Business Modernization/Transformation | Transform | Transform | FRO - Family Responsibility Office | IOB - I&IT Operations Branch | FRO Online | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | Support SCSI's FRO Digital Statement of Arrears Calculator - Phase 2 project |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B064 | SAIS B047: DAD Replacement | New in 23/24 | Approved | FALSE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | IOB - I&IT Operations Branch | DAD | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Support SAIS's Disability Adjudication Database (DAD) Replacement project | [5 empty] | Unconfirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B065 | SAIS B048: CAMS Replacement | New in 23/24 | Approved | FALSE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | IOB - I&IT Operations Branch | CAMS | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Support SAIS's Collections Administration and Management System (CAMS) Replacement project | [5 empty] | Unconfirmed |  | Tentative - pending funding | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B066 | PSSAH Data Masking | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance;#Audit Requirement | Run - Applications | Audit;#Run | SN - Special Needs | IOB - I&IT Operations Branch | PSSAH | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | Lead implementation of PSSAH data masking to allow copies of production masked data to be made available in non-production zones. | [5 empty] | Unconfirmed |  | Tentative - pending funding | Waiting for project creation and definition of scope and resources. Contact: Jesal. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B067 | CYIS A011: CPIN Auto-Deploy | New in 23/24 | Approved | FALSE |  | Run - Applications | Run | CW - Child Welfare & Protection | IOB - I&IT Operations Branch | CPIN CM | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | Support CYIS's CPIN Case Management Auto-Deploy project | [5 empty] | Unconfirmed |  | Confirmed | Require coordination among other DevOps work. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B070 | SDWG-EHWW: DevOps Maturity Reporting (dashboard update) | New in 23/24 | Approved | FALSE | CYSSC Strategy | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | This item will report and update the countermeasure dashboard as to the status of the DevOps Maturity. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed |  | Added SDWG prefix (Meg) | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B071 | EAO B088: SDWG-ATP: Develop the MCCSS Business + Technology Strategy | New in 23/24 | Approved | FALSE | CYSSC Strategy | Grow (Enhancements) | Grow | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | This is an EAO-led item that will look into strategies for the following; (1) Digital Transformation Strategy (2) Cloud Strategy - Infrastructure and Tooling (3) Data Management Strategy (4) Security Strategy (5) Vendor Roadmap Strategy (6) Infrastructure Strategy | [5 empty] | Unconfirmed |  | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B072 | Financial Management Action Plan | New in 23/24 | Approved | FALSE | Audit Recommendation | Run - Cluster Services | Audit;#Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#OCIO - Office of the Chief Information Officer | FALSE | Resulting from the OIAD engagement on the CYSSC base budget review, the cluster has committed to the creation of a Financial Management Action Plan. CYSSC commits to developing a financial management action plan to: align to Technology Road Maps; identify long-term efficiencies through further optimization of internal operations; ensure effective governance and business planning for IT activities across the Ministry, and; ensure ongoing updates to the IT Funding Model. |  |  |  | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B073 | SCSI B103 : FCMS Enterprise Command Center POC | New in 23/24 | Approved | FALSE | Business Modernization/Transformation | Grow (Enhancements) | Grow | FRO - Family Responsibility Office | IOB - I&IT Operations Branch | FCMS | Become a Trusted Advisor | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | Support SCSI-led project. Proof of Concept (POC) of Oracle Enterprise Command Center (ECC). ECC Dashboards and graphical visualization enable Oracle E-Business Suite users to identify and act on priority financial transactions without custom operational reporting. Users can easily create customized dashboards and reports using a simple drag-and-drop interface. |  |  |  | Cluster Base Budget |  | Confirmed | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B074 | Maintain CYSSC data replication to Azure for Disaster Recovery | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | CW - Child Welfare & Protection;#SA - Social Assistance;#FRO - Family Responsibility Office | IOB - I&IT Operations Branch | CPIN;#SAMS;#FCMS | Advance Our Technology Platforms | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | CPIN, SAMS, FCMS databases have real-time replication to Azure for Disaster recovery |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B076 | Update infrastructure blueprints for cluster-supported solutions (Project) | New in 23/24 | Approved - with changes | FALSE | Keeping the Lights On | Run - Applications | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#EAO - Enterprise Architecture Office | TRUE | Update infrastructure blueprints for cluster-supported solution to serve as reference documents. | [5 empty] | Unconfirmed |  | Confirmed | Support not required from other branches. | Rename this one | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B077 | EAO A006: Data Leakage Prevention Program Phase 1 - Assessment | New in 23/24 | Approved | FALSE | Audit Recommendation | Run - Applications | Audit | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | EAO - Enterprise Architecture Office;#CYIS - Child and Youth I&IT Solutions | FALSE | Assess the feasibility of implementing automated technologies to prevent data leakage. |  | Feasibility analysis on DLP implementation to address audit findings and best practices in implementing safe guards. As a result, to come up with recommendations on DLP implementation for Phase 2 |  | Cluster Base Budget |  | Confirmed |  | Confirmed | The IOB support for Phase 1 will be to attend sessions and to provide input to the discussions. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B078 | CPIN SOR-RL Integration | New in 23/24 | Approved | TRUE | Business Modernization/Transformation | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN;#SOR-RL | Advance Our Technology Platforms | Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | SPP Integration of data between CPIN and SOR-RL. Reduction in duplicate data entry |  |  |  | SPP/MYP | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B079 | CYFSA Website Enhancements | New in 23/24 | Approved | TRUE | Business Modernization/Transformation | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CYFSA Website |  | Hamilton, Jennifer (MCCSS);#17;#Pawlowski, Walter (MCCSS);#36 |  |  |  |  | FALSE | SPP CYFSA Website additional search functionality for public use. |  |  |  | SPP/MYP |  |  |  |  | Application: CYFSA Website | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B080 | Child Welfare Application Platform - Phase 1 | New in 23/24 | Approved | TRUE |  | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Hamilton, Jennifer (MCCSS);#17;#Pawlowski, Walter (MCCSS);#36 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | SPP Development of a modular Child Welfare Application Platform to support new development outside of CPIN. |  |  |  | SPP/MYP | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B081 | CYIS Special Needs Team Continuous Quality Improvement QI | New in 23/24 | Approved | FALSE | CYSSC Strategy;#Ongoing Business Operations | Transform | Transform | SN - Special Needs | CYIS - Children & Youth I&IT Solutions |  | Evolve How We Work | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68;#Small, Amanda (MCCSS);#73;#Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | To complete milestone reflections with each staff member and identify key outputs that can be included in FORTE plans, training and personal development approaches and CQI for staff engagement across branch initiatives and culture to evolve how teams work together |  | supports steward leaderships and agile methodologies and culture for how teams work with each other and business partners | [8 empty] | 2023-04-01 | 2024-03-31 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B082 | SPP Submission - CyberSecurity CAS Strategy | New in 23/24 | Approved - with changes | FALSE | Security Compliance;#Audit Recommendation | Transform | Transform | MCCSS - Ministry-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) |  | Cyber Security Division | CMO - Cluster Management Office;#IOB - I&IT Operations Branch;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#Other | FALSE | A multi-year Cyber Security Strategy for Children’s Aid Societies to address evolving cyber threats in the Child Welfare and Protection sector ; • A multi-year Data Leakage Prevention Phase 2 Strategy for making sure that end users (OPS staff, service delivery partners) do not share sensitive or critical information outside the corporate network. |  | Appropriate safeguards are implemented to protect data assets in MCCSS |  | SPP/MYP | 23/24 - Social Services Sector – Cyber Security Strategy (2023/24 – 2026/27) | Unconfirmed | Pending | Tentative - pending ministry direction | TB has asked to resource (fund) from within. Further discussion is needed with MPBSD and Cyber Security to determine a path forward. | Please update the name | 2023-04-03 | 2024-03-29 | SPP funding to be confirmed | Pending | Procurement for vendor to implement DLP | Pending | Vendor to start implementation | Pending | Appropriate safeguards implemented | Pending |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B083 | SDWG-EHWW: CI/CD pipeline for HCD-ISCIS | New in 23/24 | Approved | FALSE | CYSSC Strategy | Grow (Enhancements) | Grow | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | HCD ISCIS | Evolve How We Work | Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | A continuous integration and continuous deployment (CI/CD) pipeline for automated code builds |  | Streamlined process for developers and improving software delivery throughout the software development life cycle via automation. | [8 empty] | 2023-03-13 | 2024-03-29 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B084 | Automated Testing for HCD-ISCIS | New in 23/24 | Approved | FALSE | CYSSC Strategy | Grow (Enhancements) | Grow | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | HCD ISCIS | Evolve How We Work | Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | QA/Testing process is being automated for HCD-ISCIS |  | Better resource utilization Reduces testing time and cost Improves product quality Suited for CI/CD and DevOps | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B085 | Graduated Skills Training for SA | New in 23/24 | Approved | FALSE | Audit Recommendation | Run - Cluster Services | Audit;#Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions |  | Evolve How We Work | Veedu, Ummer (MCCSS);#72 | Syed, Aleem (MCCSS) |  |  |  | FALSE | Establish skills pathway, training and lab for different roles to build in-house expertise to run/grow SA portfolio. |  | Build in-house expertise to run/grow SA portfolio and reduce dependency on FFS/vendors. | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B086 | AMIS Fixed Price Work | New in 23/24 | Approved | FALSE | Audit Recommendation;#Audit Requirement;#Ongoing Business Operations | Run - Applications | Audit;#Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions |  | Evolve How We Work | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | Application Maintenance and Improvement Services (AMIS) agreement is valued at $60M for 6 years (3+1+1+1). The first three year period end FY24-25. The scope of work is to do a cost-benefit analysis and make a business case to bring this work in the cluster and prepare for a TB submission in Fall '23. |  | Cluster becomes self-sufficient in maintaining and supporting the SAMS portfolio. | [20 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B087 | SAIS Workforce Strategy | New in 23/24 | Approved | TRUE | Audit Recommendation;#CYSSC Strategy | Run - Applications | Audit;#Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions |  | Evolve How We Work |  | Syed, Aleem (MCCSS) |  |  |  | FALSE | Execute the counter measures for the branch's workforce strategy with the goal of becoming self-sufficient and meeting the TB /Audit recommendations. |  |  | TB Commitment | [19 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B088 | SDWG ATP - Develop MCCSS Business + Technology Strategy - SPP | New in 23/24 | Approved | TRUE | CYSSC Strategy | Grow (Enhancements) | Grow | MCCSS - Ministry-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  |  |  |  | BIPD - Business Intelligence & Practice Division;#CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#GovTechON;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | (1) Digital Transformation Strategy (2) Cloud Strategy - Infrastructure and Tooling (3) Data Management Strategy (4) Security Strategy (5) Vendor Roadmap Strategy (6) Infrastructure Strategy |  | Defining a new cluster business and technology strategy for transforming the technology landscape and approach to address business vision and priorities. Goal to align with the life course approach and ensure value of IT investment in the Cluster by leveraging strategy concepts of digital transformation, cloud strategy, data management, security, vendor roadmap and infrastructure. |  | Cluster Base Budget | N/A | Confirmed | Pending | Other | Digital Transformation - Integration of digital technology into all areas of business. Evaluate current state, Life Course Approach, Data Driven, Technology Adoption Cloud - Standards - Cloud computing, Cloud Infrastructure and Tooling Data Management - Approach to data governance, data architecture, data storage, systems integration, unified data intake Security - Protect Information Systems, Data and Networks from Cyber Threats Vendor - Selecting, managing, maximizing technology vendors. Entrance and exit criteria for vendor products Infrastructure - Manage infrastructure assets to ensure hosting and service optimization |  | 2023-02-17 | 2023-04-28 | Draft strategy document | In Progress | Review strategy document in CLT meeting | In Progress | Review strategy document with Cluster Management | Pending | Review strategy with Ministry executives | Pending | Finalize strategy document | Pending | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B089 | CPIN Automation Testing - Reporting | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Set up an automated process for all releases to significantly reduce the testing time during regression cycles for testing activities such as: projects, smoke testing, integration testing, bug fixes related to CM, FM and Reports | We are working on a project plan and implementation of devops to support work |  |  | Cluster Base Budget | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B090 | CPIN Automation Testing - FM | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Grow (Enhancements) | Grow | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions | CPIN |  | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Set up an automated process for all releases to significantly reduce the testing time during regression cycles for testing activities such as: projects, smoke testing, integration testing, bug fixes related to CM, FM and Reports | We are working on a project plan and implementation of devops to support work |  |  | Cluster Base Budget | [18 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B091 | CYIS Child Welfare Team Continuous Quality Improvement QI | Carried forward from 22/23 OpPlan | Approved | FALSE |  | Transform | Transform | CW - Child Welfare & Protection | CYIS - Children & Youth I&IT Solutions |  |  | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35;#Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19;#Pawlowski, Walter (MCCSS);#36;#Torrance, Tyler (MCCSS);#37 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | To complete milestone reflections with each staff member and identify key outputs that can be included in FORTE plans, training and personal development approaches and CQI for staff engagement across branch initiatives and culture to evolve how teams work together | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B092 | 2023 OAGO VFM Audit: Governance of IT Systems and Operations | New in 23/24 | Approved | FALSE | Audit Requirement | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#D'Annunzio, James (MCCSS);#95;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (MCCSS) |  |  |  | FALSE | Coordination of: information and meeting requests; factual clearance of draft audit report; development of management responses and action plans. |  |  | High attention from Premier/Minister's office | Cluster Base Budget |  | Confirmed | Pending |  |  |  | 2023-01-03 | 2024-03-29 | Coordinate Responses to Requests for Information | In Progress | Coordinate OAGO Meeting Requests | In Progress | Factual Clearance and Management Responses for Audit Report | Pending | Develop Action Plans in Response to Audit Recommendations | Pending |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B093 | TB Reporting | New in 23/24 | Approved | FALSE |  | Run - Cluster Services | Run | MCCSS - Ministry-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#Zhang, Jerry (MCCSS);#97;#Wong, Kenneth (MCCSS);#98 | Garant, Kelly (MCCSS) |  |  |  | FALSE | Provide coordination and support of quarterly (MPR and QSR) and ad hoc TB reporting. |  |  | MYP/SPP/TB approved | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-04-03 | 2024-03-29 | Q1 Reporting | Pending | Q2 Reporting | Pending | Q3 Reporting | Pending | Q4 Reporting | Pending |  |  | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B094 | IT Funding Model (ITFM) - Annual Review | New in 23/24 | Approved | FALSE |  | Run - Cluster Services | Run | MCCSS - Ministry-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#Wong, Kenneth (MCCSS);#98 | Garant, Kelly (MCCSS) |  |  |  | FALSE | As part of the SPP process -- update the ITFM to determine portfolio adjustments required. |  |  | MYP/SPP/TB approved | Cluster Base Budget |  | Confirmed |  |  |  |  | 2023-09-01 | 2023-11-30 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B095 | IT General Control (ITGC) Assessments | New in 23/24 | Approved | FALSE |  | Run - Cluster Services | Run | CYSSC - Cluster-wide | CMO - Cluster Management Office |  |  | Burns-Solitar, Carrie (MCCSS);#40;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (MCCSS) |  |  |  | FALSE | Coordinate the completion of ITGC assessments (Design and Operating Effectiveness) and reporting. |  |  |  | Cluster Base Budget |  | Confirmed | [16 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B096 | OACIS & PEIS Migration from KDC | New in 23/24 | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | OACIS |  | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | Migrate OACIS & PEIS applications out of KDC to GDC | [25 empty] | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B098 | Business and Technology Roadmap | New in 23/24 | Approved | FALSE |  | Run - Cluster Services | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | [7 empty] | FALSE | [10 empty] | Update the link to ATP | [15 empty] | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B099 | Annualized Earnings Exemptions - Business Analysis | New in 23/24 | Approved | FALSE | Policy Change | Transform | Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS |  | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  |  | FALSE | Acquire a BA resource to do requirements analysis and grooming for the Annualized Earnings Exemptions initiative |  |  |  | Ministry LOA |  | Confirmed | Pending |  | The funding for the overall initiative has not been approved yet. The BA resource will be used as a stop gap solution to meet a potential January 2024 delivery date, given there is a 9 month critical path in the high level delivery plan with requirements analysis being at the start of the path. | Funding required | 2023-04-03 | [11 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B100 | Reporting Integration work with BIPD | New in 23/24 | Approved | FALSE |  | Run - Cluster Services | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions |  | Advance Our Technology Platforms | [5 empty] | FALSE | Placeholder to determine and plan for co-design operational model for Reports integration work | [22 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B101 | SAMS: First Nations ODSP | New in 23/24 | On hold | FALSE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | SAMS |  | Karageorgos, Effie (MCCSS);#32;#Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | Changes required in SAMS so it can be used by First Nations for ODSP program applicants | [5 empty] | Unconfirmed |  | Tentative - pending funding |  | Funding required | [12 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B102 | SAIS B044: Accounts Payable Modernization | New in 23/24 | Approved - with changes | FALSE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | IOB - I&IT Operations Branch | TPON | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Support SAIS-led project. Provide a self-service option for Vision Care Service Providers to submit and track invoices online. | [7 empty] | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B103 | FCMS Enterprise Command Center POC | New in 23/24 | Approved | FALSE | Business Modernization/Transformation | Grow (Enhancements) | Grow | FRO - Family Responsibility Office | SCSI - Shared & Community Services I&IT Solutions | FCMS | Become a Trusted Advisor |  | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | Proof of Concept (POC) of Oracle Enterprise Command Center (ECC) ECC Dashboards and graphical visualization enable Oracle E-Business Suite users to identify and act on priority financial transactions without custom operational reporting. Users can easily create customized dashboards and reports using a simple drag-and-drop interface. |  | Allow FRO (Financial) users to prioritize financial transactions that require immediate attention and affectively identify and address transactions of potential concern. |  | Cluster Base Budget | [6 empty] | 2023-04-03 | 2023-06-30 | [10 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B104 | Counter Reg and Visitor Reg migration | New in 23/24 | Approved | TRUE | Keeping the Lights On | Run - Applications | Run | SA - Social Assistance | SAIS - Social Assistance I&IT Solutions | Counter Registration;#Toronto Region Visitor Registration | Advance Our Technology Platforms | Hamilton, James (MCCSS);#33 | Hamilton, James (MCCSS) |  |  | IOB - I&IT Operations Branch | TRUE | Migrate CR and VR applications from KDC to GDC, as a part of KDC decommission activity |  | Ensure CR and TR applications continue to operate after the Kingston Data Center is decommissioned |  | Cluster Base Budget |  | Unconfirmed |  |  |  |  | 2023-04-03 | 2023-05-26 | [10 empty] | Review pending |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B105 | Application Support and Maintenance for Social Assistance applications | New in 23/24 | Approved | FALSE | Keeping the Lights On | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS;#SALIS;#SAMS-EDM | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. Includes: SAMS, SALIS, SAMS-EDM, OASA |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B106 | SAIS A113: Limit use and safeguard personal information (PI) in system, test environments and minimize access to PI | New in 23/24 | On hold | FALSE |  | Grow (Enhancements) | Grow | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS |  | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Assess opportunity to build reports within core systems to meet user needs instead of extracting the data. | [5 empty] | Unconfirmed |  | Tentative - pending funding | IOB does not have resources. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B107 | SAIS A089: Emergency Assistance migration to GoCloud | New in 23/24 | On hold | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | EA | Advance Our Technology Platforms | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Migrate EA hosting from on-prem to public cloud. |  | * Scalability of public cloud hosting platform to any surge in user demand * Higher stability and availability of public cloud hosting platform * Scaling of hosting cost based on usage * Alignment of EA application hosting architecture with other SA digital applications enabling leveraging of resource pool for application support |  |  |  | Unconfirmed |  | Tentative - pending funding | IOB does not have resources. | [13 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B109 | SAIS B100: Reporting integration work with BIPD | New in 23/24 | Pending | FALSE |  | Run - Cluster Services | Run | SA - Social Assistance | IOB - I&IT Operations Branch |  |  | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Placeholder to determine and plan for co-design operational model for Reports integration work | [5 empty] | Unconfirmed |  | Tentative - pending funding |  | Pending until BIPD's discussion on Tuesday | [12 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B110 | SAIS B104: Counter Reg and Visitor Reg migration | New in 23/24 | On hold | FALSE | Keeping the Lights On | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | Counter Registration;#Toronto Region Visitor Registration | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Migrate Counter Registration and Toronto Region Visitor Registration applications from KDC to GDC, as a part of KDC decommission activity |  | Ensure CR and TR applications continue to operate after the Kingston Data Center is decommissioned |  | Cluster Base Budget |  | Confirmed |  | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B111 | SAIS B101: SAMS: First Nations ODSP | New in 23/24 | On hold | FALSE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS |  | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Changes required in SAMS so it can be used by First Nations for ODSP program applicants | [5 empty] | Unconfirmed |  | Tentative - pending funding | IOB support is pending SAIS confirmation and funding of this project. | [13 empty] | Ready for director approval |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B112 | SAIS A144: SA Digital: SAMS - Electronic Document Management (EDM): Transform Scope | New in 23/24 | Approved | FALSE | Business Modernization/Transformation | Transform | Transform | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS-EDM | Advance Our Technology Platforms | Obias, Joven (MCCSS);#21;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | a. Digital Integrations (scale EDM service); b. Expansion of E-forms Capabilities; c. Expansion to OW and Centralized Services; and d. Document Assignment Logic Refinement. |  | Project allows for digitization of a client’s file and new incoming mail for retention, including imaging, electronic storage, and retrieval of documentation for ODSP and OW partners. EDM reduces the amount of data entry and paper handling time and enables staff to access files without needing to search through a file room or internal mail system. EDM includes Digital Day 1, which allows staff to scan documents that have been dropped off by clients. Files are immediately digitized and connected to the client’s file, improving response time to client inquires.​ |  | Cluster Base Budget |  | Confirmed |  | Confirmed | Only a. Digital Integrations (scale EDM service) will need IOB support. The IOB resources will be internal. No new additional resources required. | [13 empty] | Ready for director approval |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B113 | SAIS A085: Enhance existing SAMS dev and deployment pipeline | New in 23/24 | Approved | FALSE | Application Sustainment & Maintenance | Run - Applications | Run | SA - Social Assistance | IOB - I&IT Operations Branch | SAMS | Advance Our Technology Platforms | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | Continue to improve the maturity of the SAMS production deployment pipeline for example automated front end validation and pipe line to pipe line integration with SA Mod application. | [6 empty] | In Progress | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B114 | I&IT Operations Branch Strategy | New in 23/24 | Approved | FALSE |  | Run - Cluster Services | Run | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  | Evolve How We Work | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CMO - Cluster Management Office | FALSE | Create and implement a branch strategy. |  |  |  | Cluster Base Budget |  | Confirmed |  | Confirmed | [14 empty] | Ready for director approval |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B115 | SPP Submission - Data Leakage Prevention Phase 2 | New in 23/24 | Approved | FALSE | Security Compliance | Transform | Transform | MCCSS - Ministry-wide | EAO - Enterprise Architecture Office |  | Advance Our Technology Platforms |  |  |  | Cyber Security Division | CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#Other | FALSE | A multi-year Cyber Security Strategy for Children’s Aid Societies to address evolving cyber threats in the Child Welfare and Protection sector ; • A multi-year Data Leakage Prevention Phase 2 Strategy for making sure that end users (OPS staff, service delivery partners) do not share sensitive or critical information outside the corporate network. |  |  |  | SPP/MYP | N/A | Unconfirmed | Pending | Tentative - pending ministry direction | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B116 | Metaverse - Training Strategy for Business Sectors | New in 23/24 | Approved | FALSE |  | Run - Cluster Services | Run | FRO - Family Responsibility Office | EAO - Enterprise Architecture Office | FCMS | Advance Our Technology Platforms |  |  |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | Develop a strategy and implement a metaverse/sharepoint spaces strategy to help improve and support the business training teams | [25 empty] | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B117 | EIAM Modernization oversight | Carried forward from 22/23 OpPlan | Approved | TRUE | Security Compliance;#Business Modernization/Transformation | Run - Cluster Services | Run | CYSSC - Cluster-wide;#Enterprise I&IT | EAO - Enterprise Architecture Office | CPIN;#DSCIS;#FCMS;#SAMS | Advance Our Technology Platforms |  | Lourdes, Alvin (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#CYIS - Child and Youth I&IT Solutions | FALSE | Assisting projects in the various solution branches with their application IAM modernization activities to OPS/BPS/Public Secure |  | Individual applications are recommended to follow one of the approved IAM migration patterns | Not specified | Cluster Base Budget | N/A | Confirmed | In Progress | Confirmed | It is part of GovTechON corporate mandate to move applications to OPS/BPS/Public Secure |  | 2023-04-03 | 2024-03-29 | Determine alignment of application to one of the approved pattern | Complete/Operationalized | As part of EA governance, project to demonstrate alignment to approved pattern | Pending | [6 empty] | Ready for director approval |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B118 | Support for audits, reviews, assessments | New in 23/24 | Approved | FALSE | Audit Requirement | Run - Applications |  | CYSSC - Cluster-wide | IOB - I&IT Operations Branch |  |  | Obias, Joven (MCCSS);#21;#Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | CMO - Cluster Management Office | FALSE | Provide support for audits, reviews, assessments, risk remediation, and other related requests (e.g. ITGC, risk recalculations) |  |  |  | Cluster Base Budget |  | Confirmed | Ongoing Work | Confirmed | [14 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
B119 | HCD ISCIS and HCD IRSS ITGC Toolkit Completion and Operational Effectiveness Assessments | New in 23/24 | Approved | FALSE | Audit Requirement | Run - Applications |  | SN - Special Needs | CYIS - Children & Youth I&IT Solutions | HCD ISCIS | Evolve How We Work | Tyson, Shalini (MCCSS);#74 | Cunningham, Nicki (MCCSS) | CMO, IOB, IPEB |  | CMO - Cluster Management Office | FALSE | Initiate HCD ISCIS and HCD IRSS ITGC Toolkit Completion and Operational Effectiveness Assessment. Previous ITGC was completed in 2019 | [22 empty] | Approved by director |  |  | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Y1 | old_sample