## query
CLT LxL Status | Item ID | Item Name | Work Item Description | Work Type | Driver | Type of work | CYSSC Strategic Direction | Business Outcome | Program-Portfolio | Application | Planview ID | Accountable Branch | RACI - Responsible | RACI - Accountable | RACI - Consult | RACI - Inform | Support Needed | Requires ITS | Must-Do-Can't-Fail | MDCF Criteria | Funding Source | Funding Confirmed | SPP Item Name | Comments | Project Timeline | Anticipated Start Date | Anticipated End Date | Approval Status | Progress Status | Health Check | Percent Complete | Milestones Total | Milestone 1 - Name | Milestone 1 - Size | Milestone 1 - Percent Complete | Milestone 2 - Name | Milestone 2 - Size | Milestone 2 - Percent Complete | Milestone 3 - Name | Milestone 3 - Size | Milestone 3 - Percent Complete | Milestone 4 - Name | Milestone 4 - Size | Milestone 4 - Percent Complete | Milestone 5 - Name | Milestone 5 - Size | Milestone 5 - Percent Complete | Milestone 6 - Name | Milestone 6 - Size | Milestone 6 - Percent Complete | Milestone 7 - Name | Milestone 7 - Size | Milestone 7 - Percent Complete | Milestone 8 - Name | Milestone 8 - Size | Milestone 8 - Percent Complete | Item Origin | Quarterly Update Complete? | Q1 CMO Review | Item Type | Path
Approved | A001 | ITGC - eBill | Conduct ITGC design effectiveness testing for eBill. | Run - Applications | Audit Requirement | Project/initiative |  |  | CYSSC - Cluster-wide | eBill |  | CMO - Cluster Management Office | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (She/Her) (MCCSS) |  |  | CMO - Cluster Management Office;#SCSI - Shared & Community Services I&IT Solutions;#Audit Team | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  |  | 4501700% | 4538200% |  | On Backlog | Yellow | 0% | 100% | Planning | 25% | 0% | Project Completion | 75% | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A006 | Audit - Data Leakage Prevention Program Phase 1 - Assessment | Assess the feasibility of implementing automated technologies to prevent data leakage. | Run - Applications | Audit Requirement | Project/initiative | Advance Our Technology Platforms | Feasibility analysis on DLP implementation to address audit findings and best practices in implementing safe guards. As a result, to come up with recommendations on DLP implementation for Phase 2 | CYSSC - Cluster-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) | Jason Persaud (Cyber Security Division) - MPBSD |  | CMO - Cluster Management Office;#Audit Team;#CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  | Other | Confirmed |  | There is agreement by Ministry to carry out this work. Funding for cluster to use but Ministry will account for this pressure. | Finishing in year | 4499100% | 4507900% | Confirmed | Complete/Operationalized | Complete | 100% | 100% | RFS to be shared with vendors | 25% | 100% | RFS submissions to be evaluated and finalized | 25% | 100% | RFS vendor kick-start work | 25% | 100% | Vendor completes deliverables as per SOW | 25% | 100% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A010 | ACWI, CAR, CPIN Dev Migration from KDC | Support the migration of applications out of KDC. | Run - Applications |  | Support for GovTechON initiative |  |  | CW - Child Welfare & Protection | ACW/I;#CAR;#CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 50% | 100% | ACWi and CAR have been moved into PPE at GDC | 25% | 100% | Tested ACWi and CAR in PPE | 25% | 100% | Tested ACWi and CAR in GDC Production | 25% | 0% | ACWi and CAR have been moved into Production at GDC | 25% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A011 | SDWG-EHWW: CPIN Auto-Deploy | as part of the SPP. Set up an automated process for auto code deployment in the lower environments. Planning phase. May overlap into next fiscal 24/25 to complete ALL components of CPIN. (CM, FM, QA, Automation). | Run - Applications |  | Project/initiative |  |  | CW - Child Welfare & Protection | CPIN CM |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Kugendran, Shanmugathasan (MCCSS);#19 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  |  |  |  | Part of the SDWG Countermeasures | Carrying over to next year |  |  |  | Pending | Green | 14% | 100% | SPP approved funding | 10% | 90% | Procure resources | 10% | 0% | requirements gathering | 10% | 50% | Project plan and development | 70% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A014 | Quality Standards Framework (QSF) - Phase 1 | Legislated changes to provide additional safety factors for out of home care of children. | Grow (Enhancements) | Ministry Request | Project/initiative |  |  | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) |  |  | CWOB - Child Welfare Operations Branch;#IOB - I&IT Operations Branch | FALSE | FALSE |  | SPP/MYP |  |  | QSF will be released in 2 -3 phases. Phase 1 will deploy in to production on July 1, 2023 | Finishing in year |  | 4510100% |  | Complete/Operationalized | Complete | 100% | 100% | Phase 1 | 100% | 100% | [21 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A015 | OACIS & PEIS Releases (OAP reconciliation) | Develop application releases from backlog prioritization by the business to support Autism program redesign and transition to an independent intake organization (IIO). Work include: IIO: CRT Operation: CB, IOT, CCS expenses reconciliation, IOT and IOT renewal after EBBS ends, Incidents and service requests | Grow (Enhancements) |  | Project/initiative |  |  | SN - Special Needs | OACIS;#PEIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division | FALSE | FALSE |  | Cluster Base Budget |  |  |  | Finishing in year | 4501900% | 4538000% |  | In Progress | Green | 50% | 100% | OACIS enhancements to support CRT | 70% | 50% | Continue to support transition to IIO | 30% | 50% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A016 | FCIS-KIDS Sustainment (CPRI) | Provide business continuity / keeping-the-lights-on support for FCIS-KIDS, which has reached end of life and for which there is no vendor support. | Run - Applications | Keeping the Lights On | Ongoing/Operational |  |  | SN - Special Needs | FCIS-KIDS |  | CYIS - Children & Youth I&IT Solutions | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A017 | Ideasweb Sustainment (CPRI) | Monitor the application and provide maintenance work only to provide business continuity until a replacement software is implemented. In conjunction with KIDS | Run - Applications | Keeping the Lights On | Ongoing/Operational |  |  | SN - Special Needs | Ideasweb |  | CYIS - Children & Youth I&IT Solutions | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A018 | HCD ISCIS Application Sustainment | Keep lights on while modernization activities are underway. | Run - Applications | Keeping the Lights On | Ongoing/Operational |  |  | SN - Special Needs | HCD ISCIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  |  |  |  | Ongoing Keep the lights on work, resolving production issues | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0.5% | 100% | Data Extracts for Western University | 10% | 5% | Production Ticket Resolution | 90% | [19 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A020 | CPRI Pharmacy Application Sustainment | Provide keeping-the-lights-on production support, including coordinating with CPRI and vendor to implement application-related patches and bug fixes. | Run - Applications | Keeping the Lights On | Ongoing/Operational |  |  | SN - Special Needs | CPRI Pharmacy Application |  | CYIS - Children & Youth I&IT Solutions | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | Other | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A021 | SchedulePRO Sustainment | Provide keeping-the-lights-on, maintenance-only production support. | Run - Applications | Keeping the Lights On | Ongoing/Operational |  |  | SN - Special Needs | SchedulePRO |  | CYIS - Children & Youth I&IT Solutions | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A023 | Application Support & Maintenance For All Child Welfare Applications | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, database maintenance, and testing activities to support maintenance and anticipated enhancements. Inclusive of A002 and A004 | Run - Applications | Keeping the Lights On | Ongoing/Operational |  |  | CW - Child Welfare & Protection | CPIN;#mFTIS;#ACW;#ACW/I;#CAR |  | CYIS - Children & Youth I&IT Solutions | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17;#Acuna, Oscar (MCCSS);#35;#Kugendran, Shanmugathasan (MCCSS);#19;#Torrance, Tyler (He/Him) (MCCSS);#37;#Pawlowski, Walter (MCCSS);#36 | Kabiawu, Joachim (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A024 | Elasticsearch, Logstash and Kibana (ELK) Enterprise Tool Implementation (Project) | Lead implementation of ELK as central logging tool for CPIN and FCMS to comply with TRA recommendations. | Grow (Enhancements) | Audit Requirement;#Security Compliance | Project/initiative | Advance Our Technology Platforms |  | CW - Child Welfare & Protection;#FRO - Family Responsibility Office | CPIN;#FCMS |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) | Peter Wright, Cedric Wang |  | CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#EAO - Enterprise Architecture Office | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  | The completion of this work item is a carry over from 2022-23 with most of the remaining work for solution DEV teams to test and confirm functionality of the tool. There will be ongoing cost for the hosting of the Logstash VM server to be setup to support each of the application solutions | Finishing in year |  |  | Confirmed | In Progress | Green | 61% | 100% | Complete Logstash server setup | 20% | 100% | End-to-end connectivity | 20% | 100% | Set up logs ingestion for all environments | 30% | 40% | Users set and onboarding | 30% | 30% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A025 | Operational Support for CYSSC Windows & .NET based applications & solutions | Provide operational support to cluster solution branches; servers and OS availability for Windows and SQL; performance, monitoring, capacity, licensing, SSL, evergreen process, release. OACIS, PEIS, PSSAH, ACW, IdeasWeb, DAD, FWDS, ISCIS, CARS, DDI, MRM, ESMS&ESMS-SPM, ChatBot, ALM, SMIS). Incoming: CR, VRTR, FCISKids) | Run - Applications | Keeping the Lights On | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide | ACW;#DAD;#Fieldworker;#CAR;#PEIS;#PSSAH;#DDI;#ESMS;#SMIS;#OACIS |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) | Patel, Jesal |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A026 | Upgrades/patches to development, testing and DevOps tools | Keep the CYSSC DevOps toolkits on support and maintenance path; Jenkins Upgrade; potential RTC upgrade if required beyond Q3 2023 | Run - Applications | Application Evergreening | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A027 | Performance Tuning | Conduct infrastructure hardware/operating system/software (middleware) component health checks, tuning, and efficiency improvements. OS, DB, middleware, applications, scripting, systems health checks. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A028 | Application Support and Maintenance for other MCCSS Applications | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | PSSAH;#SALIS;#DAD;#DAS;#PEIS;#Compliance Sheriff;#mFTIS;#HCD ISCIS |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21;#Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A029 | CYSSC Platform Support Services | Provide CYSSC platform services related to: - server & network provisioning (WIA), OS patching, capacity, monitoring & alerting; cost estimations and projects execution oversight; - Vendor support priority engagement - IBM , Oracle, Microsoft - Solution on-boarding and service management design (KAs/KRs, support model...) - Vulnerabilities assessment and remediation; provide updated data on vulnerabilities and location; | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A030 | Applications Monitoring and Alerting (e.x. Nagios, Prometheus, Azure Monitoring & Insight, ControlM, OEM) | Provide alert notifications and support for CYSSC server and applications monitoring, as well as dashboard capability to support capacity management and planning and trending analysis. In some cases application monitoring scope will be expanded. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A032 | Migrate Source Code Repository from SAMS RTC to GitLab (Project) SAIS A080 | Migrate SAMS source code, SAMS builds process, pipelines, from Rational Team Concert to GitLab & Jenkins on modern DevOps toolkits. Decommission RTC, avoid extended support cost, save on hosting costs, reduce VM server footprint. SAMS is the remaining solution using RTC. The current version of RTC used is on extended support until October 2023. The cost of the extended support is approx $22K. | Run - Applications | Application Evergreening | Project/initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | SAMS |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  | Includes SAIS item A080: Move SAMS builder from KDC to GDC. | Finishing in year |  | 4507700% | Confirmed | Complete/Operationalized | Complete | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A033 | System Patching | Includes patching such as but not limited to; Operating System, web server software, applications software stack, DBs, Curam and others | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A034 | ITS Exadata patching support | Exadata patching occurs twice a year; one in March and the other in September. This is an ITS facilitated work with Oracle and requires planning and communication. The testing phase immediately following the patching requires solution branch teams to help validate functionalities of their respective supported applications. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | CPIN;#HCD ISCIS;#mFTIS;#FCMS;#SAMS;#SALIS |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A035 | SAIS A086: Transition to Operations (TTO) of Digital Applications to IOB | Transition operational support for the remaining SA Digital applications (SADA, and MyBenefits) from SAIS to Operations | Grow (Enhancements) | Keeping the Lights On | Support for other OpPlan initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | SADA;#MyBenefits |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) | Sanjeev Bordoloi, Michael Lau |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 100% | 100% | Directors decision to pause transition of MyBenefits and SADA to IOB. | 100% | 100% | [21 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A036 | Support IBM Authorized Software Program (IASP) Reporting | The IASP report-back is an ITS-led work item that is reported twice a year (in September and in March) and requires the support from all clusters. The report provides an estate-level picture of IBM product licenses within the Topaz agreement that is utilized by clusters/ministries and for entitlement compliance. IOB provides input to IASP discussions in terms of software entitlement compliance at the server level. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Become a Trusted Advisor |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A037 | Server Capacity Right-Sizing | Following the successful migration of all CCP hosted applications from the AIX to the OPCS platform, IOB will continue to monitor and implement right-sizing activities (through CRQs) on OPCS virtual servers with the solution teams to better manage capacity demands and save on hosting costs. | Run - Applications | Keeping the Lights On | Annually recurring initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | CPIN;#FCMS;#HCD ISCIS;#mFTIS;#SAMS |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 0% | 100% | Recommendation | 80% | 0% | Execution of approved recommendations | 20% | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A039 | BIPD: Move to an MCCSS Data Platform | Support BIPD data extraction requirements for reporting/analytics. | Grow (Enhancements) | Minister Commitment | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | CPIN;#FCMS;#HCD ISCIS;#SAMS |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A040 | Support for Identity and Access Management (IAM) Modernization (Migrate to OPS/BPS Secure) | Support all application migration to the new modernized Identity and Access Management service (BPS Secure and OPS Secure) following the migration to X509 pre-requisite. | Grow (Enhancements) | Business Modernization/Transformation | Support for other OpPlan initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | CAMS;#CPIN CM;#CPIN Reporting;#CPIN FM;#FCMS;#mFTIS;#SAMS;#VQRP+ |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Tentative |  | Need to schedule all the work so IOB can support properly. | Finishing in year |  |  | Tentative - pending funding | In Progress | Green | 70% | 100% | mFTIS Migration | 10% | 100% | CPIN Move to x509 | 20% | 100% | CPIN Migration to OPS/BPS Secure | 20% | 100% | SAMS Migration to OPS/BPS Secure | 20% | 50% | FCMS Migration to OPS/BPS Secure | 20% |  | OACIS Migration to OPS/BPS Secure | 10% | 100% | [6 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A042 | Kingston Data Centre Migration/Decommissioning Windows & Linux-based applications (Project) | - Coordinate by Q3 2023-24 the migration of all remaining CYSSC applications out of KDC (CR, VRTR, SPSS, SMIS, CARS, ACWI, OACIS/PEIS and IFIS Payfile). -Decommission all CYSSC KDC servers before end of Q4 2023-24 | Transform | Application Sustainment & Maintenance | Support for GovTechON initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | ACW;#ACW/I;#CAR;#OACIS;#SMIS;#Toronto Region Visitor Registration;#Counter Registration |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 66.75% | 100% | Q2: CR, VRTR, ACWI, CARS, FW-CESCR, IFIS File Transfer, SPSS. | 35% | 100% | Q3: OACIS, PEIS, SMIS, Team Foundation | 35% | 35% | Q4: Decommission server infrastructure | 30% | 65% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A043 | Account Administration/Access Management | Provide account administration for: - User account admin on FED EI application, MTO, NCBS, RBC, OSAP. - PKI user account admin 20k users (SAMS, ESMS, CPIN, mFTIS) - FCMS user account and role administration - RACF user administration - Third Party Access Management | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | FCMS;#PKI |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A046 | CMO A151: 2023 OAGO VFM Audit of the OCCIO | Provide operations support for 2023 OAGO Value-for-Money Audit | Run - Cluster Services | Keeping the Lights On;#Security Compliance;#Audit Requirement | Support for GovTechON initiative |  |  | CYSSC - Cluster-wide | CPIN;#HCD ISCIS;#mFTIS;#FCMS;#SAMS |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A047 | Application Support and Maintenance for Developmental Services Applications | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | DS - Developmental Services | DS;#Fieldworker;#Ideasweb |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22;#Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A048 | Application Support and Maintenance for FRO applications | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | FRO - Family Responsibility Office | FCMS;#FRO Online |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A049 | Operational Support and Maintenance for cloud-based SA applications | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, dev-ops and monitoring, release to production and testing activities to support maintenance and anticipated enhancements. Apps: DDDP, EQFX-Bil, EST, EAP, IRCC-Bil, Messaging, EA. Incoming: MyBenefits, SADA | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS;#SADA;#MyBenefits;#EST |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A050 | Application Support and Maintenance for all Special Needs applications | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | SN - Special Needs | HCD ISCIS;#CPRI Pharmacy Application;#OACIS |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23;#Patel, Jesal (MCCSS);#22;#Iqbal, Azhar (MCCSS);#24;#Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A052 | Implement Fieldworker DS TP Ontario Transition Site Module Integration | Changes required for FW due to TPON implementation | Run - Applications |  | Project/initiative |  |  | DS - Developmental Services | Fieldworker |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 29% | 100% | Planning | 25% | 60% | Development | 40% | 35% | Testing | 35% | 0% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A054 | FRO Digital TruePass to OPS Secure Migration | To migrate from the legacy True-Pass authentication service to OPS Secure the Identity & Access Management corporate preferred service for authenticating OPS users. | Run - Applications | CYSSC Strategy | Project/initiative | Advance Our Technology Platforms | To transition FRO users onto the preferred service for authenticating ensuring the security of high-sensitivity information | FRO - Family Responsibility Office | FCMS |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4501700% | 4519900% |  | In Progress | Yellow | 76.5% | 100% | Design & Planning | 40% | 90% | Development | 30% | 85% | Testing | 20% | 75% | Project Close Out | 10% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A056 | Fieldworker DS Business & Maintenance Releases | Normal maintenance for Fieldworker DS. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational |  |  | CYSSC - Cluster-wide | Fieldworker |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A057 | FieldWorker CESCR Upgrade & Legislative Changes Release | Upgrade FW to v9 and rewrite CESCR application. | Run - Applications | Application Sustainment & Maintenance | Project/initiative |  |  | CYSSC - Cluster-wide | Fieldworker |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Carrying over to next year |  |  |  | In Progress | Green | 14.5% | 100% | Planning | 25% | 50% | Development | 40% | 5% | Testing | 30% | 0% | Close-out | 5% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A059 | Decommission SMIS | Planview ID: 100018345 SMIS is a legacy system to be replaced by Transfer Payment (TP) Ontario enterprise solution​ As of April 1st, 2020, regional staff started using TP Ontario Enterprise System for TP budget submissions​ The TP Ontario team is working to enable functionality to allow Site and Service administration for Wave 2 ​(timelines TBD) ​SMIS is currently hosted in Kingston Data Center (KDC)​. As part of the Cloud Adoption Journey, all applications hosted in KDC have to be moved to another hosting environment or decommissioned by FY 2022- 2023​- Q4 | Run - Applications | CYSSC Strategy | Ongoing/Operational |  |  | MCCSS - Ministry-wide | SMIS |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Yellow | 7% | 100% | SMIS Data Archival | 70% | 10% | Decommission SMIS | 30% | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A060 | Implement DSCIS-TPON Integration | Integrate DSCIS with TPON through DDI. Includes changes to DSCIS as well as validation of DS data for implementation of Site Module in TPON. | Grow (Enhancements) | Business Modernization/Transformation | Ongoing/Operational |  |  | MCCSS - Ministry-wide | DSCIS;#TPON |  | SCSI - Shared & Community Services I&IT Solutions | Chan, Harry (MCCSS);#26 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Yellow | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A061 | Implement Dynamic Data and TPON Integration | Data feed from TPON to DSCIS, SOR-RL, Fieldworker | Grow (Enhancements) | Business Modernization/Transformation | Project/initiative |  |  | MCCSS - Ministry-wide | DSCIS;#SOR-RL;#Fieldworker |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 19% | 100% | TPON Site Module Implementation (TPON is responsible for completing this work) | 10% | 100% | Data Population/Validation (Milestone Owner: TPBU & Regional offices) | 30% | 30% | Data Resolution and Switch-over to TPON | 40% | 0% | SMIS Decommissioning | 20% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A065 | SAMS - Core and Technical Enhancements | Budget: 4.255M • Large number of SAMS business and technical enhancements and fixes for complex production known errors. • Business Analysis and architectural support for SAMS releases and Intake activities • SAMS release Integration and End to End test planning, coordination and execution as well as regression testsuite upgrades and automation | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational |  | Deliver defect fixes and enhancements for various SAMS functional areas in a flexible and responsive way jointly prioritized with business | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | In Progress | Green | 50% | 100% | Q1 Update | 25% | 100% | Q2 Update | 25% | 100% | Q3 Update | 25% |  | Q4 Update | 25% | [13 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A066 | SA Digital: SAMS-RBED (1.0 and 2.0) Enhancements and Maintenance | Enhancements and defect fixes to the RBED (1.0-Intake, 2.0) capabilities that have been built so far. This includes: - Addition of new small non complex information sources for RBED 1.0 - RBED 1.0 rules refinement (e.g., expand rules to put through additional case types through auto-grant without manual intervention) - PTRA and Trigger Solution | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | In Progress | Green | 50% | 100% | Q1 Scope for enhancements and maintenance | 25% | 100% | Q2 Scope for enhancements and maintenance | 25% | 100% | Q3 Scope for enhancements and maintenance | 25% |  | Q4 Scope for enhancements and maintenance | 25% | [13 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A067 | SA Digital: SAMS-EDM Maintenance, Enhancements and Support | Covers non-functional enhancements such as performance and scalability challenges (search screen, etc.) as well as fixing known issues and small enhancements | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | SAMS-EDM |  | SAIS - Social Assistance I&IT Solutions | Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division;#I&IT Technical Delivery Division;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | In Progress | Green | 50% | 100% | Q1 Update: SAMS EDM maintenance completed for this quarter, per plans | 25% | 100% | Q2 Update | 25% | 100% | Q3 Update | 25% |  | Q4 update | 25% | [13 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A068 | Curam 8 Upgrade Implementation | Upgrade SAMS from the current version (7) to version 8. | Run - Applications | Application Sustainment & Maintenance;#Security Compliance | Project/initiative | Advance Our Technology Platforms | Create opportunity to embrace new Curam 8 functionality. Potentially extend the life of the technology asset. | SA - Social Assistance | SAMS;#EA;#EST;#MyBenefits;#SADA;#SALIS;#2WAYMessaging |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | CMO - Cluster Management Office;#IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division;#ITS - Infrastructure Technology Services | TRUE | FALSE | Not specified | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4495000% | 4526000% | Confirmed | In Progress | Green | 50% | 100% | Q1 Report | 25% | 100% | V8 Code Delivered for Testing | 25% | 100% | Code Merged with 24.1 and Tested | 25% | 0% | Project Implemented and Completed | 25% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A069 | SA Digital: EST Maintenance & Support | Support and maintain Employment Service Transformation (EST) application. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | EST |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division;#MLTSD Cluster | FALSE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A070 | SA Digital: MyBenefits Maintenance & Support | Support and maintain MyBenefits | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | MyBenefits |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A071 | SA Digital: SADA Maintenance & Support | Support and maintain SADA. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | SADA |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A072 | SA Digital: Messaging Maintenance & Support | Support and maintain Messaging. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | 2WAYMessaging |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#GSIC - Government Services Integration Cluster;#BIPD - Business Intelligence & Practice Division | FALSE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A073 | SA Digital: Digital DDP maintenance | Maintain DDDP. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | DDDP |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#HSC - Health Services Cluster | FALSE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A074 | Emergency Assistance Maintenance and Support | Maintain EA. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | EA |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A075 | SAMS Chrome Extension Manifest V3 upgrade | For all SAMS OPS and BPS users, upgrade their computers' Chrome Extension to the Manifest V3 supported version, before Manifest V2 reaches end of life in 2023. | Run - Applications |  | Annually recurring initiative |  |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division;#BIIB - Business Innovation & Implementation Branch | FALSE | FALSE | [5 empty] | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 100% | 100% | Q1 report | 25% | 100% | Q2 report | 25% | 100% | q3 Report | 25% | 100% | Q4 report | 25% | 100% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A076 | SAMS CPP cost of living increase activities (annual) | Adjust cost of living increases in SAMS annually, including the mock run and actual implementation. | Run - Applications | Keeping the Lights On;#Ongoing Business Operations | Annually recurring initiative | N/A | Yearly activity to ensure CPP cost of living increases are reflected against social assistance recipients entitlements. | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4520000% | 4529200% | Confirmed | Pending | Green | 25% | 100% | Q1 repor | 25% | 100% | Plan for Initiation of the COLA Rate Increase Testing Activities | 25% | 0% | Q3 Report | 25% | 0% | Q4 Report | 25% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A077 | SAMS December pay-run date changes (annual) |  | Run - Applications | Keeping the Lights On;#Ongoing Business Operations | Annually recurring initiative | N/A |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | Legislation | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4526100% | 4529100% | Confirmed | Pending | Green | 0% | 100% | December pay-run change (Nov 2023TBD ) | 100% | [22 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A078 | SAMS T5 issuance (annual) |  | Run - Applications | Keeping the Lights On;#Ongoing Business Operations | Annually recurring initiative | N/A |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | Legislation | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4513900% | 4532300% | Confirmed | Pending | Green | 50% | 100% | Q1 Report | 25% | 100% | Plan for Initiation of the T5 Test Run | 25% | 100% | Complete Test Run for T5 in Non Production Environments | 25% | 0% | Complete T5 Production | 25% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A079 | SAMS TCB annual reconciliation process (annual) |  | Run - Applications | Keeping the Lights On;#Ongoing Business Operations | Annually recurring initiative | N/A |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | Legislation | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4501700% | 4513800% | Confirmed | Complete/Operationalized | Complete | 100% | 100% | Implemented | 100% | 100% | [21 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A080 | Move SAMS builder from KDC to GDC | Move the SAMS builder from the Kingston infrastructure to the Guelph Data Centre infrastructure. | Run - Applications | CYSSC Strategy | Project/initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Stoicescu, Valentin (MCCSS);#23;#Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4474300% | 4510800% | Confirmed | In Progress | Green | 95% | 100% | Develop Scripts | 50% | 100% | Test/Debug/Fix Scripts-SADEVOPS-6 | 50% | 90% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A081 | Environment coordination and third-party testing | Manage the coordination of third part testing activities as well as lower level environments for SAMS. | Run - Applications | Keeping the Lights On | Ongoing/Operational | N/A |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501700% | 4538200% | Confirmed | N/A (ongoing/operational work) | Green | 50% | 100% | Q1 Report | 25% | 100% | Q2 - Continue to Manage SAMS Environment | 25% | 100% | Q3 Report | 25% | 0% | Q4 Report | 25% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A082 | ITGC - Debt Administration Service (DAS) | ITGC design effectiveness testing - Debt Administration System (DAS) | Run - Applications | Audit Requirement | Project/initiative |  |  | SA - Social Assistance | DAS |  | SAIS - Social Assistance I&IT Solutions |  | Syed, Aleem (MCCSS) |  |  | CMO - Cluster Management Office;#Audit Team | FALSE | FALSE | [5 empty] | Finishing in year |  |  | Confirmed | Complete/Operationalized | Green | 100% | 100% | FY 2023-24 | 0% | 100% | FY 2023-24 | 100% | 100% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A083 | DAD, DAS, SDCalc, CAMS, SAS, Office Locator - Maintenance and Support | Provide standard support for DAD, DAS, SDCalc, CAMS, SAS, Office Locator. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A |  | SA - Social Assistance | SD-Calc;#CAMS;#SAS;#DAD;#SDCAMS;#Office Locator |  | SAIS - Social Assistance I&IT Solutions | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Carrying over to next year | 4501700% | 4538200% | Confirmed | N/A (ongoing/operational work) | Green | 50% | 100% | FY 23-24 Scope | 100% | 50% |  | 0% | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A085 | Enhance existing SAMS dev and deployment pipeline | Continue to improve the maturity of the SAMS production deployment pipeline for example automated front end validation and pipe line to pipe line integration with SA Mod application. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501700% | 4538200% | Confirmed | N/A (ongoing/operational work) | Yellow | 18% | 100% | Automated Front End Validation (post deployment)-SADEVOPS-16 | 30% | 60% | Letters improvements to deploy production-ready static content changes - SADEVOPS-137 | 40% | 0% | Centralized real-time logging for batch and ORDS logs - SADEVOPS-110 | 30% | 0% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A086 | Transition to Operations (TTO) of Digital Applications to IOB | Transition to operations of Digital Applications to IOB. | Run - Applications |  | Project/initiative |  |  | SA - Social Assistance | Digital Applications |  | SAIS - Social Assistance I&IT Solutions | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | Carrying over to next year |  |  |  | On Backlog | Yellow | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A089 | Emergency Assistance Migration to GoCloud | Migrate EA hosting from on-prem to public cloud. | Run - Applications | Application Sustainment & Maintenance | Project/initiative | Advance Our Technology Platforms | * Scalability of public cloud hosting platform to any surge in user demand * Higher stability and availability of public cloud hosting platform * Scaling of hosting cost based on usage * Alignment of EA application hosting architecture with other SA digital applications enabling leveraging of resource pool for application support | SA - Social Assistance | EA |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Other | Confirmed | N/A |  | Finishing in year | 4501700% | 4538200% |  | In Progress | Green | 52.8% | 100% | Migration to Dev | 33% | 80% | Migration to Pre-Prod | 33% | 80% | Migration to Prod | 34% | 0% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A090 | Options analysis for alternative to Pivotal Cloud Foundry (PCF) for Digital Applications | Analyze options for an alternative to Pivotal Cloud Foundry (PCF) for Digital Applications. | Run - Applications | Application Sustainment & Maintenance | Project/initiative | Advance Our Technology Platforms |  | SA - Social Assistance | Digital Applications |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | FALSE |  | Other |  |  |  | Carrying over to next year | 4501700% | 4538200% |  | On Backlog | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A091 | ITGC - Digital Disability Determination Package | ITGC design effectiveness testing - DDDP. | Run - Applications | Audit Requirement | Project/initiative |  |  | SA - Social Assistance | DDDP |  | SAIS - Social Assistance I&IT Solutions | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | CMO - Cluster Management Office;#Audit Team | FALSE | FALSE |  |  |  |  | Need clarification from CMO | Finishing in year |  |  |  | On Backlog | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A093 | DSCIS EIAM Implementation | Modernize existing secure access for DSCIS as part of the OPS Enterprise Identity and Access Management (EIAM) initiative. | Run - Cluster Services | CYSSC Strategy | Project/initiative |  |  | DS - Developmental Services | DSCIS |  | SCSI - Shared & Community Services I&IT Solutions | Chan, Harry (MCCSS);#26 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 59.5% | 100% | Development for Azure AD integration and its required change to DSCIS access | 30% | 100% | Azure AD integration to SUS Infrastructure environments (DEV, UAT, TRAINING & PROD) setup | 10% | 70% | Testing (QA, Business-end-end, UAT) | 15% | 60% | User Engagement and User Onboarding to Azure AD | 25% | 30% | Deployments to all environments (DEV, UAT, TRAINING & PROD) | 10% | 60% | Pre-production activities (deployment prep, MOP, training) | 10% | 0% | [6 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A094 | CPIN/OPSDocs Bulk Upload | SPP OPSDocs bulk upload capability. | Grow (Enhancements) |  | Project/initiative |  |  | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Kugendran, Shanmugathasan (MCCSS);#19 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | TRUE |  | SPP/MYP |  |  | Not started yet. No funding approved to work on this item | Carrying over to next year |  |  |  | Pending | Green | 9% | 100% | SPP approved funding | 10% | 90% | Procure resources | 10% | 0% | project plan and development | 80% | 0% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A095 | Oracle eBS 12.2 Upgrade | CPIN's current version of Oracle eBS (e-business suit v12.1) has expired from vendor support. Developed a business case and A3 presentation for the Oracle eBS Upgrade. Currently circulating the upgrade path through ministry approvals | Grow (Enhancements) |  | Project/initiative |  |  | CW - Child Welfare & Protection |  |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#CMO - Cluster Management Office;#EAO - Enterprise Architecture Office | TRUE | FALSE |  | Other |  |  | Slated to be completed by June 2024 | Carrying over to next year | 4486700% | 4546500% |  | In Progress | Green | 31.5% | 100% | Project approval and Business Case | 5% | 100% | Project Planning | 5% | 100% | Resource Hiring and Allocation | 10% | 100% | Environments Testing and Upgrade | 10% | 10% | Project Task Completion | 70% | 15% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | A097 | OIAD R12 - Limit Use and Safeguard PI - CPIN Data Masking Assessment | Scoping for data masking for implementation in the training and test environments is underway. More specific recommendations on how data masking will be incorporated following the pilot project for data masking PSSAH in fiscal year 23/24. | Grow (Enhancements) | Audit Recommendation |  |  |  | CW - Child Welfare & Protection |  |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | FALSE |  |  |  |  | a) is completed b) Part of a larger IOB initiative - data masking There should be a secondardy item to track Data Masking |  |  |  |  | On Backlog |  | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | N/A | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A098 | CPIN - Culturally Appropriate Language | SPP Sector requirement to update CPIN with culturally appropriate language that will be foundational work for Child Welfare Redesign. | Grow (Enhancements) |  | Project/initiative |  | To appropriately reflect the diversity of Ontario and the people being served. Proper statistical gathering | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | TRUE |  | SPP/MYP | Unconfirmed |  | Awaiting Release of funds from TB, pending SPP approved submission | Finishing in year |  |  |  | In Progress | Green | 13.5% | 100% | Release of SPP funds | 10% | 90% | requirements and development | 90% | 5% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Remove/Merge | A099 | CPIN Automation Testing - CM | Set up an automated process for all releases to significantly reduce the testing time during regression cycles for testing activities such as: projects, smoke testing, integration testing, bug fixes related to CM, FM and Reports | Grow (Enhancements) |  | Ongoing/Operational |  |  | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Torrance, Tyler (He/Him) (MCCSS);#37 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget |  |  | Awaiting SPP release of funds to solution this quicker | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q1 CMO validated | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A100 | OPSDocs Migration Planning (CPRI) | Plan the migration of CPRI file servers to OPSDocs. | Transform |  | Ongoing/Operational |  |  | SN - Special Needs |  |  | CYIS - Children & Youth I&IT Solutions | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) | Dan Grandchamp |  | SCSI - Shared & Community Services I&IT Solutions;#Other | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A106 | CYSSC OPSdocs Pilot | Implement OPSdocs for the cluster to develop an efficient process and gain experience in deploying it | Grow (Enhancements) | CYSSC Strategy | Project/initiative | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Grandchamp, Dan (MCCSS);#29 | Samuel, Sheena (MCCSS) |  |  | CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Carrying over to next year |  |  | Confirmed | In Progress | Red | 57.5% | 100% | SCSI Proof of Concept - Go Live | 50% | 100% | CYSSC Implementation | 50% | 15% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A109 | ACOE: Chair & Lead Organizer of Digital Accessibility cross-Ministerial and cross-Cluster Committees and CoP | Chair of Digital Accessibility Advisory Group (DAAG) compromised of business & technical representatives at Team Lead and Management levels; representation from CAB, ODS, ITS, CAC, TBS, ACOE, SOLGEN. Chair of Developers Accessibility Community of Practice (DACP) which hosts over 50 regular members of Developers and other Technical professionals across the OPS. | Run - Applications | CYSSC Strategy | Ongoing/Operational |  |  | ACOE - I&IT Accessibility Centre of Excellence |  |  | IOB - I&IT Operations Branch | Dabideen, Mala (MCCSS);#30 | Muñoz, Jairo (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A112 | Implement Comprehensive and Timely PIAs to Support Privacy Management and Decision-Making | Final SAMS PIA Report and Mitigation plan to be developed. | Grow (Enhancements) | Audit Requirement | Project/initiative |  |  | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | Complete/Operationalized | Complete | 100% | 100% | Scope | 100% | 100% | [21 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | A113 | Limit Use and Safeguard PI in Systems, Test Environments and Minimize Access to PI | Assess opportunity to build reports within core systems to meet user needs instead of extracting the data. | Grow (Enhancements) |  | Project/initiative |  |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE | [5 empty] | Carrying over to next year |  |  | Tentative - pending funding | On Backlog | Yellow | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | N/A | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A115 | CAMS - IAM (BPS Secure) Integration Assessment | Assess migration from Go Secure to BPS Secure | Run - Applications |  | Project/initiative |  |  | CW - Child Welfare & Protection | CAMS |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Pawlowski, Walter (MCCSS);#36;#Acuna, Oscar (MCCSS);#35;#Kugendran, Shanmugathasan (MCCSS);#19;#Torrance, Tyler (He/Him) (MCCSS);#37 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 86% | 100% | Deploy OPS/BPS Secure - mFTIS | 30% | 100% | Deploy OPS/BPS Secure - CPIN | 70% | 80% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | A116 | Decommission Old Child Abuse Register | SPP Create a complete, net-new solution to replace the current CAR system using modern, cloud-enabled technology and Java tool set or decommission the CAR system. | Transform | CYSSC Strategy;#Business Modernization/Transformation |  | Advance Our Technology Platforms |  | CW - Child Welfare & Protection | CAR |  | CYIS - Children & Youth I&IT Solutions | Pawlowski, Walter (MCCSS);#36;#Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) | Bryce, Don (MCCSS) |  | CMO - Cluster Management Office;#EAO - Enterprise Architecture Office | FALSE | TRUE |  | SPP/MYP | Tentative |  | Part of SPP ask Also, waiting to hear what the direction of CAR should be We need to work on moving the server from KDC to GDC |  |  |  |  | In Progress |  | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | N/A | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A117 | Assessment of Consolidation of Non-Indigenous CASs into the Province's Consolidated Financial Statements | Chart of Accounts Consolidation. | Transform |  | Project/initiative |  |  | CW - Child Welfare & Protection |  |  | CYIS - Children & Youth I&IT Solutions |  | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | FALSE |  | Other |  |  | FM is working with policy to determine requirements | Carrying over to next year |  |  |  | In Progress | Green | 50% | 100% | CWS to apply for and receive required funding for 24/25 fiscal | 100% | 50% | [21 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | A118 | Adoption and Crown Ward Imaging System (ACWI) - Replacement | SPP Replace the legacy ACW/I document management system with an enterprise service offering through OPSDocs. | Transform |  |  |  |  | CW - Child Welfare & Protection | ACW/I |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Pawlowski, Walter (MCCSS);#36 | Kabiawu, Joachim (MCCSS) |  |  | CMO - Cluster Management Office;#EAO - Enterprise Architecture Office | FALSE | TRUE |  | SPP/MYP | Tentative |  | Part of SPP ask |  |  |  |  | Pending |  | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | N/A | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | A119 | Adoption Crown Ward System (ACW) - Replacement | SPP Replace the legacy ACW system with a complete, net-new solution, using modern cloud-enabled technology and Java tool sets. | Transform |  |  |  |  | CW - Child Welfare & Protection | ACW |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15 | Kabiawu, Joachim (MCCSS) |  |  | CMO - Cluster Management Office;#EAO - Enterprise Architecture Office | FALSE | TRUE |  | SPP/MYP | Tentative |  | Part of SPP ask - awaiting release of funds |  |  |  |  | Pending |  | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | N/A | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A129 | Customary Care Changes in CPIN | SPP Ensure CPIN is reflective of customary care services for Indigenous and FNIM communities. | Transform |  | Project/initiative |  |  | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | TRUE |  | SPP/MYP | Tentative |  |  | Carrying over to next year |  |  |  | Pending | Green | 0% | 100% | release of SPP funding | 10% |  | Project plan, requirements and development | 90% | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A132 | Operational sustainment for OAP with AccessOAP (Data migration) | Support OAP in the assessment of technology transition to Independent Intake Organization. | Run - Applications |  | Ongoing/Operational |  |  | SN - Special Needs |  |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A133 | CPRI FCIS KIDS/ IDEASWEB Software Replacement Strategy and Planning | Develop a strategy to replace CPRI's client information system and to transfer multiple legacy applications through a new, integrated solution, particularly FCIS KIDS and Ideasweb. | Transform |  | Project/initiative |  |  | SN - Special Needs |  |  | CYIS - Children & Youth I&IT Solutions | Cunningham, Nicki (MCCSS);#20;#Small, Amanda (MCCSS);#73 | Kabiawu, Joachim (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#TBS - Treasury Board Secretariat | FALSE | TRUE | Not specified;#MYP/SPP/TB approved |  |  |  | In year TB submission, risk managed by Ministry in the event of TBS not funded | Carrying over to next year | 4501900% | 4538000% |  | In Progress | Green | 50% | 100% | TB/MBC Report Back | 25% | 100% | RFP Issued | 25% | 100% | DM approval to award contract | 25% | 0% | Award and finalize contract with successful vendor | 25% | 0% | [12 empty] | Carried forward from 22/23 OpPlan |  | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A134 | HCD-ISCIS Modernization Project Phase 2 (IH Forms and API) | Digitize Universal Newborn Hearing Screen (UNHS), Build external Interfaces | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | Reduce Redundant Data Entry: Digitizing the UNHS will reduce manual data entry. Reduce Fax Transmission: A digitized UNHS will enable direct upload into HCD-ISCIS and will eliminate the need for faxing (except as used as a back-up). Meet Early Intervention Targets: Data transmission in almost real-time will enable staff to provide faster access to services and interventions and help meet the goals of early intervention. Cost and Time Reduction: Currently, the cost associated with a paper-based system for UNHS is approximately $280,000 per year. This is inclusive of the cost of one year’s supply of paper, the cost of faxing, and the administrative cost of entering the results into HCD-ISCIS. In addition to cost savings, a digitized UNHS form would save IHP Lead Agencies an estimated 8,500 hours of administrative time per year. HCD-ISCIS modernization has been focused on the Infant Hearing Program in 2021-22 and 2022-23. One of the original objectives of the HCD-ISCIS Modernization initiative is to reduce duplicate data entry and decrease indirect client time for all of the programs administered in HCD-ISCIS. | SN - Special Needs | HCD ISCIS | 100018797 | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) | Enterprise Architecture Office | Operational Branch | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#GSIC - Government Services Integration Cluster;#ITS - Infrastructure Technology Services | TRUE | TRUE | MYP/SPP/TB approved | SPP/MYP | Confirmed | 22/23 – Early Intervention and Special Needs Modernized Technology Foundation | In 2023-24, the project team will focus on migrating the current legacy (Java thick client) application to a web-based, internet facing application that enables further modernization capabilities of business functions through frequent agile releases of business value changes. | Finishing in year | 4523100% | 4538000% | Confirmed | In Progress | Green | 66% | 100% | Safeguards , AGP1+2 Phase 2 & Gate 4 Go-No-Go approval | 15% | 100% | Development & Testing | 60% | 80% | Training & Change Management | 10% | 30% | ITS Service Mgmt /Release Workshop | 5% | 0% | Go Live Activities | 10% | 0% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A137 | Addressing Anti-Black Racism in GovTechON Action Plan | Action, monitor and report on the GovTechON Anti-Black Racism Action Plan Metrics. Management fostering greater involvement and visibility of Black Staff. | Run - Cluster Services | CYSSC Strategy | Project/initiative | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Garant, Kelly (She/Her) (MCCSS);#12;#Tolentino, Abigail (She/Her) (MCCSS);#54 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#OCIO - Office of the Chief Information Officer;#GovTechON | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Carrying over to next year | 4501700% | 4538200% | Confirmed | In Progress | Green | 56.5% | 100% | All staff release of CYSSC 2023-24 Anti-Racism Action Plan June 28th. | 20% | 100% | Build a forms survey tool to track leadership & mgmt. activity to engage Black staff. | 15% | 100% | Investigate a forte tool. | 5% | 10% | Launch survey twice per year. All CYSSC leaders have a commitment in their Forte to take specific steps and actions to enable greater involvement of Black staff. | 15% | 20% | Anti-Black racism is a standing topic at every all-staff event and every cluster or enterprise area event. Directors schedule discussions in their area twice per year. Twice per year data collection to CIO’s and OCCIO. | 45% | 40% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A141 | CYSSC Achieving Equity Working Group and Action Plan | The Achieving Equity Working Group is working to make CYSSC an organization free from racism and systemic barriers. Using media, events, and training, we seek to educate each member of CYSSC and ensure that each member of CYSSC understands that they are of value | Run - Cluster Services | CYSSC Strategy | Project/initiative | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Garant, Kelly (She/Her) (MCCSS);#12;#Tolentino, Abigail (She/Her) (MCCSS);#54 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#OCIO - Office of the Chief Information Officer | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Carrying over to next year | 4501700% | 4538200% | Confirmed | In Progress | Green | 10% | 100% | Deliver Leadership Equity Training. All Mgrs. attended equity training. | 30% | 20% | Create a greater understanding of how equity benefits us all. 25% of CYSSC staff engaged with the AEWG SharePoint site and learning resources. | 10% | 30% | Establish goals for hiring and sponsoring Black staff. Goals for hiring and promotion of Black employees at a rate higher than the Ontario labour force. Track to achieve 80% of those goals within a three-year time frame. | 10% | 10% | Increase the number of Black staff in CYSSC. # of active recruitment campaigns focused on the hiring of Black professionals. # of Black candidates hired through those outreach campaigns. | 20% | 0% | Increasing Black staff in senior and Manager roles. Black Mgmt. increases by 1% y/y to 2025. Improve transparency in hiring Managers. # of Mgr direct assignments vs interviews. # of staff assignments vs interviews. | 30% | 0% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A142 | FRO Digital Statement of Arrears and Interest Calculator - Phase 2 | Expand on the minimum viable product (MVP) we currently have in place: -Further iterate on the SOA Calculator's MVP -Build out the digital framework to scale and support other digital forms -Develop further digital integration to minimize manual processing | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms |  | FRO - Family Responsibility Office | FRO Online |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | TRUE | [5 empty] | Finishing in year |  | 4501600% |  | Complete/Operationalized | Complete | 99% | 100% | Design & Planning | 40% | 100% | Development | 30% | 100% | Testing | 20% | 100% | Project Close Out | 10% | 90% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A143 | SA Digital: SAMS - RBED 2.0: Alert Solution + Automated Loss Prevention | Enhance SAMS to support ongoing eligibility, including: - Alert Solution (Enhanced eligibility verification process) - Automated loss prevention framework | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | Enhanced Eligibility Verification Process (Alert Solution): to complement and further strengthen ongoing eligibility monitoring and program integrity by repurposing and enhancing the current EVP risk assessment model​ Loss Prevention Framework: to complement and strengthen the acceleration of risk-based, technology enabled and client-focused program | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | TRUE | MYP/SPP/TB approved | SPP/MYP | Confirmed | 23/24 – Social Assistance Digital Delivery |  | Finishing in year | 4501700% | 4538200% |  | In Progress | Green | 70% | 100% | Q1 Update | 40% | 100% | Q2 Update | 30% | 100% | Q3 Update | 15% |  | Q4 Update | 15% | [13 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A144 | SA Digital: SAMS - Electronic Document Management (EDM): Transform Scope | a. Digital Integrations (scale EDM service); b. Expansion of E-forms Capabilities; c. Expansion to OW and Centralized Services; and d. Document Assignment Logic Refinement. | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | Project allows for digitization of a client’s file and new incoming mail for retention, including imaging, electronic storage, and retrieval of documentation for ODSP and OW partners. EDM reduces the amount of data entry and paper handling time and enables staff to access files without needing to search through a file room or internal mail system. EDM includes Digital Day 1, which allows staff to scan documents that have been dropped off by clients. Files are immediately digitized and connected to the client’s file, improving response time to client inquires.​ | SA - Social Assistance | SAMS-EDM |  | SAIS - Social Assistance I&IT Solutions | Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#I&IT Technical Delivery Division;#BIPD - Business Intelligence & Practice Division;#ITS - Infrastructure Technology Services | TRUE | TRUE | MYP/SPP/TB approved | SPP/MYP | Confirmed | 23/24 – Social Assistance Digital Delivery |  | Finishing in year | 4501700% | 4538200% |  | In Progress | Green | 50% | 100% | Q1 Update | 25% | 100% | Q2 Update | 25% | 100% | Q3 Update | 25% |  | Q4 Update | 25% | [13 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A145 | SA Digital: EST Product Backlog Enhancements | Enhance Employment Service Transformation (EST) application. | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | * Common Assessment (CA) Re-administration: Tracks changes in a client’s life stabilization needs and outcomes over time in a consistent and measurable way. Helps identify gaps in life stabilization services and inform system-wide resource allocation across the broader human services system. * Expansion of the CA Tool and Action Plan: Enables the delivery of life stabilization services through the provision of case management tools to caseworkers. Rollout of the tools provincially will prepare sites for onboarding to Integrated Employment Services (IES) as EST sites are phased in. * Service Level Determination: Introduces capabilities to track client progress for those that are close to the labour market and may only need low touch or self-directed services from EO. * EST Provincial Rollout: Rollout three additional stages of EST, which include major sites, such as Toronto and Ottawa. Complexity will differ from earlier prototype implementations and may include additional integration work to provide data in a format for municipal peripheral systems. * Participation Benefits: Introduction of a new participation benefit which will provide more flexibility for life stabilization service delivery. * Life Stabilization Provider POC: This is renamed to Simplified e-Referrals for Stability Supports to match policy wording. This provides an electronic method for caseworkers and clients to access community service providers and send/receive referral requests for stability supports to ensure clients become ready for employment. Technical design and proof of concept will be completed with enhancements to EST technologies. * Case Management Tools to Support Decision-Making for Caseworkers: Automated decision-support tools for case workers to support service delivery (e.g. assessing employment readiness decisions; providing client profiles to review demographics and potential supports needed, etc.). | SA - Social Assistance | EST |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#LTC - Labour and Transportation I&IT Cluster;#BIPD - Business Intelligence & Practice Division | FALSE | TRUE | MYP/SPP/TB approved | SPP/MYP | Confirmed | 23/24 – Social Assistance Digital Delivery |  | Finishing in year | 4501700% | 4538200% |  | In Progress | Yellow | 64.5% | 100.1% | Common Assessment (CA) Re-administration | 5.2% | 100% | Expansion of CA Tool and Action Plan | 16.5% | 50% | Service Level Determination | 2.8% | 0% | EST Provincial Rollout | 13.4% | 50% | Participation Benefits | 17.5% | 50% | Life Stabilization Service Provider POC | 8.3% | 100% | Case Mgmt. Tools to Support Decision-Making | 17.5% | 75% | User and Ministry Prioritized Enhancements | 18.9% | 75% | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A146 | SA Digital: MyBenefits Product Backlog Enhancements | Enhance MyBenefits application | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | * Integration with MyBenefits, Identity Verification Service, Public Secure: These integrations will enable a connected and seamless experience across different digital solutions for Ontarians. For social assistance clients, it will expedite the application process and access to benefits, and from a system perspective, it will improve infrastructure security. For example, MyBenefits integration with the enterprise Identity Verification Service (IVS) and Public Secure solutions, will enable social assistance applicants/recipients to leverage the samedigital ID & login across different govt. services. Similarly, the integration with MyBenefits will provide a seamless re-application process for eligible former recipients, completed directly through MyBenefits. Allows for workflow efficiencies for staff, greater transparency and accountability, and an easier re-application process for recipients. The integrations will reduce wait time, increase access to services and reduce the need for applicants to travel into local offices, among other benefits. * Trustee and Spousal Access:Providing access to trustees of one client, multiple clients, and clients who are also trustees, to be implemented iteratively through an MVP/co-design approach. Providing access to spouses (note, level of access is to be determined). There are over 50,000 social assistance recipients with trustees who will benefit from self-service access to support our most vulnerable recipients. * Application for Additional Benefits:Allows recipients to access, complete and submit high-volume benefit requests digitally via MyBenefits, reducing wait times for recipients and workload for staff. * E-forms: Enabling recipients to access high-volume forms directly from their MyBenefits account. Will reduce time required by staff to complete form requests. Auto-complete options within MyBenefits will ensure correct client identification information is recorded on eachform and further reduce client wait times from 72 hours to under 2 minutes. * Income Reporting Enhancements: Will allow clients to change employer information and report income against a new employer via MyBenefits. Information will update in SAMS through MyBenefits integration. Will eliminate need for client to contact caseworker to manuallycomplete update. Other features include reminding clients of ‘unreported income’ through MyBenefits notifications, which will improve on-time reporting of income, as well as reduce monthly benefit suspensions and follow-up work by staff. | SA - Social Assistance | MyBenefits |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | TRUE | MYP/SPP/TB approved | SPP/MYP | Confirmed | 23/24 – Social Assistance Digital Delivery |  | Finishing in year | 4501700% | 4538200% |  | In Progress | Yellow | 39.48% | 100.2% | SADA Integration | 14% | 30% | Public Secure integration | 11.7% | 100% | IVS (Digital ID ) Integration | 11.7% | 0% | Messaging Integration | 8% | 100% | Trustee Access | 31.16% | 50% | Application for additional Benefits | 9.35% | 0% | E- Forms | 10.12% | 0% | Income Reporting Enhancements | 4.15% | 0% | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A147 | SA Digital: SADA Product Backlog Enhancements | Enhance SA Digital Application (SADA) | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | * Expansion - Additional Social Assistance Applications: Expand service to include all applications currently available in the legacy online application (ODSP, Temporary Care and Assistance for Children with Severe Disabilities - ACSD), ensuring all programs are able to access the simplified online application, improving access to services and streamlining processes for staff. This also reduces the need for in-person office visits and phone calls * MyBenefits and Messaging Integration: Improves experience for re-applicants. Supports ODSP referrals from Ontario Works. * Document Upload: Gives applicants an opportunity to provide verification of information at the time of submission (i.e. improved access to services through digital features). Strengthens accountability without extending the amount of time it takes to apply. * Application Status Update: Reduces applicant’s anxiety by enabling self-serve option to check the status of their application online. Diverts calls from the central intake team and makes the process more transparent for client. * ODSP One-Door Entry: Improves experience, reduces barriers and creates efficiencies for ODSP applicants. Applicants can start with Ontario Works application and automatically be bridged to ODSP based on their situation. Supports SA vision and Ontario Digital Service recommendations to streamline & centralize access to services based on identified user need(s). * Emergency Assistance Integration: Supports program vision of streamlining and centralizing access to services. Enhances the client experience by automatically providing the best option for assistance based on an individual’s situation. * Simplified Re-applications: Provides a seamless re-application process for eligible former recipients (e.g. ability to confirm that existing info on file is accurate and only report new information or changes). Enables workflow efficiencies for staff (e.g. reduces time spent on handling duplicate evidence). | SA - Social Assistance | SADA |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | TRUE | MYP/SPP/TB approved | SPP/MYP | Confirmed | 23/24 – Social Assistance Digital Delivery |  | Finishing in year | 4501700% | 4538200% |  | In Progress | Yellow | 26.3% | 100.1% | Expansion - ODSP, TCA, ACSD | 31.6% | 0% | MyBenefits and Messaging Integration | 17.5% | 100% | Document Upload | 5.3% | 100% | Application Status Update | 3.5% | 100% | ODSP One-Door Entry | 21.1% | 0% | Emergency Assistance Integration | 8.8% | 0% | Simplified Re-applications | 12.3% | 0% |  |  |  | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A148 | SA Digital: Messaging Product Backlog Enhancements | Enhance Messaging application | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | * Conversation View: Providing a simplified chain of communications between caseworkers and clients. Copying other communication formats (e.g. e-mail, messenger, etc.). Feature is estimated to improve digital uptake and usability of the service. * Message Forwarding: Allowing staff the capabilities to forward a message to another caseworker for actioning (note, this is a popular request from operations staff). Will streamline services, support staff better in decision-making, and allow for better coverage across case management (e.g. during vacations, sick days, etc.). * Broadcast Messaging: Enables corporate and local office staff to easily send mass communications to target audiences (e.g. to only clients seeking employment, or to only clients with children, etc.). Targeted messaging will improve responsiveness and reduce complexity of program for clients. * Contact Centre Queue Model: Leverages the Contact Centre to manage incoming messages & attachments in a queue and respond to low-level inquiries and forward complex inquiries to caseworkers/centralized processing teams. Integration opportunities with EDM & MyBenefits workflows to effectively manage evidence & document attachments * Digital Integrations (likely integration with SADA and Digital DDP) : Integration of SADA and MyBenefits will provide a seamless experience for applicants and clients through all stages of their social assistance journey. It will lay the groundwork for future features | SA - Social Assistance | 2WAYMessaging |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#GSIC - Government Services Integration Cluster;#BIPD - Business Intelligence & Practice Division | FALSE | TRUE | MYP/SPP/TB approved | SPP/MYP | Confirmed | 23/24 – Social Assistance Digital Delivery |  | Finishing in year | 4501700% | 4538200% |  | In Progress | Yellow | 57.49% | 100% | Conversation View | 3.7% | 100% | Message Forwarding | 4.8% | 100% | Trustee and Spousal Access | 19.3% | 30% | Broadcast Messaging | 7.1% | 0% | Contact Centre Queue Model | 11.3% | 0% | Digital Integration | 32.6% | 100% | User and Ministry Prioritized Enhancements | 21.2% | 50% |  |  |  | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A149 | Ontario Digital Service Digital Identity - Online ID Proofing | Implement online ID proofing capability within SADA. Online ID proofing capability to be developed by CAC. | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SADA |  | SAIS - Social Assistance I&IT Solutions | Dawoud, Safaa (MCCSS);#27 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ODS - Ontario Digital Service;#GovTechON | FALSE | TRUE | MYP/SPP/TB approved | SPP/MYP | Confirmed | 23/24 - Digital Identity: Integration of Social Assistance Digital Application (SADA) with the Identity Verification Module (IVM) |  | Carrying over to next year | 4520000% | 4574700% |  | On Backlog | Yellow | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | A151 | 2022 OAGO VFM Audit of the OCCIO | Coordinate CYSSC response to OCCIO Action Plans addressing the OAGO Audit Recommendations: 2022 VFM Audit of the OCCIO | Run - Cluster Services | Audit Requirement | Project/initiative |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#D'Annunzio, James (MCCSS);#95;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (She/Her) (MCCSS) |  |  | CMO - Cluster Management Office | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4501900% | 4538000% |  | Pending | Green | 0% | 0% | Develop CYSSC Action Plans in Support of the OAGO Audit Recommendations: 2022 VFM Audit of the OCCIO (see Q1 comments) |  | 0% | [21 empty] | Carried forward from 22/23 OpPlan | N/A | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A152 | Mental Health Action Plan | Implement and maintain the cluster's Mental Health Action Plan, including countermeasures | Run - Cluster Services | CYSSC Strategy | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Kernohan, Neill (He/Him) (MCCSS);#41;#Whibley, Alex (MCCSS);#42 | Garant, Kelly (She/Her) (MCCSS) | MCCSS HRSBU |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Tentative | N/A | This is an ongoing piece of work that started in 2021 | N/A (ongoing work) | 4420000% | 4538200% | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% |  |  |  | Implement mental health countermeasures | [20 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A153 | CYSSC Events | Curate and host bi-monthly all-staff meetings. Curate and deliver the annual Learning and Engagement Week. Curate and coordinate monthly CELTs with one in person quarterly. | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Kernohan, Neill (He/Him) (MCCSS);#41;#Whibley, Alex (MCCSS);#42;#Robles, Jemmie (She/Her) (MCCSS);#83;#Tolentino, Abigail (She/Her) (MCCSS);#54 | Garant, Kelly (She/Her) (MCCSS) | CLT | Cluster EAs | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A | This is year over year work | N/A (ongoing work) | 4501700% | 4538200% | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [6 empty] | Deliver Learning & Engagement Conference |  | 0% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A154 | Employee Experience Survey | Review the CYSSC results from the EE survey; develop and host deep dive sessions with CLT and cross functional & specific teams (e.g, women management), identify areas for improvement and develop an action plan, make recommendations to CLT and Implement approved action plan. Prepare communications for OPS EE survey launch and when results available. | Run - Cluster Services | CYSSC Strategy | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Kernohan, Neill (He/Him) (MCCSS);#41;#Whibley, Alex (MCCSS);#42;#Robles, Jemmie (She/Her) (MCCSS);#83;#Kharal, Sehar (MCCSS);#163 | Garant, Kelly (She/Her) (MCCSS) | CLT |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A | Ongoing work year over year | N/A (ongoing work) | 4501700% | 4538200% | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A155 | 2023/24 Operational Plan | Develop, update and maintain the 2023/24 Operational Plan. | Run - Cluster Services | CYSSC Strategy | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Whibley, Alex (MCCSS);#42;#Jarvis, Meg (She/Her) (MCCSS);#10 | Garant, Kelly (She/Her) (MCCSS) | CLT | All staff | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) | 4493500% | 4538200% | Confirmed | N/A (ongoing/operational work) | Green | 67% | 100% | Deliver 2023/24 Operational Plan | 60% | 100% | Q1 Health Check | 10% | 70% | Q2 Health Check | 10% | 0% | Q3 Health Check | 10% |  | Q4 Health Check and Close out | 10% | [10 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A156 | Review and Refresh Cluster Internal Governance Process | Review and make continuous improvements to Cluster internal Governance Processes | Run - Cluster Services | CYSSC Strategy | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Whibley, Alex (MCCSS);#42 | Garant, Kelly (She/Her) (MCCSS) |  |  | EAO - Enterprise Architecture Office | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 75% | 100% | Develop and Pilot CYSSC Intake template | 50% | 100% | Update and implement new CEOC AGP template | 50% | 50% | Other milestones TBD | 0% | [16 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A157 | CYSSC Performance Measurement | Develop and implement a cluster performance measurement and reporting framework. This includes work done on KIT and MDCF. (includes operational and strategic measurement side; e.g. A3 performance measuring, project, operational, etc.) | Run - Cluster Services | CYSSC Strategy | Project/initiative | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Whibley, Alex (MCCSS);#42;#Jarvis, Meg (She/Her) (MCCSS);#10 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE | [5 empty] | Carrying over to next year |  |  |  | In Progress | Green | 37% | 100% | Determine and manage MDCF for 23/24 | 10% | 100% | Determine future of KIT | 5% | 50% | Plan for performance reporting for Strategy close out | 50% | 15% | Develop tracking and reporting of OP items | 15% | 100% | Link IT value Story into performance | 20% | 10% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A158 | Governance Secretariat Support (CEOC) |  | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Whibley, Alex (MCCSS);#42;#Sparks, Sarah (MCCSS);#59 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | Provide all secretariat support for CEOC |  | 25% | [21 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A159 | Planview Support and Operations | Ongoing administrative support for Planview | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Whibley, Alex (MCCSS);#42;#Sewcharran, Brandon (MCCSS);#92;#Fox, Jesse (He/They) (MCCSS);#91 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE | [5 empty] | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A160 | Strategic Planning Process | Coordinate and support annual strategic planning process. | Run - Cluster Services |  | Annually recurring initiative |  |  | MCCSS - Ministry-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#Zhang, Jerry (MCCSS);#97;#Wong, Kenneth (MCCSS);#98 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE | MYP/SPP/TB approved | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4517000% | 4538000% |  | In Progress | Green | 35% | 100% | SPP Submission | 70% | 50% | SPP Q&A | 30% | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A161 | Maintain and Support CYSSC Online, CMO SharePoint and Cluster SharePoint Requests |  | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational | N/A |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Whibley, Alex (MCCSS);#42;#Dogantzis, Rosie (MCCSS);#88;#Kelly, Danielle (MCCSS);#89;#Mayor, Hannah (She/Her) (MCCSS);#90 | Garant, Kelly (She/Her) (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A162 | Develop and Support Ongoing Communications Products | Develop and support ongoing communications products, including newsletter, training newsletter, annual report, CIO emails and videos, etc. | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Whibley, Alex (MCCSS);#42;#Kelly, Danielle (MCCSS);#89;#Dogantzis, Rosie (MCCSS);#88;#Mayor, Hannah (She/Her) (MCCSS);#90 | Garant, Kelly (She/Her) (MCCSS) | OCIO | MCCSS CMB, GovTechON/OCCIO | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A163 | Forecasting/Budgeting/TCO | Develop and maintain the forecasts, KLTO, TCOs, including monitoring, forecasting, cashflow, year-end and financial updates to CLT. | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 62.5% | 100% | Baseline budget | 15% | 100% | Baseline TCO/KTLO | 10% | 100% | Monthly forecasting and reporting | 75% | 50% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A164 | Base Budget Review | Complete the Base Budget review exercise (January - June 2022). Ongoing process to be developed to determine IT Funding Model (ITFM) needs/make adjustments during SPP. | Run - Cluster Services |  | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | Base Budget Review Completed |  | 100% | Process for ITFM Annual Adjustments |  | 100% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A165 | Transactional Processing | Process transactions, including A/P, A/R, User Seat Billing, Client Recoveries | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational |  |  | CYSSC - Cluster-wide | eBill |  | CMO - Cluster Management Office | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 36.5% | 100% | Recoveries | 30% | 25% | User Seat Billings | 30% | 40% | Journal Entries | 30% | 40% | Misc invoices, transaction processing | 10% | 50% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A166 | Enterprise Risk Management Reporting | Provide and coordinate quarterly updates to the MCCSS Risk Registry. | Run - Cluster Services |  | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#D'Annunzio, James (MCCSS);#95;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501900% | 4538000% |  | N/A (ongoing/operational work) | Green | 50% | 100% | Q1 Report | 25% | 100% | Q2 Report | 25% | 100% | Q3 Report | 25% | 0% | Q4 Report | 25% | 0% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A167 | Provide Audit Coordination and Support - Other Audits and Audit Supports | Provide coordination and support for all OAGO and OIAD audits which includes: working with branches to provide updates; monitoring progress; reporting, and; providing support to the OCIO for Sector Audit Committee meetings. Coordinates the annual Certificate of Assurance and OAGO Attestations. | Run - Cluster Services | Audit Recommendation;#Audit Requirement | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#D'Annunzio, James (MCCSS);#95;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501900% | 4538000% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A168 | Provide Ongoing Support for TB Submissions | Provide coordination and support for in-year Treasury Board submissions. | Run - Cluster Services | Business Modernization/Transformation | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#Zhang, Jerry (MCCSS);#97;#Wong, Kenneth (MCCSS);#98 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501900% | 4538000% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A169 | Procurement Services | Coordinate and support all Cluster procurement and reporting requirements, including contribution to TB/MBC submissions where appropriate. | Run - Cluster Services | Keeping the Lights On | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Nichol, Cindy (MCCSS);#43 | Garant, Kelly (She/Her) (MCCSS) | All Branches |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  | Ongoing work | N/A (ongoing work) | 4496400% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | N/A | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A170 | Run the Student Recruitment Programs |  | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Awad, Mohamed (MCCSS);#57 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A171 | Bargaining Agent Work | Coordinate and complete bargaining work for CYSSC. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Awad, Mohamed (MCCSS);#57 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A174 | Workforce Reporting | Complete monthly workforce reporting. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Awad, Mohamed (MCCSS);#57 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A175 | Business Continuity | Complete business continuity activities, including disaster recovery and call tree exercises. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Awad, Mohamed (MCCSS);#57 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A176 | Joint Health and Safety | Coordinate Joint Health and Safety for CYSSC at North York locations, including building leadership, management of fire warden and first aid training for the cluster and associated strategies. | Run - Cluster Services | Legislation | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Awad, Mohamed (MCCSS);#57 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A177 | 23/24 Procurement Plan | Develop, implement and maintain the 23/24 procurement plan for CYSSC. | Run - Cluster Services | CYSSC Strategy | Annually recurring initiative | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Nichol, Cindy (MCCSS);#43 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4496400% | 4508200% |  | Complete/Operationalized | Green | 100% | 100% | Meet with SAIS Branch | 20% | 100% | Meet with CYIS Branch | 20% | 100% | Meet with SCSI Branch | 20% | 100% | Meet with IO Branch | 20% | 100% | Meet with EAO | 20% | 100% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A181 | Software licence management | CMO Procurement will work with Solution Branches and Operations Branch to strengthen the annual review of license usage to ensure licenses are reassigned or noted where staff have left the organization. | Run - Cluster Services | Audit Recommendation | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Kabiawu, Joachim (MCCSS);#14;#Syed, Aleem (MCCSS);#31;#Muñoz, Jairo (MCCSS);#18;#Obias, Joven (MCCSS);#21;#Nichol, Cindy (MCCSS);#43 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4498600% | 4538200% |  | N/A (ongoing/operational work) | Green | 100% | 100% | Outline current process for licence tracking and how licences are reassigned | 20% | 100% | Create tracker for Curam licences, including current term, cost and number of licences | 40% | 100% | Create tracker for other licences, including current term, cost and number of licences | 40% | 100% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A187 | Cost centre and accounting code framework to ensure appropriate tracking of expenditures and capitalization | CMO Controllership to develop a cost centre and accounting code framework to ensure appropriate tracking of expenditures and capitalization. CMO Controllership will work with branches to ensure that FFS timesheets and vendor invoices provide adequate detail to enable accurate classification. | Run - Cluster Services | Audit Recommendation | Project/initiative |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4517000% | 4538200% |  | In Progress | Green | 0% | 100% | Planning | 25% | 0% | Complete the framework | 75% | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A189 | Recruitment strategy | Includes ongoing recruitment assessment of ongoing recruitments and reporting, exploring options around future recruitments e.g., open location. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Awad, Mohamed (MCCSS);#57 | Garant, Kelly (She/Her) (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A190 | CYSSC training strategy | Develop and implement the 2023-24 CYSSC Training strategy inlcuding required procurements. This includes management of mandatory training and management of pluralsight licenses. This also includes leadership training and development. Has links to EHWW SO 1 & 2 countermeasures. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Awad, Mohamed (MCCSS);#57 | Garant, Kelly (She/Her) (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Yellow | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A192 | Disaster Recovery Testing | - April 22-26, 2024 (resource change freeze April 19-28, 2024) - April 28-May 2, 2025 (resource change freeze April 25-May 4, 2025) - April 27-May 1, 2026 (resource change freeze April 24-May 3, 2026) - April 26-30, 2027 (resource change freeze April 23-May 2, 2027 - April 24-28, 2028 (resource change freeze April 21-30, 2028) Develop and conduct a Disaster Recovery Exercise (DRE) to validate the effectiveness of the Disaster Recovery Plan. The DRE includes roles and responsibilities, resource and facility requirements, key contact information and detailed step by step recovery procedures pertaining to all mission critical applications. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Awad, Mohamed (MCCSS);#57 | Garant, Kelly (She/Her) (MCCSS) |  |  | IOB - I&IT Operations Branch;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4540400% | 4540800% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A193 | Gratitude and Recognition | Develop an integrated program and implement the plan for gratitude and recognition in CYSSC | Run - Cluster Services | CYSSC Strategy | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Whibley, Alex (MCCSS);#42;#Robles, Jemmie (She/Her) (MCCSS);#83;#Mayor, Hannah (She/Her) (MCCSS);#90;#Kernohan, Neill (He/Him) (MCCSS);#41;#Fox, Jesse (He/They) (MCCSS);#91 | Garant, Kelly (She/Her) (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 65% | 100% | Work MCCSS on long service recognition catch up | 25% | 100% | Develop a new approach to long service recognition in CYSSC | 25% | 80% | Develop and implement a recognition and possibly rewards program in CYSSC (gratitude project phase 2) | 25% | 30% | Make recommendation on future cadence of CIO emails (gratitude project phase 1) | 25% | 50% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A195 | Maturing CYSSC Vendor Management in the Cluster | Manage policies and processes. Establish organizational governance and measure and report on vendor management performance, risk and knowledge transfer activities. | Run - Cluster Services | Audit Recommendation | Project/initiative |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Nichol, Cindy (MCCSS);#43 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  | ongoing | Finishing in year | 4498600% | 4757300% |  | In Progress | Green | 29% | 100% | CLT endorsement to establish working group to review current process and establish Cluster VM strategy | 10% | 100% | A3 - KPIs / Metrics | 30% | 30% | A3 - Knowledge Transfer | 20% | 50% | Establish VM Cluster Strategy from A3 outcomes | 20% | 0% | Establish Change Management Strategy | 20% | 0% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A196 | Engagement with Cyber Security | Ongoing engagement with Cyber Security Division to align CYSSC and MCCSS needs with Enterprise Security policies and standards to help address potential cyber-threats. | Run - Cluster Services | Security Compliance | Ongoing/Operational | Advance Our Technology Platforms | Lead and support the development of Security policies, standards, and procedures for CYSSC and MCCSS in conjunction with Cyber Security (CS) Division. Includes support of development and implementation of CS services. | CYSSC - Cluster-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | FALSE |  | Other | Tentative | N/A |  | N/A (ongoing work) | 4501900% | 4538000% | Confirmed | N/A (ongoing/operational work) | Green | 50% | 100% | Reaching out to Cyber-Security Division to provide input, guidance and assistance on matters related to Cyber-Security Threats | 100% | 50% | [21 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A197 | Enterprise Architecture Governance | Review, endorse and approve projects through the Cluster Exec Operational Committee & Corporate Architecture Review processes; Participate in the OPS enterprise architecture governance committees (ARB) and architecture domain workgroups ; Provide review of Cluster and Corporate I&IT standards, policies and guidelines; Participate in EA Modernization planning and implementation; Provide early engagement on project solution architecture planning & guidance as needed | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational | Advance Our Technology Platforms | Ensure Architecture design and deliverables align to OPS standard and industry best practices | EA - Enterprise Architecture |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) | 4501900% | 4538000% | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | Verify, validate and update EA intake forms |  | 25% | Perform AGP0 review on new initiatives |  | 25% | Perform AGP1, 2 and 3 review on initiatives |  | 25% | Updates to CEOC on AGP endorsement/approval for projects |  | 25% | Participation in Corporate ARB meetings for EA approvals of OPS projects |  | 25% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A198 | CYSSC enterprise architecture program management | Manage and oversee the CYSSC enterprise architecture program including Architecture Community of Practice | Run - Cluster Services |  | Ongoing/Operational | Advance Our Technology Platforms | Develop and maintain the EAO Mandate & Services profile, Cluster Architecture Principles, Advancing our Technology Platforms Strategic Direction. Ensure the ongoing operation of the Architecture Community of Practise (ACOP) for knowledge sharing, ongoing maintenance and promotion of architecture best practices, standards and training; Promote and raise awareness of architecture, roles and responsibilities, related tools and methodologies; Provide strategic advice to portfolio branches for Intake/feasibility analysis (e.g. SOAP) which includes review of conceptual solution scope, strategic alignment, potential solution option(s) and recommended option; Development of Cluster Enterprise Reference Architectures and usage patterns (as required) which are re-useable across solutions (e.g. mobile, BI/DA, cloud); Development of Cluster Architecture Baseline framework, plan and definition of roles and responsibilities to support Digital transformation roadmaps based on business strategy; Provide support & analysis for Application Portfolio Management and review against Ministry strategies /MYP & IT Roadmaps for horizontal opportunities | CYSSC - Cluster-wide;#EA - Enterprise Architecture |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) | 4501900% | 4538000% | Confirmed | N/A (ongoing/operational work) | Green | 100% | 100% | Regular monthly engagement with ACOP | 25% | 100% | Bi-weekly strategic direction working group (SDWG) meetings for ATP | 25% | 100% | Addressing countermeasures for SDWG-ATP | 50% | 100% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A199 | Corporate and Enterprise I+IT engagement and alignment | Ensure cluster strategic alignment with Enterprise IT initiatives (TRIP Enterprise Technology Roadmap, ITS, CyberSecurity, IAM, ODS roadmaps) through ongoing engagement with enterprise stakeholder partners. | Run - Cluster Services |  | Ongoing/Operational | Advance Our Technology Platforms | Ensure Ministry applications and solutions align with corporate I&IT guidelines and practices | Enterprise I&IT;#CYSSC - Cluster-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) | 4501900% | 4538000% | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | Engagement with ODS on as-need basis based on project needs |  | 25% | Engagement with TRIP on as-need basis based on project needs |  | 25% | Engagement with Cyber-Security and ITS on as-need basis based on project needs |  | 25% | [15 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A200 | OCIO Management and Operations | Support the implementation of strategic, operational, and cultural divisional agenda, including timely advice and responses to internal and external divisional issues and requests. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | OCIO - Office of the Chief Information Officer | Carter, Ann (MCCSS);#45 | Carter, Ann (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#CMO - Cluster Management Office | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A201 | SAMS Interactive Voice Response (IVR) support | Provide help desk support for IVR. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | SA - Social Assistance |  |  | SCSI - Shared & Community Services I&IT Solutions | Mackiewicz, Rick (MCCSS);#46 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A202 | Consult & Implement of the Public Access Terminals (PAT) | Provide consultation and implementation support services for implementation of the ODSP PAT. This is a client project that CSU is involved in support of IT component. The project was originally approved by Jan 17, 2017and was then put on hold due to the freeze of the whole OPS during 2017-18 and was re-started in May 2019. | Run - Cluster Services | Business Modernization/Transformation | Ongoing/Operational |  |  | SA - Social Assistance |  |  | SCSI - Shared & Community Services I&IT Solutions | Mackiewicz, Rick (MCCSS);#46 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | Complete/Operationalized | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A203 | ACOE Enterprise Supports & Services | Providing Training, Consultations, Advice & Guidance, Accessibility Assessment best practice, newsletter and various digital accessibility events. Administration of ACOE InsideOPS site, Intake service and a suite of Testing Tools. | Run - Cluster Services |  | Ongoing/Operational |  |  | ACOE - I&IT Accessibility Centre of Excellence |  |  | IOB - I&IT Operations Branch | Dabideen, Mala (MCCSS);#30 | Muñoz, Jairo (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A204 | Tier-2 incident management and service fulfillment for 12 applications | Tier 2+ service support for the following applications: Counter Registration, DSCIS, ESMS, ESMS-SPM, KIDS – FCIS, Pharmacy, PEIS, PSSAH, Toronto Region Visitor Registration application (TRVR), Freedom of Information (FOI) Request Management System, Ministry Resource Manager (MRM), eBill | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide | DSCIS;#ESMS;#ESMS-SPM;#KIDS-FCIS;#CPRI Pharmacy Application;#PEIS;#PSSAH;#TRVR;#MRM;#eBill;#SIS Reporting Tool Service;#Freedom of Information Request Management System;#Toronto Region Visitor Registration;#Counter Registration |  | SCSI - Shared & Community Services I&IT Solutions | Patrick, Christine (MCCSS);#47 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A205 | Support accommodations | -Potential political Ministry re-organizations and/or office moves; - Co-location of future planned ODSP and OW offices; - MCCSS Realty accommodation plan. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  | 100013860 | SCSI - Shared & Community Services I&IT Solutions | Mackiewicz, Rick (MCCSS);#46 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 3% | 60% | Provide/Consult on IT Services for the Renovation/Relocation of Kirkland Lake ODSP | 30% | 10% | Provide/Consult on IT Services for the Renovation/Relocation of Kenora ODSP | 30% | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A206 | Support telephony updates | Planview ID: 100013849 | Run - Cluster Services | Ongoing Business Operations | Project/initiative |  |  | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Mackiewicz, Rick (MCCSS);#46 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Carrying over to next year |  |  |  | In Progress | Green | 100% | 100% | Updating Telephony Services for ODSP -Centrex 2.0Offices | 50% | 100% | Updating Telephony Services for ODSP -Centrex 2.0 | 50% | 100% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A207 | Quarterly renewals of ministry computers | Work with client to identify legacy assets, manage quarterly renewals. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Mackiewicz, Rick (MCCSS);#46 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A208 | Implement RM module in OPSDocs for RMU Phase 2 (regional offices ECM content) | Develop process, reporting requirements, complete pilot for subset of business function | Run - Cluster Services | Business Modernization/Transformation | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Grandchamp, Dan (MCCSS);#29 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Yellow | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A209 | Support desktop modernization | Oversee and co-ordinate activities related to end-user technology that is being upgraded, implemented or removed as part of the ITS Desktop technology road map. Testing of Windows 11 O/S with CYSSC Applications | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  | Outcomes: Validation of the Widows 11 O/S being compatible with the CYSSC Applications | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Grandchamp, Dan (MCCSS);#29 | Samuel, Sheena (MCCSS) |  |  | CMO - Cluster Management Office;#CWOB - Child Welfare Operations Branch;#CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#BIPD - Business Intelligence & Practice Division;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | Completing validation testing | [23 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A211 | Advisory services: information management | Provide consultation, advice and guidance to the ministry as related to IM needs | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Grandchamp, Dan (MCCSS);#29 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A212 | Develop IM tools to support IMU services | Developing IM tools/resources to support IMU services | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Grandchamp, Dan (MCCSS);#29 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A214 | Email rationalization | OPS clean-up of unused emails to find efficiencies; reduce number of unnecessary accounts | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Mackiewicz, Rick (MCCSS);#46 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A215 | Support MCCSS implementation of enterprise applications/solutions | Enterprise Services Unit to provide guidance, consultation and onboarding support to OPS digital enterprise products for MCCSS programs when required. (e.g. eApprovals, BinderBrowser, OPSdocs eSignature) | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Grandchamp, Dan (MCCSS);#29 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A217 | ACOE digital accessibility and testing modernization strategy | Streamline access to automated testing tools, checkers, and provide hands-on learning to conduct manual accessibility tests; simplify & standardize Accessibility Testing Report; enhance Testing service as a consultation - reduce time spent on conducting tests. Increase opportunities for engagement through Virtual Drop-in sessions with ACOE experts and training services / products. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | ACOE - I&IT Accessibility Centre of Excellence |  |  | IOB - I&IT Operations Branch | Dabideen, Mala (MCCSS);#30 | Muñoz, Jairo (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [14 empty] | 0% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A218 | Reduce dependence on consultants (SAMS VFM audit recommendation) | SAMS VFM Audit 2015 Recommendation - To prevent unnecessary delays in bringing the Social Assistance Management System (SAMS) to full and effective functionality, and to ensure that the consultants still working on SAMS are held accountable for delivering quality results, the Ministry of Community and Social Services should on future projects, work towards reducing its dependence on consultants, and ensure consultants’ knowledge is transferred to ministry staff. Audit Tracker Recommendation VFM.17.15.03.12.02.03.2 OAGO recognize that the Ministry has completed the following: - has reduced its dependence on the consultants, - has developed the Knowledge Transfer framework, - has trained its staff on the Knowledge Transfer framework, - has made necessary changes to vendor contracts. - However, the Ministry has not provided documentation to support the use of KT framework (including, for example, any of the KT checklist, KT plan, knowledge share plan, KT tracking documentation and KT reporting) for knowledge transfer from a consultant to the Ministry’s staff. Based on the above, OAGO assesses this recommended action as “In process of being implemented” with an estimated implementation date of March 2021. | Run - Cluster Services | Audit Requirement | Project/initiative |  |  | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | Complete/Operationalized | Complete | 100% | 100% | Q1 Report | 25% | 100% | Q2 - Meet TB 75:25 Staffing Ratio | 25% | 100% | Q2 - Create KT Framwork and Complete KT | 25% | 100% | Q2 - Skill Gap Assessment and Train Staff | 25% | 100% | [12 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A219 | SDWG ATP - Architecture Intake and Review Engine (AIRE) | An automated BOT to generate EA intake forms based on the operational plan. Automates the initial review of Enterprise Architecture artifacts, produces a detailed compliance report which Enterprise Architects review and respond to. | Run - Cluster Services | CYSSC Strategy | Ongoing/Operational | Advance Our Technology Platforms | Provides early visibility to the upcoming EA Governance pipeline and provide support at the right time for the Governance to projects. Also this helps solution teams to prioritize on the MDCF items | EA - Enterprise Architecture | AIRE |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) | 4465200% | 4501600% | Confirmed | N/A (ongoing/operational work) | Green | 100% | 100% | Build initial version of AIRE to generate automated forms |  | 100% | Enhance product to look for changes on Operational Plan and UI | 100% | 100% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | A220 | SDWG ATP - Lessons Learned Repository (ALDA) | Build an automated bot to gather information from EA AGP3 documents on lessons learned and compile a knowledge exchange to be utilized by all teams in the cluster. Solutions teams will be required to reference ALDA information in all projects | Run - Cluster Services | CYSSC Strategy | Ongoing/Operational | Advance Our Technology Platforms | Provides ability for project managers, managers, architects and other project staff to query on lessons learnt from various projects in the Cluster. Helps to prepare project plans for new initiatives or help to address issues that project teams might be facing with lessons learnt from past projects | EA - Enterprise Architecture | ALDA |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) | 4492700% | 4501600% | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | Build initial version of ALDA |  | 100% | Enhance project based on input and feedback from team |  | 50% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B001 | PSSAH & PEIS Sustainment | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, database maintenance, and testing activities to support maintenance and anticipated enhancements of PSSAH & PEIS | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational |  | Support continue operation of SSAH program | SN - Special Needs | PSSAH;#PEIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Cluster Base Budget | Confirmed |  | To be decommissioned once new application (TPON Phase 2) is online in next fiscal 2024-25 | N/A (ongoing work) | 4501900% | 4538000% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B002 | Evergreening CYSSC Windows OS upgrades | IOB to coordinate/support upgrade. Multiple applications require OS upgrades up from 2012 by Oct 2023 - CARS, ACWi (and possibly others) | Run - Applications | Application Evergreening;#Keeping the Lights On | Annually recurring initiative | Advance Our Technology Platforms |  | CW - Child Welfare & Protection | ACW/I;#CAR;#FCIS-KIDS |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 100% | 100% | Identify impacted inventory. | 20% | 100% | Plan for upgrade or extended support. | 20% | 100% | Conduct upgrades. | 60% | 100% | [15 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B003 | OACIS & PEIS Migration to OPS Secure | Migrate OACIS & PEIS IAM from current Go-Secure to the new Enterprise Solution OPS Secure | Run - Applications | Application Sustainment & Maintenance | Project/initiative |  |  | SN - Special Needs | OACIS;#PEIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#IAM - Identity and Access Management | FALSE | FALSE | [5 empty] | Finishing in year | 4498800% | 4510000% |  | Complete/Operationalized | Complete | 100% | 100% | Kick-off | 5% | 100% | Requirements | 20% | 100% | Approved LOA | 5% | 100% | Environment Build & Test | 60% | 100% | Go-Live | 10% | 100% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B004 | FSI Modernization Project: PSSAH Data Cleansing and Migration | Cleanse and Migrate required data from the existing PSSAH application to the new TPON application | Transform | Application Sustainment & Maintenance | Project/initiative |  |  | SN - Special Needs | PSSAH;#PEIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#Other | FALSE | FALSE |  | Cluster Base Budget |  |  |  | Finishing in year | 4513900% | 4538000% |  | In Progress | Yellow | 5% | 100% | Data Migration to TPON | 100% | 5% | [21 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B005 | OAP Future state planning including OACIS decommissioning | Planning for the next steps for OACIS & PEIS including roadmap planning, the eventual decommissioning and helping Autism Program with a view into historic files etc. | Transform | Application Sustainment & Maintenance;#Business Modernization/Transformation | Ongoing/Operational |  |  | SN - Special Needs | OACIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division;#SCSI - Shared & Community Services I&IT Solutions;#EAO - Enterprise Architecture Office;#Other | FALSE | FALSE |  | Cluster Base Budget |  |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B006 | SDWG - ATP Options Analysis, POC & SPP Business Case Development - CYSSC Service Mesh | Perform options analysis to determine SWOT of extending BIL as the Cluster's Service Mesh. ​ Complex applications are decomposed into a collection of small, independent services that communicate with each other through APIs.​ ​ Each service is focused on a specific business capability and can be developed, deployed, reused and maintained independently.​ ​ Minimal enhancement of existing applications e.g. SAMS, FCMS, CPIN, DSCIS ​Trace - Digital Transformation + Data Management Strategy | Grow (Enhancements) | CYSSC Strategy | Project/initiative | Advance Our Technology Platforms | Horizontal IT systems integration to support CYSSC Portal - unified data ingestion + Life Course Approach + Tell Us Once | CW - Child Welfare & Protection;#DS - Developmental Services;#FRO - Family Responsibility Office;#SA - Social Assistance;#SN - Special Needs | SAMS;#CPIN;#FCMS;#DSCIS |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division;#CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#GSIC - Government Services Integration Cluster;#GovTechON | FALSE | TRUE |  |  |  |  | Resources required to complete this work | Finishing in year |  |  | Other | In Progress | Green | 87.5% | 100% | Analyze Service Mesh + API Management Options | 25% | 100% | Document rationale + recommendation | 25% | 100% | POC - Define scope, feasibility, evaluate capabilities | 10% | 100% | Complete POC | 25% | 80% | Document POC findings | 15% | 50% | [9 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B007 | SDWG ATP - Options Analysis, POC & SPP Business Case development - CYSSC Portal | Perform options analysis to determine SWOT of MyOntario Portal for CYSSC - MCCSS ​Trace - Digital Transformation + Data Management Strategy | Grow (Enhancements) | CYSSC Strategy | Project/initiative | Advance Our Technology Platforms | Improve the experience of an Ontarian seeking MCCSS support and services.​ ​ Consistent User Experience: A standardized and consistent user interface for citizens to access services, regardless of the underlying technology or system being used.​ ​ Efficient Data Input: A simplify and streamline the process of entering and managing data by providing a centralized platform for data input, which can reduce errors and improve data quality.​ ​ Improved Citizen Engagement: Enhance the citizen experience by providing a single access point for all services and information, reducing frustration and improving engagement.​ ​ Increased Accessibility: Portals can provide easy and accessible information and services to citizens, regardless of their location or device, which can help organizations reach a wider audience and improve accessibility. | CYSSC - Cluster-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  | CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#BIPD - Business Intelligence & Practice Division;#GSIC - Government Services Integration Cluster;#GovTechON | FALSE | TRUE |  |  |  |  | Resources required to complete this work | Finishing in year |  |  |  | In Progress | Green | 87.5% | 100% | Analyze CX Portal Option + Status Quo Options | 25% | 100% | Document rationale + recommendation | 25% | 100% | POC - Define scope, feasibility, evaluate capabilities, | 10% | 100% | Complete POC | 25% | 80% | Document POC findings | 15% | 50% | [9 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B008 | SDWG ATP - Options Analysis, POC & SPP Business Case development- ChatBot for IT Systems | Perform options analysis, POC to determine SWOT of implementing ChatBots to SAMS, CPIN, FCMS, DSCIS internally for staff ​Trace - Digital Transformation + Data Management Strategy | Grow (Enhancements) | CYSSC Strategy | Project/initiative | Advance Our Technology Platforms | Increased efficiency: Automate routine tasks and provide quick and accurate responses to frequently asked questions, freeing up time for employees to focus on more complex tasks.​ ​ Improved customer experience: Provide 24/7 support and offer a convenient, user-friendly way for citizens to access government services, improving the overall customer experience.​ ​ Enhanced data collection: Collect data from citizens, such as feedback and survey responses, helping the government to better understand their needs and improve services.​ ​ Cost savings: Reduce the cost of providing services by reducing the need for manual labor, freeing up resources for other initiatives.​ ​ Improved access to information: Provide citizens with quick and easy access to information about government services and programs, reducing wait times and improving accessibility. | CYSSC - Cluster-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  | CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#BIPD - Business Intelligence & Practice Division;#GovTechON | FALSE | TRUE |  |  |  |  | Resources required to complete this work | Finishing in year |  |  |  | In Progress | Green | 87.5% | 100% | Analyze Chatbot options | 25% | 100% | Document rationale + recommendation | 25% | 100% | POC - Define scope, feasibility, evaluate capabilities | 10% | 100% | Complete POC | 25% | 80% | Document POC findings | 15% | 50% | [9 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B009 | Analysis on Informatica Upgrade / v10.4 Extended Support (Project) | The current Informatica v10.4 we use to provide data integration operations/data warehousing support for SAMS, CPIN, HCD ISCIS, DAS will expire on March 2024. | Run - Applications | Keeping the Lights On | Project/initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | SAMS;#CPIN;#DAS;#HCD ISCIS |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CMO - Cluster Management Office;#SAIS - Social Assistance I&IT Solutions;#CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  | The vendor has provided an unofficial and high level estimate for a one year extended support cost of $85K (from April 1 2024 to March 31 2025). The cluster (through IOB's lead) has 2 options; (1) to project manage the Informatica upgrade in FY2023-24. The project might cause disruption to already planned cluster high priority projects in 23-24 requiring resource time from impacted solution teams, or (2) to buy the extended support for one year allowing the upgrade project sometime to plan and to avoid implementation conflicts with other priority initiatives. | Carrying over to next year |  |  | Confirmed | In Progress | Green | 10% | 100% | CEOC Pre AGP0 Presentation July 13 | 10% | 100% | CEOC Update Presentation - Nov 2023 | 20% | 0% | Build environments | 30% | 0% | Complete all testing | 30% | 0% | Go Live | 10% | [10 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B012 | CMO A192: Disaster Recovery Testing | Disaster Recovery Exercises is an annual activity led by CMO Business Continuity unit to ensure that documented processes for resumption of services of mission-critical applications are tested and reported. In certain situations table top exercise is conducted in lieu of disaster recovery exercises. Either approach is supported by IOB. | Run - Cluster Services | Keeping the Lights On | Support for other OpPlan initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | CPIN;#FCMS;#SAMS |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 100% | 100% | Complete DR exercise scheduled for Apr 24-28 | 75% | 100% | Complete DR de-briefs with Sol'n branches | 25% | 100% | [18 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B013 | SCSI B022: VQRP+ Transition Plan | This work item is contingent on SCSI leading the development of the plan to transition VQRP operational support from MAG to CYSSC. IOB will provide infrastructure and technology support expertise into the transition plans. | Grow (Enhancements) | Application Sustainment & Maintenance | Support for other OpPlan initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Carrying over to next year |  |  | Confirmed | On Backlog |  | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B014 | Lead the Social Assistance Extended Network Access (ENA) Decommissioning (Project) | Lead the decommission of the ENA circuits. Business Innovation & Implementation Branch, Social Assistance Policy, Planning & Innovation Division had asked for CYSSC to investigate the feasibility of decommissioning ENA circuits previously used by SAMS Case Workers in the municipalities following the successful SAMS migration to OPCS. SAMS is now accessible through the Internet (instead of the previous GoNET access only). The ENA circuits are now limited to providing only MCCSS-developed OSAP portal for Case Workers. | Run - Applications | Keeping the Lights On;#Application Sustainment & Maintenance | Project/initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Ministry LOA | Unconfirmed |  | Need support from SCSI (Rick M.) and SAIS. BIIB has requested to look into further savings by decommissioning the ENAs.&nbsp; If completed can save up to $500K/yr | Finishing in year |  |  | Tentative - pending ministry direction | In Progress | Green | 90% | 100% | MCCSS/SAPA & MCU/CSC Mtg in July 2023 | 10% | 100% | Cluster assessment & next action(s): Director BN | 80% | 100% | Remaining steps: Closing the loop with CMO/Business client | 10% | 0% | [15 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B015 | Cognos Upgrade (Project) | Cognos v11.1.7 is used by HCD ISCIS, CPIN and SAMS applications. The current fix-pack 6 includes fixes to additional Log4j related vulnerability. Log4j is a high-severity vulnerability that needs to be remediated. Cognos infrastructure instances are separate between SAMS, CPIN and HCD ISCIS. This item will address the FP upgrade for all 3 application solutions at different times. | Run - Applications | Application Sustainment & Maintenance | Project/initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide | CPIN;#HCD ISCIS;#SAMS |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  | SAIS, CYIS solution teams | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Carrying over to next year |  |  | Confirmed | In Progress | Green | 10% | 100% | Pre AGP0 approved at July 13 CEOC | 10% | 100% | CEOC Report Back - Nov 2023 | 10% | 0% | Implementation | 80% | [16 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B016 | Application Support & Maintenance for all Child Welfare applications | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | CW - Child Welfare & Protection | CAMS;#CPIN;#CPIN Reporting;#CPIN CM;#CPIN FM |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23;#Obias, Joven (MCCSS);#21;#Iqbal, Azhar (MCCSS);#24;#Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B017 | DSCIS Curam V8 Technical Upgrade | Implementation of Curam V8, and supporting technologies (i.e. WebSphere, Oracle, Reporting Remediation) | Run - Cluster Services | Application Sustainment & Maintenance | Project/initiative | Advance Our Technology Platforms | Evergreening of the Curam Technology to retain support from the vendor. In turn, will help to reach industry standards for security and accessibility. | DS - Developmental Services | DSCIS |  | SCSI - Shared & Community Services I&IT Solutions | Chan, Harry (MCCSS);#26 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4489600% | 4538000% |  | In Progress | Green | 66.75% | 100% | SUS Infrastructure – building new environments (DEV, UAT & PROD) | 40% | 75% | UAT, Penetration & Performance Tests | 15% | 60% | Architecture gating (AGP0, 1 &2) | 10% | 90% | Deployments to all environments (DEV, UAT,PROD) | 25% | 75% | Pre-production activities (deployment prep, MOP, training) | 10% | 0% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B018 | DSCIS Application Business & Maintenance Releases | Implementation of priortized Change Requests for the maintenanace to keep the application updated. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | Multiple releases to ensure Policy and Business needs are aligned with the DSCIS application to support DSO programs and initiatives that provide effective programs for individuals and families | DS - Developmental Services | DSCIS |  | SCSI - Shared & Community Services I&IT Solutions | Chan, Harry (MCCSS);#26 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B019 | SharePoint Online: Delivery of corporate SharePoint services, website services intranet/extranet (support/maintenance/development) | (1) Consultation and work to develop new intra-extranet sites in SharePoint Online that come in during the year via multiple Service Requests, including updates to functionality of existing sites (e.g. Diverse Interview Panel Program, Corporate Services Branch site, Indigenous Healing & Wellness Strategy (IHWS) site, etc.) (2) Responding to service requests to decommission unused sites throughout the fiscal | Run - Cluster Services | Application Sustainment & Maintenance | Ongoing/Operational | N/A |  | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Patrick, Christine (MCCSS);#47 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B020 | 2023-24 e-Bill Business & Maintenance Releases | Regular operational releases of prioritized items to support ongoing CMO operations. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | Increased access to and management of information, resulting in improved business processes | CYSSC - Cluster-wide | eBill |  | SCSI - Shared & Community Services I&IT Solutions | Patrick, Christine (MCCSS);#47 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B021 | 2023-24 FOI Request Tracker (FRED) Business & Maintenance Releases | Operational releases of prioritized items to support ongoing Access & Privacy Office, Business Planning and Corporate Services operations. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational |  | Increased access to and management of information, resulting in improved business processes | CYSSC - Cluster-wide | Freedom of Information Request Management System |  | SCSI - Shared & Community Services I&IT Solutions | Patrick, Christine (MCCSS);#47 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B022 | VQRP+ Transition Plan | Victim Quick Response Program+ (VQRP) Database, is an application to support the program to fund services for eligible victims of crime, where no other recourse is available, in the immediate aftermath of a crime. The application is accessed through a network of approximately 50 Service Delivery Organizations (SDOs), nearly all of which are also funded through transfer payment agreements with MAG to deliver the Victim Crisis Assistance Ontario (VCAO) program. Program staff that use the application have transferred from MAG to MCCSS, but the application is currently being run by Justice Technology Services (JTS) The plan is to conduct an analysis to determine the suitability of transitioning the development and support of the tool from JTS to CYSSC. | Grow (Enhancements) | Ministry Request | Project/initiative |  |  | MCCSS - Ministry-wide | VQRP+ |  | SCSI - Shared & Community Services I&IT Solutions | Patrick, Christine (MCCSS);#47 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4480500% | 4519900% | Confirmed | In Progress | Green | 92% | 100% | Planning - Development of Transition Plan | 20% | 100% | Knowledge Transfer/Demos/Architecture Review | 50% | 100% | Training/Upskilling of existing team | 20% | 90% | Service Planning Activities | 5% | 80% | Transition cut-over | 5% | 0% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B023 | Develop Options Analysis Future of MRM | Develop & Finalize the Options Analysis for MRM | Grow (Enhancements) | Application Evergreening | Project/initiative |  | MRM, a highly used legacy tool used for managing Ministry resources (meeting rooms, equipment, fleet vehicles, etc.) has been out of vendor support for a few years and is approaching end of life. Options analysis was started 2022/23 and will continue into Q1 of 2023/24 | MCCSS - Ministry-wide | MRM |  | SCSI - Shared & Community Services I&IT Solutions | Patrick, Christine (MCCSS);#47 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 96% | 100% | Finalization of Business Requirements | 25% | 100% | Consultation with ITS concerning Enterprise Service tools | 10% | 100% | TRIP Consultation | 5% | 100% | Options Analysis | 50% | 100% | Review of Options Analysis Outcome | 10% | 60% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B024 | Chatbot as a Service | To standardize chatbot service management across CYSSC Conduct option analysis for Chatbot Modernization Develop a POC to test and validate the recommended modernization option | Grow (Enhancements) | Business Modernization/Transformation | Project/initiative |  | Provide easy access with quick response time to key information resources to the CYSSC and MCCSS staff. Improve the interactive conversation with the cluster and ministry users ​ | CYSSC - Cluster-wide | ChatBot |  | SCSI - Shared & Community Services I&IT Solutions | Awad, Mohamed (MCCSS);#57 | Samuel, Sheena (MCCSS) |  |  | EAO - Enterprise Architecture Office | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 100% | 100% | POC | 100% | 100% | [21 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B025 | SAIS A068: Curam 8 Upgrade Implementation | Support the planning and implementation of SAMS Curam v8 upgrade. | Run - Applications | Application Evergreening | Support for other OpPlan initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B026 | SA Digital: SAMS-Match & Merge Enhancements and Maintenance | Maintain SAMS Automated Match and Merge functionality | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational |  | * Keeping the lights on of the application * Deliver defect fixes and minor enhancements jointly prioritized with business | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Ministry LOA | Confirmed | N/A |  | N/A (ongoing work) | 4501700% | 4538200% |  | In Progress | Green | 50% | 100% | Q1 Update: SAMS M&M maintenance completed for this quarter, per plans | 25% | 100% | Q2 Update | 25% | 100% | Q3 Update | 25% |  | Q4 Update | 25% | [13 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B027 | SD Calc Refactoring | Refactoring the SD-Calc application to improve functionality and reduce technical complexity | Grow (Enhancements) | Ongoing Business Operations | Project/initiative | N/A | Reduced manual work and improved system sustainment | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4492700% |  | Confirmed | In Progress | Green | 65.9% | 100% | Design | 20% | 100% | Development | 40% | 90% | Testing | 30% | 33% | Implementation | 10% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B028 | Migrate Field Worker CESCR out of KDC | As part of the Cloud Adoption Journey, the Kingston Data Centre (CAJ-KDC) project, the Kingston Data Centre is to be shut down. Applications hosted in KDC are required to move to new infrastructure by end of 2022/2023 fiscal year. FW DS are both hosted in KDC, so these two applications have to be moved to another infrastructure. | Run - Applications | Application Evergreening | Project/initiative |  | Solution will be moved to the Cloud | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Awad, Mohamed (MCCSS);#57 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | Complete/Operationalized | Complete | 100% | 100% | Implementation | 100% | 100% | [21 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B029 | Secure Letter Storage Service | Move SAMS letters into a secure storage solution in order to better protect client information and meet TRA cyber security requirements | Grow (Enhancements) | Audit Requirement | Project/initiative | Advance Our Technology Platforms | More secure storage of client personal information linked to letters. | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#EAO - Enterprise Architecture Office;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4495000% | 4504600% | Confirmed | In Progress | Green | 75% | 100% | Q1 Update | 50% | 100% | Q2 - Implement Code with Functionality Turned Off | 25% | 100% | Q3 - Turn on Code/Initiate Migration Planning for historical letters | 10% |  | Q4 - Execute Migration Plan for Historical Letters | 15% | [13 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B030 | 2019 TRA Recommendation | Implement 2 remaining TRA recommendation from the 2019 SAMS TRA 1. Create and onboarding program for new data consumers for SAMS 2. Document data segregation requirements | Run - Applications |  | Project/initiative | N/A | Improved security and data maintenance | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Unconfirmed |  |  | Finishing in year |  |  | Other | Pending | Yellow | 25% | 100% | Q1 Report | 25% | 100% | Q2 - Create Plan for Implementation | 25% | 0% | Q3 - Execute Plan | 25% | 0% | Q4 Report | 25% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B031 | Feasibility Study for SAMS Data Archiving | Complete a feasibility study of the rules for data archiving to determine options for SAMS data archiving. | Run - Applications | Application Sustainment & Maintenance | Project/initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Cluster Base Budget | Unconfirmed |  |  | Carrying over to next year |  |  | Other | On Backlog | Yellow | 0% | 0% | [24 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B032 | OPS Secure Migration | Migrate all SAMS users to OPS Secure | Run - Applications | Security Compliance | Project/initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  | EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#GovTechON | FALSE | FALSE |  | SPP/MYP | Unconfirmed |  |  | Carrying over to next year | 4495800% | 4526000% | Confirmed | In Progress | Yellow | 25% | 100% | Q1 Report | 25% | 100% | Q2 Implementation of New Solution | 25% | 0% | Q3 Report | 25% | 0% | Q4 Report | 25% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B033 | Assessment and migration of VQRP+ to new IAM services (BPS Secure/OPS Secure) | VQRP+ IAM Migration - Assessment and Migration to new IAM services | Run - Applications | Application Sustainment & Maintenance | Project/initiative |  | Assessment and migration to new IAM services (targeted for Q3 2023/24) | MCCSS - Ministry-wide | VQRP+ |  | SCSI - Shared & Community Services I&IT Solutions | Patrick, Christine (MCCSS);#47 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  |  | In Progress | Green | 66.5% | 90% | Consultation with ITS | 5% | 95% | Planning | 15% | 95% | Design/Development | 50% | 95% |  | 20% | 0% |  |  | 0% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B034 | Support Ministry with Boardroom Technology Modernization | Evaluate the site and make recommendations with ITS. | Run - Cluster Services | Ongoing Business Operations | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Mackiewicz, Rick (MCCSS);#46 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B037 | SDWG-EHWW: DevOps Maturity Implementation | The high level implementation plan was completed in late January 2023 as agreed to by 17 solution support teams. The execution of the tasks has started with the quick wins. This Ops Plan item will require cluster funding for up to 6 months for a PM to sustain the coordination of the activities and to report back on implementation status on a regular basis. SCSI - FCMS CM, FCMS FM, DSCIS, SASS,CSSD. CYIS - CPIN CM, CPIN FM, CPIN CAMS, CPIN Reporting, mFTIS, HCD-ISCIS, OACIS SAIS - SAMS, SADA, MyBenefits, Messaging, EST | Run - Applications | CYSSC Strategy | Ongoing/Operational | Evolve How We Work |  | CYSSC - Cluster-wide | CAMS;#CPIN;#CPIN Reporting;#CPIN FM;#SAMS;#MyBenefits;#mFTIS;#HCD ISCIS;#FCMS |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  | CYIS has committed to provide any additional resources (1 Middleware and 1 DBA for 16 weeks each) to support their portion of the work. Linked to SAIS A085: Enhance existing SAMS dev and deployment pipeline. | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B038 | E-Writs in FCMS-Phase 2 | Implementation of electronic data transfers: Process to create and transmit outgoing files Process to retrieve and consume return files from Teranet | Grow (Enhancements) | CYSSC Strategy | Project/initiative | Advance Our Technology Platforms | Supporting FRO’s strategic plan and satisfying one of their strategic priorities of optimizing system integration | FRO - Family Responsibility Office |  |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4495800% | 4513800% |  | In Progress | Green | 85% | 100% | Design & Planning | 40% | 100% | Development | 30% | 90% | Testing | 20% | 90% | Project Close Out | 10% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Remove/Merge | B039 | SCSI DevOps Improvements | As part of the CYSSC Agile and DevOps Improvement initiative, FRO Digital has identified areas of improvement in both Agile and DevOps | Grow (Enhancements) | Security Compliance |  | Evolve How We Work | Faster time to market, continuous collaboration, high release visibility, more automation, shorter release cycles, improved monitoring and observability | CYSSC - Cluster-wide | FCMS;#DSCIS;#FRO Online;#eBill;#Freedom of Information Request Management System |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  |  | 4501700% | 4538000% |  |  |  | 0% | 0% | Visualising all work in JIRA (Dev & Ops) |  |  | Product development pipeline automation |  |  | Leveraging ELK for observability | [17 empty] | New in 23/24 | N/A | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B040 | FRO Digital Business Releases | Regular business releases based on business priority and the product backlog. | Run - Applications | CYSSC Strategy | Ongoing/Operational |  | Enhancements and defect fixes to improve business functionalities and processes. | FRO - Family Responsibility Office |  |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28 | Samuel, Sheena (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | N/A (ongoing work) | 4501700% | 4538000% |  | N/A (ongoing/operational work) | Green | 73.75% | 100% | Q1 (R23.3) | 25% | 100% | Q2 (R23.4) | 25% | 100% | Q3 (R23.5) | 25% | 95% | Q4 (R24.1) | 25% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B041 | CYIS A095: Oracle eBS 12.2 Upgrade | CPIN's current version of Oracle eBS (e-business suite v12.1) has expired from vendor support. This work is required to support the project to upgrade eBS to vendor supported version, avoid legacy related issues with the current version, and avoid the cost of 'market driven support' to keep the current eBS version. | Run - Applications | Application Evergreening | Support for other OpPlan initiative | Advance Our Technology Platforms |  | CW - Child Welfare & Protection | CPIN;#CPIN FM |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Carrying over to next year |  |  | Confirmed | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B042 | SAIS B029: Secure Letter Storage Service | Support SAIS-led project to move SAMS letters into a secure storage solution in order to better protect client information and meet TRA cyber security requirements | Run - Applications | Application Sustainment & Maintenance;#Audit Requirement | Support for other OpPlan initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B043 | Vulnerability management, assessment and remediation | - Assess, remediate solutions/systems impacted by CVEs communicated by Cyber - Implement patching cycles (O/S, software stack, DBs) - Implement TRA/PenTest report recommended vulnerability fixes/mitigations | Run - Applications | Audit Requirement;#Security Compliance;#Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B044 | Accounts Payable Modernization | Provide a self-service option for Vision Care Service Provides to submit and track invoices online. | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | * Improved service experience and client satisfaction by providing timely payments and status updates through the TPON portal for vendors. Vendors will save time by not having to call the ministry to get an update regarding delayed payments. * Reduce reliance on additional temporary resources and paid overtime by reducing manual, administrative work (e.g., handling, scanning and storage of documents and data entry) * Reduce the risk of vendors refusing to serve ODSP clients due to outstanding repayment for invoices payments * Pave the way for additional SA benefits to be direct-billed to the province through TPON | SA - Social Assistance | TPON |  | SAIS - Social Assistance I&IT Solutions | Bordoloi, Sanjeev (MCCSS);#34 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | TRUE |  | SPP/MYP | Confirmed | 23/24 – Social Assistance Digital Delivery |  | Finishing in year | 4504700% | 4538200% |  | On Backlog | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B045 | Coordinate KDC Mainframe functionality migration (Project) | Coordinate by Q3 2023-24 the migration of any KDC mainframe functionality to GDC mainframe | Run - Applications | Application Evergreening | Support for GovTechON initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 0% | 100% | Validation of scope of work | 15% | 0% | Non-production testing (Dec-Feb) | 60% | 0% | Completion of migration (Feb 2024) | 25% | 0% | [15 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B046 | BIPD - Implement Data Quality Standards and checklist for existing/new applications | Implement a data quality checklist for all projects reviewed during Cluster Architecture Intake. Data quality checklist will reference BIPD's data quality guidelines | Run - Cluster Services |  | Ongoing/Operational | Advance Our Technology Platforms | Improve quality of data on data input by ensuring data quality standards up front | CYSSC - Cluster-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  | All branch areas to reference data quality checklist and adhere to guidelines. | BIPD - Business Intelligence & Practice Division;#CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed | N/A |  | N/A (ongoing work) | 4508200% | 4516900% | Other | Pending | Green | 0% | 0% | Gather input and material from BIPD on existing data quality standards and practices |  | 0% | Gather input and material from other OPS/Corporate entities on existing data quality standards and practices |  | 0% | Perform analysis and prepare draft checklist |  | 0% | Validate and finalize checklist with CYSSC branches |  | 0% | [12 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B047 | DAD Replacement (Business Case Development) | Creation of the business case and additional work for replacement of the existing DAD system which supports the SA DAU functions | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | Modernize technology solution to improve service for citizen applying for ODSP benefits. | SA - Social Assistance | DAD |  | SAIS - Social Assistance I&IT Solutions | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ODS - Ontario Digital Service;#TBS - Treasury Board Secretariat;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Other | Unconfirmed |  | Work on business case for in year submission has started.. | Finishing in year | 4492700% |  | Confirmed | On Backlog | Red | 50% | 100% | Technical Option Analysis + Preliminary Business Case | 25% | 100% | Solution Design Document | 25% | 100% | Cost Benefit Analysis + KPI + Outcomes for Replacement Solution (by business team) | 25% | 0% | Final Business Case | 25% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B048 | CAMS Replacement | CAMS Replacement business case to support collection of overpayments for Social Assistance | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | Replacement of tool used to collect overpayments for client who have left SA. | SA - Social Assistance | CAMS |  | SAIS - Social Assistance I&IT Solutions | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | CMO - Cluster Management Office;#IOB - I&IT Operations Branch;#SAIS - Social Assistance I&IT Solutions;#ODS - Ontario Digital Service;#ITS - Infrastructure Technology Services | TRUE | FALSE |  | Other | Unconfirmed |  | Business case must be developed working with SACSB to determine timing. | Finishing in year |  |  | Tentative - pending funding | On Backlog | Red | 25% | 100% | Technical Option Analysis | 25% | 100% | Cost Benefit Analysis + KPI + Outcomes for Replacement Solution | 40% | 0% | Business Case | 35% | 0% | [15 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B049 | PSSAH Data Masking | Anonymized PSSAH Production data for UAT environment to support data migration to new TPON solution, production support, and testing. | Run - Applications | Application Sustainment & Maintenance;#Audit Requirement | Project/initiative | Become a Trusted Advisor |  | SN - Special Needs | PSSAH |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | Finishing in year | 4513800% | 4541500% |  | In Progress | Green | 30% | 100% | Initial Scripts | 30% | 100% | Final Scripts | 70% | 0% |  |  | 0% | [15 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B050 | Implement PIM/PAM and related access monitoring (Project) | Improve security of applications at CYSSC OPCS & AWS to mitigate Corporate Security TRA related to unauthorized access tries. Privileged identity management (PIM) and privileged access management (PAM) are subsets of IAM (identity and access mgmt.) | Run - Applications | Security Compliance | Support for GovTechON initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) | Mohamed Awad; Aleem Syed; Joachim Kabiawu |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#ITS - Infrastructure Technology Services | TRUE | FALSE |  |  | Unconfirmed |  | Need cost-recovery model to be defined by Corporate Security. | Carrying over to next year |  |  | Confirmed | In Progress | Green | 10% | 100% | Corporate Security conducted demos of CyberArk tool | 10% | 100% | Register all IOB staff for PROD use by end of March 2024 | 40% | 0% | Implement to all remaining IOB Supported non-PROD VM servers by end of 2024-25 | 50% | 0% | [15 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B051 | Recordkeeping readiness assessment for CYSSC application projects | A Self Assessment tool that will define the RM maturity level and possible changes required in an application/solution to increase that maturity. | Run - Cluster Services |  | Ongoing/Operational | Evolve How We Work | The application service owner will have a better sense of the RM gaps in their application. | CYSSC - Cluster-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Grandchamp, Dan (MCCSS);#29 | Samuel, Sheena (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division;#CMO - Cluster Management Office;#CWOB - Child Welfare Operations Branch;#CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B052 | HCD-ISCIS Modernization Phase 3 Strategy | Re-write old thick-client application into a web solution | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms | This redesign will allow HCD-ISCIS to run on a web-browser eventually replacing the HCD-ISCIS desktop application. A web-based application has a number of advantages over the traditional desktop application. Accessible anywhere: The system provides users who travel across multiple locations with immediate access to HCD-ISCIS. Greater availability of information: Users can refer to multiple additional systems simultaneously when delivering or administering the programs. No installation and easy maintenance: A web-based HCD-ISCIS will simplify deployment of updates and fixes to the application. This is because all updates to the application would be done remotely, in the back-end, and without the involvement of Lead Agency users. Additionally, users will no longer be required to install software with each update to the applications. Easy data sharing and collaboration: Users can access and share authorized data as required easily. Centralized security: Users will be able to login securely using an enterprise-wide service called BPS Secure. Device agnostic: Users can switch between mobile devices and laptops as required. Increased efficiency: Direct entry into HCD-ISCIS reduces redundant data entry, improves time of data availability and helps meet early intervention targets. Additionally, there will be a reduction in the reliance on fax transmissions. Benefits to Partner Agencies: A web-based and digitized HCD-ISCIS will lead to the reduction of manual data entry by Lead Agencies and partner agencies like NSO. When additional components of HCD-ISCIS are digitized, direct upload of documentation will eliminate the need for faxing. | SN - Special Needs | HCD ISCIS | 100018797 | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#EAO - Enterprise Architecture Office;#Other;#ITS - Infrastructure Technology Services | TRUE | TRUE | Not specified | SPP/MYP | Confirmed | 22/23 – Early Intervention and Special Needs Modernized Technology Foundation | HCD-ISCIS GUI Re-design to web-based portal work this year, will include o Workshop and analysis o Breakdown of work & activities planning o Change management & training needs o Development work estimates and plans to kick of depending on resource availability | Carrying over to next year | 4511000% | 4538000% | Tentative - pending ministry direction | In Progress | Green | 10% | 100% | Planning - UI Redesign Workshops & User Engagement | 10% | 50% | Design Prototypes & Requirement Readiness | 10% | 50% | Development and Testing | 60% | 0% | Training and Change Management | 10% | 0% | AGP1+2 and Gate 4 Approval /Go-Live Activities | 10% | 0% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B053 | HCD-IRSS Sustainment | Keep the lights on for IRSS (Reporting) | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | N/A | Keeping the lights on, while IRSS is being modernized by BIPD | SN - Special Needs | HCD ISCIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) | CW Team, Cognos resources |  | CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch;#BIPD - Business Intelligence & Practice Division | FALSE | FALSE |  |  |  |  | IRSS contains legacy unsupported software's that will impact business reporting needs. | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Yellow | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B054 | Rocky Bay Child and Family Services (RBCFS) onboarding | RBCFS is a newly designating indigenous agency located outside of Thunder Bay, Ontario. They were deployed to CPIN provider module in January 2023 following their provider designation. Phase 2 will be a full agency deployment following their full agency designation as a child protection agency | Grow (Enhancements) | Legislation;#Ongoing Business Operations | Project/initiative | Become a Trusted Advisor | For Rocky Bay to provide provider and protection services to members of their community | CW - Child Welfare & Protection | CAMS;#CAR;#CPIN;#CPIN Reporting;#CPIN CM;#CPIN FM;#mFTIS | 100018030 | CYIS - Children & Youth I&IT Solutions | Hamilton, Jennifer (MCCSS);#17 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | FALSE |  |  |  |  | date TBC for phase 2: Full agency designation was slated for April 1, 2023 and then changed to a tentative date of July 1, 2023. CWOB advised that they will likely not desigante on this date. | Carrying over to next year |  | 4510800% |  | Pending | Green | 50% | 100% | Onboarded Provider module to CPIN | 50% | 100% | Awaiting CWOB directive to move forward with full deployment, following agency protection designation. No date determined at this time. Advised we require 6 months runway | 50% | 0% | [18 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B055 | Ogwadeni:deo FM Deployment (OGD) | Ogwadeni:deo (OGD) FM Deployment is a current designated indigenous agency in 6 nations. OGD does not currently use CPIN as their casemanagement system, but need to start capturing their FM information as the band is releaseing this responsibility to the agency. OGD decided they would like to deploy to CPIN for FM and eventually shift from their current case management system to CPIN. Phase 1: FM deployment is planned to occur on April 1, 2023 | Grow (Enhancements) | Legislation;#Ongoing Business Operations | Project/initiative | Become a Trusted Advisor | OGD will be able to capture FM data following April 1, 2023 | CW - Child Welfare & Protection | CAMS;#CPIN;#CPIN FM | 100020155 | CYIS - Children & Youth I&IT Solutions | Hamilton, Jennifer (MCCSS);#17 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget |  |  | OGD FM deployment to CPIN completed as scheduled. | Finishing in year |  |  |  | Complete/Operationalized | Complete | 100% | 100% | Deployment | 100% | 100% | [21 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B057 | Quality Standards Framework (QSF) Phase 2 | Developing and implementing enhanced requirements to reduce administrative burden on workers. Dependent on SPP approval and timelines to be determined, based on that | Grow (Enhancements) | Legislation | Project/initiative |  | Enhanced features to support QSF work | CW - Child Welfare & Protection | CPIN;#CPIN CM;#CPIN Reporting |  | CYIS - Children & Youth I&IT Solutions | Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget |  |  | We have the list of backlog items, developed with the sector using co-design. Items were prioritized for phase 1 and 2 Awaiting TB release of funds from approved SPP in August 2023 | Finishing in year |  |  | Tentative - pending funding | Pending | Red | 2% | 100% | Gating & Governance Approvals | 20% | 5% | Solution Discovery Phase | 20% | 5% | Development Phase | 40% |  | UAT & Sign off | 20% | [13 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B058 | Enhanced LA ( Local Admin) role | SPP Sector has requested creating a new role to support agencies being able to fix some internal data errors | Transform | Ongoing Business Operations | Project/initiative | Advance Our Technology Platforms | Business would like to have more control over being able to correct some data | CW - Child Welfare & Protection | CAMS;#CPIN |  | CYIS - Children & Youth I&IT Solutions | Hamilton, Jennifer (MCCSS);#17 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | TRUE |  | Cluster Base Budget |  |  | Awaiting TB release of funds from SPP submission | Finishing in year |  |  |  | Pending | Green | 9% | 100% | Release of SPP funding | 10% | 90% | first iteration of enhanced LA role | 25% | 0% | second phase of Enhanced LA role | 65% | 0% | [15 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B060 | Ongoing support for SA Digital Applications | Provide ongoing support for digital applications, including: 1. DDDP (Digital Disability Determination Package) 2. EQFX-BIL (Equifax-Business Integration Layer) 3. EST (Employment Services Transformation) 4. EAP (Employment Action Plan) 5. IRCC-BIL (Immigration, Refugee and Citizenship Canada – Business Integration Layer) 6. Messaging (formerly 2 Way Messaging) 7. EA (Emergency Assistance) 8. MyBenefits - scheduled for April 24 2023 9. SADA (Social Assistance Digital Application - scheduled for May 22, 2023 | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | SA - Social Assistance | Digital Applications;#DDDP;#EST;#EA;#MyBenefits;#SADA;#2WAYMessaging |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B061 | Ongoing support for MCCSS Data Platform | Support BIPD data extraction requirements for Reporting/Analytics. | Run - Applications | Minister Commitment | Ongoing/Operational | Advance Our Technology Platforms |  | MCCSS - Ministry-wide |  |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B062 | SAIS B031: Feasibility Study for SAMS Data Archiving | Support SAIS's Feasibility Study for SAMS Data Archiving project | Grow (Enhancements) | Application Sustainment & Maintenance | Support for other OpPlan initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  | Waiting for project scope and resource definition. | Finishing in year |  |  | Tentative - pending funding | Complete/Operationalized | Complete | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B063 | SCSI A142: FRO Digital Statement of Arrears Calculator - Phase 2 | Support SCSI's FRO Digital Statement of Arrears Calculator - Phase 2 project | Transform | Business Modernization/Transformation | Support for other OpPlan initiative | Advance Our Technology Platforms |  | FRO - Family Responsibility Office | FRO Online |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B064 | SAIS B047: DAD Replacement | Support SAIS's Disability Adjudication Database (DAD) Replacement project | Transform | Business Modernization/Transformation | Support for other OpPlan initiative | Advance Our Technology Platforms |  | SA - Social Assistance | DAD |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  |  | Carrying over to next year |  |  | Confirmed | On Backlog |  | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B065 | SAIS B048: CAMS Replacement | Support SAIS's Collections Administration and Management System (CAMS) Replacement project | Transform | Business Modernization/Transformation | Support for other OpPlan initiative | Advance Our Technology Platforms |  | SA - Social Assistance | CAMS |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  |  | Carrying over to next year |  |  | Tentative - pending funding | On Backlog |  | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B066 | PSSAH Data Masking | Implement PSSAH data masking to allow copies of production masked data to be made available in non-production zones. | Run - Applications | Application Sustainment & Maintenance;#Audit Requirement | Project/initiative | Advance Our Technology Platforms |  |  | PSSAH |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  | Waiting for project creation and definition of scope and resources. Contact: Jesal. | Finishing in year |  |  | Tentative - pending funding | On Backlog |  | 0% | 100% | Phase 1 - POC at PPE Server or SANDBOX | 30% |  | Phase 2 - Build a second PROD Standalone Database (Duplicate Copy of PROD) | 30% |  | Phase 3 - Build Standby database and Automate with Snapshot Standby @ PROD Server | 30% |  | Project close-out | 10% | [13 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B067 | CYIS A011: CPIN Auto-Deploy | Support CYIS's CPIN Case Management Auto-Deploy project | Run - Applications |  | Support for other OpPlan initiative | Advance Our Technology Platforms |  | CW - Child Welfare & Protection | CPIN CM |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  | Require coordination among other DevOps work. | Carrying over to next year |  |  | Confirmed | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B070 | SDWG-EHWW: DevOps Maturity Reporting (dashboard update) | This item will report and update the countermeasure dashboard as to the status of the DevOps Maturity. | Run - Applications | CYSSC Strategy | Ongoing/Operational | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B071 | EAO B088: SDWG-ATP: Develop the MCCSS Business + Technology Strategy | This is an EAO-led item that will look into strategies for the following; (1) Digital Transformation Strategy (2) Cloud Strategy - Infrastructure and Tooling (3) Data Management Strategy (4) Security Strategy (5) Vendor Roadmap Strategy (6) Infrastructure Strategy | Grow (Enhancements) | CYSSC Strategy | Support for other OpPlan initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B072 | Financial Management Action Plan | Resulting from the OIAD engagement on the CYSSC base budget review, the cluster has committed to the creation of a Financial Management Action Plan. CYSSC commits to developing a financial management action plan to: align to Technology Road Maps; identify long-term efficiencies through further optimization of internal operations; ensure effective governance and business planning for IT activities across the Ministry, and; ensure ongoing updates to the IT Funding Model. | Run - Cluster Services | Audit Recommendation | Project/initiative |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Chalmers, Ashley D. (MCCSS);#13 | Garant, Kelly (She/Her) (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#EAO - Enterprise Architecture Office;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#OCIO - Office of the Chief Information Officer | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4501700% | 4538200% |  | In Progress | Green | 6.25% | 100% | Planning | 25% | 25% | Finalize and operationalize action plan | 75% | 0% | [18 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B073 | SCSI B103 : FCMS Enterprise Command Center POC | Support SCSI-led project. Proof of Concept (POC) of Oracle Enterprise Command Center (ECC). ECC Dashboards and graphical visualization enable Oracle E-Business Suite users to identify and act on priority financial transactions without custom operational reporting. Users can easily create customized dashboards and reports using a simple drag-and-drop interface. | Grow (Enhancements) | Business Modernization/Transformation | Support for other OpPlan initiative | Become a Trusted Advisor |  | FRO - Family Responsibility Office | FCMS |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B074 | Maintain CYSSC data replication to Azure for Disaster Recovery | CPIN, SAMS, FCMS databases have real-time replication to Azure for Disaster recovery | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | Advance Our Technology Platforms |  | CW - Child Welfare & Protection;#SA - Social Assistance;#FRO - Family Responsibility Office | CPIN;#SAMS;#FCMS |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B076 | Update infrastructure topology for cluster-supported solutions | Update infrastructure topology for cluster-supported solution to serve as reference documents. | Run - Applications | Keeping the Lights On | Project/initiative | Advance Our Technology Platforms |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#EAO - Enterprise Architecture Office;#ITS - Infrastructure Technology Services | TRUE | FALSE |  |  | Unconfirmed |  | Support not required from other branches. | Carrying over to next year |  |  | Confirmed | In Progress | Green | 20% | 100% | Gather information and requirements | 20% | 100% | Develop the topology template to be used | 20% | 0% | Establish the repository where documents will be stored and published | 20% | 0% | Socialize the repository and process to update documents | 20% | 0% | Present at Operations/Solutions Directors Planning Meeting | 20% | [10 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B077 | EAO A006: Data Leakage Prevention Program Phase 1 - Assessment | Assess the feasibility of implementing automated technologies to prevent data leakage. | Run - Applications | Audit Recommendation | Support for other OpPlan initiative | Advance Our Technology Platforms | Feasibility analysis on DLP implementation to address audit findings and best practices in implementing safe guards. As a result, to come up with recommendations on DLP implementation for Phase 2 | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | EAO - Enterprise Architecture Office;#CYIS - Child and Youth I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  | The IOB support for Phase 1 will be to attend sessions and to provide input to the discussions. | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 100% | 100% | Draft Roadmap presented by Deloitte in late June 2023 | 10% | 100% | DLP Ph1 Roll Out Strategy (Quick Wins) - completed and provided on Aug 8 2023 | 90% | 100% | [18 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B078 | CPIN SOR-RL Integration | SPP Integration of data between CPIN and SOR-RL. Reduction in duplicate data entry | Transform | Business Modernization/Transformation | Project/initiative | Advance Our Technology Platforms |  | CW - Child Welfare & Protection | CPIN;#SOR-RL |  | CYIS - Children & Youth I&IT Solutions | Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | TRUE |  | SPP/MYP |  |  | Awaiting TB release of funds from SPP approval | Carrying over to next year |  |  |  | Pending | Green | 0% | 100% | Release of SPP funding for year 2 | 10% |  | Requirements gathered and implemented | 90% | 0% | [18 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B079 | CYFSA Website Enhancements | SPP CYFSA Website additional search functionality for public use. | Transform | Business Modernization/Transformation | Project/initiative |  |  | CW - Child Welfare & Protection | CYFSA Website |  | CYIS - Children & Youth I&IT Solutions | Hamilton, Jennifer (MCCSS);#17;#Pawlowski, Walter (MCCSS);#36 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | TRUE |  | SPP/MYP |  |  | Application: CYFSA Website Awaiting approval of release of funds from TB | Carrying over to next year |  |  |  | On Backlog | Yellow | 1.25% | 100% | Planning for SPP activities | 25% | 5% | Scrum work - dev/test | 60% | 0% | Business Sign off | 5% | 0% | Deployment | 10% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B080 | Child Welfare Application Platform - Phase 1 | SPP Development of a modular Child Welfare Application Platform to support new development outside of CPIN. | Transform |  | Project/initiative |  |  | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Hamilton, Jennifer (MCCSS);#17;#Pawlowski, Walter (MCCSS);#36 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | TRUE |  | SPP/MYP |  |  | Awaiting TB approval to release funds from successful TB submission | Carrying over to next year |  |  |  | Pending | Green | 9% | 100% | Release of SPP funding | 10% | 90% | Requirements gathering and implementation | 90% | 0% | [18 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B081 | CYIS Special Needs Team Continuous Quality Improvement QI | To complete milestone reflections with each staff member and identify key outputs that can be included in FORTE plans, training and personal development approaches and CQI for staff engagement across branch initiatives and culture to evolve how teams work together | Transform | CYSSC Strategy;#Ongoing Business Operations | Ongoing/Operational | Evolve How We Work | supports steward leaderships and agile methodologies and culture for how teams work with each other and business partners | SN - Special Needs |  |  | CYIS - Children & Youth I&IT Solutions | Cunningham, Nicki (MCCSS);#20;#Soon, Wilson (MCCSS);#68;#Small, Amanda (MCCSS);#73;#Tyson, Shalini (MCCSS);#74 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) | 4501700% | 4538200% |  | N/A (ongoing/operational work) | Green | 25% | 25% | Amanda Small | 25% | 100% | [21 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B082 | SPP Submission - CyberSecurity CAS Strategy | A multi-year Cyber Security Strategy for Children’s Aid Societies to address evolving cyber threats in the Child Welfare and Protection sector ; • A multi-year Data Leakage Prevention Phase 2 Strategy for making sure that end users (OPS staff, service delivery partners) do not share sensitive or critical information outside the corporate network. | Transform | Security Compliance;#Audit Recommendation | Project/initiative | Advance Our Technology Platforms | Appropriate safeguards are implemented to protect data assets in MCCSS | MCCSS - Ministry-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  | Cyber Security Division | CMO - Cluster Management Office;#IOB - I&IT Operations Branch;#CYIS - Child and Youth I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#SCSI - Shared & Community Services I&IT Solutions;#Other | FALSE | FALSE |  | SPP/MYP | Unconfirmed | 23/24 - Social Services Sector – Cyber Security Strategy (2023/24 – 2026/27) | TB has asked to resource (fund) from within. Further discussion is needed with MPBSD and Cyber Security to determine a path forward. | Finishing in year | 4501900% | 4538000% | Tentative - pending ministry direction | In Progress | Green | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% | [12 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B083 | SDWG-EHWW: CI/CD pipeline for HCD-ISCIS | A continuous integration and continuous deployment (CI/CD) pipeline for automated code builds | Grow (Enhancements) | CYSSC Strategy | Project/initiative | Evolve How We Work | Streamlined process for developers and improving software delivery throughout the software development life cycle via automation. | SN - Special Needs | HCD ISCIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE | [5 empty] | Finishing in year | 4499800% | 4538000% |  | In Progress | Green | 98.5% | 100% | Build a CI/CD Pipeline for HCD-ISCIS | 25% | 100% | Automate code deployments to all four environments | 50% | 100% | Server build book - Deployment guide | 10% | 100% | Collaborate with IOB for deployments | 10% | 100% | Upskill team to oversee and manage deployments | 5% | 70% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B084 | Automated Testing for HCD-ISCIS | QA/Testing process is being automated for HCD-ISCIS | Grow (Enhancements) | CYSSC Strategy | Project/initiative | Evolve How We Work | Better resource utilization Reduces testing time and cost Improves product quality Suited for CI/CD and DevOps | SN - Special Needs | HCD ISCIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year | 4492800% | 4538000% |  | In Progress | Green | 56.5% | 100% | Establish an API & UI Automation Framework | 30% | 100% | Automate API Tests for NSO Interface | 30% | 50% | Automate UI tests for Digital UNHS form | 30% | 30% | Create a Automation Testing Strategy Document | 5% | 40% | Upskill QA team to do Automation Test | 5% | 10% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B085 | Graduated Skills Training for SA | Establish skills pathway, training and lab for different roles to build in-house expertise to run/grow SA portfolio. | Run - Cluster Services | Audit Recommendation | Project/initiative | Evolve How We Work | Build in-house expertise to run/grow SA portfolio and reduce dependency on FFS/vendors. | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions | Veedu, Ummer (MCCSS);#72 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B086 | AMIS Fixed Price Work | Application Maintenance and Improvement Services (AMIS) agreement is valued at $60M for 6 years (3+1+1+1). The first three year period end FY24-25. The scope of work is to do a cost-benefit analysis and make a business case to bring this work in the cluster and prepare for a TB submission in Fall '23. | Run - Applications | Audit Recommendation;#Audit Requirement;#Ongoing Business Operations | Ongoing/Operational | Evolve How We Work | Cluster becomes self-sufficient in maintaining and supporting the SAMS portfolio. | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 50% | 100% | Q1 Report | 25% | 100% | Q2 - Continued Delivery of Maintenance Work for SAMS | 25% | 100% | Q3 Report | 25% | 0% | Q4 Report | 25% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B087 | SAIS Workforce Strategy | Execute the counter measures for the branch's workforce strategy with the goal of becoming self-sufficient and meeting the TB /Audit recommendations. | Run - Applications | Audit Recommendation;#CYSSC Strategy | Ongoing/Operational | Evolve How We Work |  | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions |  | Syed, Aleem (MCCSS) |  |  |  | FALSE | TRUE | TB Commitment |  |  |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B088 | SDWG ATP - Develop MCCSS Business + Technology Strategy - SPP | (1) Digital Transformation Strategy (2) Cloud Strategy - Infrastructure and Tooling (3) Data Management Strategy (4) Security Strategy (5) Vendor Roadmap Strategy (6) Infrastructure Strategy | Grow (Enhancements) | CYSSC Strategy | Project/initiative | Advance Our Technology Platforms | Defining a new cluster business and technology strategy for transforming the technology landscape and approach to address business vision and priorities. Goal to align with the life course approach and ensure value of IT investment in the Cluster by leveraging strategy concepts of digital transformation, cloud strategy, data management, security, vendor roadmap and infrastructure. | MCCSS - Ministry-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  | BIPD - Business Intelligence & Practice Division;#CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#GovTechON;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions | FALSE | TRUE |  | Cluster Base Budget | Confirmed | N/A | Digital Transformation - Integration of digital technology into all areas of business. Evaluate current state, Life Course Approach, Data Driven, Technology Adoption Cloud - Standards - Cloud computing, Cloud Infrastructure and Tooling Data Management - Approach to data governance, data architecture, data storage, systems integration, unified data intake Security - Protect Information Systems, Data and Networks from Cyber Threats Vendor - Selecting, managing, maximizing technology vendors. Entrance and exit criteria for vendor products Infrastructure - Manage infrastructure assets to ensure hosting and service optimization | Finishing in year | 4497400% | 4504400% | Other | Pending | Green | 30% | 100% | Draft SPP document | 40% | 50% | Review SPP in CLT meeting | 20% | 30% | Finalize SPP document | 40% | 10% |  |  | 0% |  |  | 0% | [9 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B089 | CPIN Automation Testing - Reporting | Set up an automated process for all releases to significantly reduce the testing time during regression cycles for testing activities such as: projects, smoke testing, integration testing, bug fixes related to CM, FM and Reports | Grow (Enhancements) |  | Ongoing/Operational |  |  | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Torrance, Tyler (He/Him) (MCCSS);#37 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget |  |  |  | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B090 | CPIN Automation Testing - FM & CM | Set up an automated process for all releases to significantly reduce the testing time during regression cycles for testing activities such as projects, smoke testing, integration testing, and bug fixes related to CM, FM and Reports | Grow (Enhancements) | CYSSC Strategy;#Application Sustainment & Maintenance | Project/initiative | Advance Our Technology Platforms | Quicker response at delivering projects to enhance the user's experience while also quickly addressing urgent fixes, and P1s hindering the ability of the users to conduct their day to day operational activities | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35;#Torrance, Tyler (He/Him) (MCCSS);#37 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch | TRUE | FALSE |  | Cluster Base Budget |  |  | Automation work is part of the day-to-day operational activities.&nbsp; It is fundamental that the work is included in our Operational budget, so the work is supported and funded. Awaiting SPP release of funds to solution this quicker | Carrying over to next year | 4492800% | 4583800% |  | In Progress | Green | 17% | 100% | Analysis of Selenium | 5% | 100% | Transferring of all Smoke Test Scripts from ALM to Selenium | 5% | 80% | Transferring of all regression test scripts from ALM to Selenium | 80% | 10% | Move environment to cloud | 5% | 0% | Adoption of Jira and Zephyr | 5% | 0% | [9 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B091 | CYIS Child Welfare Team Continuous Quality Improvement QI | To complete milestone reflections with each staff member and identify key outputs that can be included in FORTE plans, training and personal development approaches and CQI for staff engagement across branch initiatives and culture to evolve how teams work together | Transform |  | Ongoing/Operational |  |  | CW - Child Welfare & Protection |  |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35;#Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19;#Pawlowski, Walter (MCCSS);#36;#Torrance, Tyler (He/Him) (MCCSS);#37 | Kabiawu, Joachim (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | Carried forward from 22/23 OpPlan | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B092 | 2023 OAGO VFM Audit: Security and Operations of IT Systems for Four Clusters | Coordination of: information and meeting requests; factual clearance of draft audit report; development of management responses and action plans. | Run - Cluster Services | Audit Requirement | Project/initiative |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#D'Annunzio, James (MCCSS);#95;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE | High attention from Premier/Minister's office | Cluster Base Budget | Confirmed |  |  | Finishing in year | 4492900% | 4538000% |  | In Progress | Green | 50% | 100% | Coordinate Responses to Requests for Information | 25% | 100% | Coordinate OAGO Meeting Requests | 25% | 100% | Factual Clearance and Management Responses for Audit Report | 25% | 0% | Develop Action Plans in Response to Audit Recommendations | 25% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B093 | TB Reporting | Provide coordination and support of quarterly (MPR and QSR) and ad hoc TB reporting. | Run - Cluster Services |  | Ongoing/Operational |  |  | MCCSS - Ministry-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#Zhang, Jerry (MCCSS);#97;#Wong, Kenneth (MCCSS);#98 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE | MYP/SPP/TB approved | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4501900% | 4538000% |  | N/A (ongoing/operational work) | Green | 45% | 100% | Q1 Reporting | 25% | 100% | Q2 Reporting | 25% | 80% | Q3 Reporting | 25% | 0% | Q4 Reporting | 25% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B094 | IT Funding Model (ITFM) - Annual Review | As part of the SPP process -- update the ITFM to determine portfolio adjustments required. | Run - Cluster Services |  | Annually recurring initiative |  |  | MCCSS - Ministry-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#Wong, Kenneth (MCCSS);#98 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE | MYP/SPP/TB approved | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) | 4517000% | 4526000% |  | In Progress | Green | 96% | 100% | 2024-25 Program Forecasts | 20% | 100% | Program Consultation | 40% | 100% | SPP Technical Decision Note | 40% | 90% | [15 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B095 | IT General Control (ITGC) Assessments | Coordinate the completion of ITGC assessments (Design and Operating Effectiveness) and reporting. | Run - Cluster Services |  | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | CMO - Cluster Management Office | Burns-Solitar, Carrie (MCCSS);#40;#Liwanag, Uriah (MCCSS);#96 | Garant, Kelly (She/Her) (MCCSS) |  |  |  | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  |  | In Progress | Yellow | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B096 | OACIS & PEIS Migration from KDC | Migrate OACIS & PEIS applications out of KDC to GDC | Run - Applications | Keeping the Lights On | Project/initiative |  |  | SN - Special Needs | OACIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 0% | 0% | Planning with ITS and IOB |  | 100% | Implementation |  | 30% | [18 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B098 | Business and Technology Roadmap |  | Run - Cluster Services |  | Project/initiative |  |  | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions |  | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | Pending | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B099 | Annualized Earnings Exemptions - Business Analysis | Acquire a BA resource to do requirements analysis and grooming for the Annualized Earnings Exemptions initiative | Transform | Policy Change | Project/initiative |  |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE |  | Ministry LOA | Confirmed |  | The funding for the overall initiative has not been approved yet. The BA resource will be used as a stop gap solution to meet a potential January 2024 delivery date, given there is a 9 month critical path in the high level delivery plan with requirements analysis being at the start of the path. | Finishing in year | 4501900% |  |  | In Progress | Green | 40% | 100% | Q1 Update | 10% | 100% | Q2 Update | 30% | 100% | Q3 Update | 30% |  | Q4 Update | 30% | [13 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B100 | Reporting Integration work with BIPD | Placeholder to determine and plan for co-design operational model for Reports integration work | Run - Cluster Services |  | Project/initiative | Advance Our Technology Platforms |  | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions |  | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Carrying over to next year |  |  |  | In Progress | Green | 5% | 100% | Create temporary governance process between BIPD, BIIB and SAIS | 5% | 100% | TBD | 95% | 0% | [18 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | B101 | SAMS ODSP for First Nations - Initial Implementation | Changes required in SAMS so it can be used by First Nations for ODSP program applicants | Transform | Business Modernization/Transformation | Project/initiative |  |  | SA - Social Assistance | SAMS |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33;#Duicu, Ana (MCCSS);#82 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE |  |  | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Yellow | 10% | 100% | Q1 Update | 10% | 100% | Q2 Update | 20% |  | Q 3 Update | 50% |  | Q4 Update | 20% | [13 empty] | New in 23/24 | N/A | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B102 | SAIS B044: Accounts Payable Modernization | Support SAIS-led project. Provide a self-service option for Vision Care Service Providers to submit and track invoices online. | Transform | Business Modernization/Transformation | Support for other OpPlan initiative | Advance Our Technology Platforms |  | SA - Social Assistance | TPON |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE | [5 empty] | Carrying over to next year |  |  | Confirmed | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B103 | FCMS Enterprise Command Center POC | Proof of Concept (POC) of Oracle Enterprise Command Center (ECC) ECC Dashboards and graphical visualization enable Oracle E-Business Suite users to identify and act on priority financial transactions without custom operational reporting. Users can easily create customized dashboards and reports using a simple drag-and-drop interface. | Grow (Enhancements) | Business Modernization/Transformation | Project/initiative | Become a Trusted Advisor | Allow FRO (Financial) users to prioritize financial transactions that require immediate attention and affectively identify and address transactions of potential concern. | FRO - Family Responsibility Office | FCMS |  | SCSI - Shared & Community Services I&IT Solutions |  | Samuel, Sheena (MCCSS) |  |  | IOB - I&IT Operations Branch | FALSE | FALSE |  | Cluster Base Budget |  |  |  | Finishing in year | 4501900% | 4510700% |  | Complete/Operationalized | Complete | 100% | 100% | POC | 100% | 100% | [21 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B104 | Counter Reg and Visitor Reg migration | Migrate CR and VR applications from KDC to GDC, as a part of KDC decommission activity | Run - Applications | Keeping the Lights On | Project/initiative | Advance Our Technology Platforms | Ensure CR and TR applications continue to operate after the Kingston Data Center is decommissioned | SA - Social Assistance | Counter Registration;#Toronto Region Visitor Registration |  | SAIS - Social Assistance I&IT Solutions | Karageorgos, Effie (MCCSS);#32 | Syed, Aleem (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services | TRUE | TRUE |  | Cluster Base Budget | Unconfirmed |  |  | Finishing in year | 4501900% | 4507200% |  | Complete/Operationalized | Green | 100% | 100% | Q1 Report | 50% | 100% | Q2 Report | 50% | 100% |  | 0% | 0% |  | 0% | 0% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B105 | Application Support and Maintenance for Social Assistance applications | CRQs, incident investigation and restoration, application releases, software patches, minor technical upgrades, batch processing support, performance tuning, system integrations, database maintenance, and testing activities to support maintenance and anticipated enhancements. Includes: SAMS, SALIS, SAMS-EDM, OASA | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS;#SALIS;#SAMS-EDM |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | B106 | SAIS A113: Limit use and safeguard personal information (PI) in system, test environments and minimize access to PI | Assess opportunity to build reports within core systems to meet user needs instead of extracting the data. | Grow (Enhancements) |  | Ongoing/Operational |  |  | SA - Social Assistance | SAMS |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  | IOB does not have resources. | N/A (ongoing work) |  |  | Tentative - pending funding | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q1 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | B107 | SAIS A089: Emergency Assistance migration to GoCloud | Migrate EA hosting from on-prem to public cloud. | Run - Applications | Application Sustainment & Maintenance | Ongoing/Operational | Advance Our Technology Platforms | * Scalability of public cloud hosting platform to any surge in user demand * Higher stability and availability of public cloud hosting platform * Scaling of hosting cost based on usage * Alignment of EA application hosting architecture with other SA digital applications enabling leveraging of resource pool for application support | SA - Social Assistance | EA |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  | IOB does not have resources. | N/A (ongoing work) |  |  | Tentative - pending funding | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q1 update ready for CMO validation | changes requested;#Change Type of Work to Project/initiative | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Pending | B109 | SAIS B100: Reporting integration work with BIPD | Placeholder to determine and plan for co-design operational model for Reports integration work | Run - Cluster Services |  | Ongoing/Operational |  |  | SA - Social Assistance |  |  | IOB - I&IT Operations Branch | Patel, Jesal (MCCSS);#22 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  |  | N/A (ongoing work) |  |  | Tentative - pending funding | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q1 update ready for CMO validation | prechecked - okay | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | B110 | SAIS B104: Counter Reg and Visitor Reg migration | Migrate Counter Registration and Toronto Region Visitor Registration applications from KDC to GDC, as a part of KDC decommission activity | Run - Applications | Keeping the Lights On | Ongoing/Operational | Advance Our Technology Platforms | Ensure CR and TR applications continue to operate after the Kingston Data Center is decommissioned | SA - Social Assistance | Counter Registration;#Toronto Region Visitor Registration |  | IOB - I&IT Operations Branch | Stoicescu, Valentin (MCCSS);#23 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q1 update ready for CMO validation | changes requested;#Change Type of Work to Project/initiative | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
On hold | B111 | SAIS B101: SAMS ODSP for First Nations - Initial Implementation | Changes required in SAMS so it can be used by First Nations for ODSP program applicants | Transform | Business Modernization/Transformation | Ongoing/Operational |  |  | SA - Social Assistance | SAMS |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  |  | Unconfirmed |  | IOB support is pending SAIS confirmation and funding of this project. | N/A (ongoing work) |  |  | Tentative - pending funding | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q1 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B112 | SAIS A144: SA Digital: SAMS - Electronic Document Management (EDM): Transform Scope | a. Digital Integrations (scale EDM service); b. Expansion of E-forms Capabilities; c. Expansion to OW and Centralized Services; and d. Document Assignment Logic Refinement. | Transform | Business Modernization/Transformation | Support for other OpPlan initiative | Advance Our Technology Platforms | Project allows for digitization of a client’s file and new incoming mail for retention, including imaging, electronic storage, and retrieval of documentation for ODSP and OW partners. EDM reduces the amount of data entry and paper handling time and enables staff to access files without needing to search through a file room or internal mail system. EDM includes Digital Day 1, which allows staff to scan documents that have been dropped off by clients. Files are immediately digitized and connected to the client’s file, improving response time to client inquires.​ | SA - Social Assistance | SAMS-EDM |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  | Only a. Digital Integrations (scale EDM service) will need IOB support. The IOB resources will be internal. No new additional resources required. | Finishing in year |  |  | Confirmed | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B113 | SAIS A085: Enhance existing SAMS dev and deployment pipeline | Continue to improve the maturity of the SAMS production deployment pipeline for example automated front end validation and pipe line to pipe line integration with SA Mod application. | Run - Applications | Application Sustainment & Maintenance | Support for other OpPlan initiative | Advance Our Technology Platforms |  | SA - Social Assistance | SAMS |  | IOB - I&IT Operations Branch | Iqbal, Azhar (MCCSS);#24 | Muñoz, Jairo (MCCSS) |  |  | SAIS - Social Assistance I&IT Solutions | FALSE | FALSE | [5 empty] | Finishing in year |  |  | Confirmed | Complete/Operationalized | Complete | 100% | 100% | Complete assessment. | 100% | 100% | [21 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B114 | I&IT Operations Branch Strategy | Create and implement a branch strategy. | Run - Cluster Services |  | Project/initiative | Evolve How We Work |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CMO - Cluster Management Office | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | Finishing in year |  |  | Confirmed | In Progress | Green | 73.4% | 100% | Define the scope | 10% | 100% | Socialize the Strategy (CLT, CELT, Branch) | 10% | 100% | Create the Dashboard for implementation tracking | 10% | 100% | Implement | 70% | 62% | [12 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B115 | SPP Submission - Data Leakage Prevention Phase 2 | A multi-year Cyber Security Strategy for Children’s Aid Societies to address evolving cyber threats in the Child Welfare and Protection sector ; • A multi-year Data Leakage Prevention Phase 2 Strategy for making sure that end users (OPS staff, service delivery partners) do not share sensitive or critical information outside the corporate network. | Transform | Security Compliance | Project/initiative | Advance Our Technology Platforms |  | MCCSS - Ministry-wide |  |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  | Cyber Security Division | CMO - Cluster Management Office;#CYIS - Child and Youth I&IT Solutions;#IOB - I&IT Operations Branch;#SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#Other | FALSE | FALSE |  | SPP/MYP | Unconfirmed | N/A |  | Carrying over to next year |  |  | Tentative - pending ministry direction | Pending | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B116 | Metaverse - Training Strategy for Business Sectors | Develop a strategy and implement a metaverse/sharepoint spaces strategy to help improve and support the business training teams | Run - Cluster Services |  | Project/initiative | Advance Our Technology Platforms |  | FRO - Family Responsibility Office | FCMS |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B117 | EIAM Modernization oversight | Assisting projects in the various solution branches with their application IAM modernization activities to OPS/BPS/Public Secure | Run - Cluster Services | Security Compliance;#Business Modernization/Transformation | Ongoing/Operational | Advance Our Technology Platforms | Individual applications are recommended to follow one of the approved IAM migration patterns | CYSSC - Cluster-wide;#Enterprise I&IT | CPIN;#DSCIS;#FCMS;#SAMS |  | EAO - Enterprise Architecture Office |  | Lourdes, Alvin (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#SAIS - Social Assistance I&IT Solutions;#CYIS - Child and Youth I&IT Solutions | FALSE | TRUE | Not specified | Cluster Base Budget | Confirmed | N/A | It is part of GovTechON corporate mandate to move applications to OPS/BPS/Public Secure | N/A (ongoing work) | 4501900% | 4538000% | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | Determine alignment of application to one of the approved pattern |  | 100% | As part of EA governance, project to demonstrate alignment to approved pattern |  | 0% | [18 empty] | Carried forward from 22/23 OpPlan | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B118 | Support for audits, reviews, assessments | Provide support for audits, reviews, assessments, risk remediation, and other related requests (e.g. ITGC, risk recalculations) | Run - Applications | Audit Requirement | Ongoing/Operational |  |  | CYSSC - Cluster-wide |  |  | IOB - I&IT Operations Branch | Obias, Joven (MCCSS);#21 | Muñoz, Jairo (MCCSS) |  |  | CMO - Cluster Management Office | FALSE | FALSE |  | Cluster Base Budget | Confirmed |  |  | N/A (ongoing work) |  |  | Confirmed | N/A (ongoing/operational work) | Green | 0% | 0% | [24 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B119 | HCD ISCIS and HCD IRSS ITGC Toolkit Completion and Operational Effectiveness Assessments | Operational Effectiveness Assessment. Previous ITGC was completed in 2019 | Run - Applications | Audit Requirement | Ongoing/Operational | Evolve How We Work |  | SN - Special Needs | HCD ISCIS |  | CYIS - Children & Youth I&IT Solutions | Kugendran, Shanmugathasan (MCCSS);#19;#Soon, Wilson (MCCSS);#68 | Kabiawu, Joachim (MCCSS) | CMO, IOB, IPEB |  | CMO - Cluster Management Office | FALSE | FALSE | [5 empty] | N/A (ongoing work) |  |  |  | Pending | Green | 0% | 100% | ITGC Audit for HCD-ISCIS | 100% | 0% | [21 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B120 | OPS Web Accessibility Compliance Plan | The goal of the OPS Web Accessibility Compliance plan is to bring OPS into compliance with the Accessibility for Ontarians with Disabilities Act (AODA) Integrated Accessibility Standards Regulation (IASR) by December 2024. Focus areas to complete by December 31, 2023: 1.Non-compliant Internet/Extranet Sites 2.Standardization Focus areas to complete by December 31, 2024: 1.Corporate & Enterprise Web Applications 2.Document Accessibility 3.Video Remediation 4. Cultural Transformation | Grow (Enhancements) | Legislation | Project/initiative | Evolve How We Work | OPS will be compliant with the Accessibility for Ontarians with Disabilities Act (AODA) Integrated Accessibility Standards Regulation (IASR) by December 2024. | Enterprise I&IT |  |  | IOB - I&IT Operations Branch | Dabideen, Mala (MCCSS);#30 | Muñoz, Jairo (MCCSS) |  |  | SCSI - Shared & Community Services I&IT Solutions;#CAC - Central Agencies Cluster;#ITS - Infrastructure Technology Services;#TBS - Treasury Board Secretariat;#OCIO - Office of the Chief Information Officer;#ODS - Ontario Digital Service;#GovTechON | TRUE | TRUE | Legislation | Enterprise Funding | Tentative |  | Resource constraints | Carrying over to next year | 4496000% | 4565700% | Confirmed | In Progress | Green | 38.5% | 100% | Endorsement of OPS Web Accessibility Compliance Plan | 10% | 100% | Quarterly report back to Regulator (Jul 2023 to Dec 2024) | 30% | 25% | Engagement and Tracking with IT Contacts for Non-Compliant Sites | 20% | 30% | Development & Implementation of Digital Accessibility Standard | 20% | 75% | Communications and Change Management Roll-Out | 20% | 0% | [9 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B121 | OIAD R13 - AI Assessment to discover PI Data flows | As part of a longer strategy, Children and Youth I&IT Solutions Branch will start an assessment of implementing AI that may be able to discover PI data flows and anticipate, detect and prevent invasive privacy events, following the Curam upgrade scheduled for May 2020. Specific recommendations from the assessment will be reported back by December 2023. "This initiative will need a dedicated team to review the scope and timelines to deliver this initiative. At this time there is no investment on tools, resources, or infrastructure to begin scoping this initiative. March 31, 2023: Assessment is being conducted by CYIS with TRIP consultation on AI technologies available on the market. The focus has been on prevention through education and safeguards and intervention. CWOB has been working with the sector to provide information, the sector has been responsive to keeping security technology up to date." | Grow (Enhancements) |  | Project/initiative |  |  | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19;#Torrance, Tyler (He/Him) (MCCSS);#37;#Acuna, Oscar (MCCSS);#35;#Pawlowski, Walter (MCCSS);#36 | Kabiawu, Joachim (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | Complete/Operationalized | Complete | 100% | 100% | Assess AI opportunities | 100% | 100% | [21 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B122 | OIAD R2 - Identify lessons learned and potential opportunities for strengthening I&IT processes to prevent recurrence. | Based on a sample of municipal/ service delivery partners this may include, where feasible, reviewing recent security incidents and cyberattacks to assess risks and impacts on information systems and interruptions to ministry program service delivery. Identify lessons learned and potential opportunities for strengthening I&IT processes to prevent recurrence. MCCSS: To address the recommendations directed towards the Ministry of Children, Community and Social Services (MCCSS), the Child Welfare Operations Branch, the I&T Cluster, and the MGCS Cyber Security Division will meet and work together to determine: - The work that has already been undertaken relating to cyber security generally, and specifically for/in the child welfare sector - The opportunities that might exist to leverage ministry and OPS resources or knowledge - The opportunities for sector-led initiatives that may be brought forward Having the time to properly consult internally will allow us to engage our sector partners to develop a work plan, and define next steps, that can address the issues and recommendations presented during future OIAD follow-up activities. | Transform | Audit Recommendation | Project/initiative |  |  | CW - Child Welfare & Protection |  |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35;#Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19;#Pawlowski, Walter (MCCSS);#36;#Torrance, Tyler (He/Him) (MCCSS);#37 | Kabiawu, Joachim (MCCSS) |  |  | CWOB - Child Welfare Operations Branch;#CYIS - Child and Youth I&IT Solutions | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 40% | 100% | Finalize user agreement | 50% | 80% | Disseminate user agreement | 10% |  | Communicate implemented agreements | 40% | [16 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B123 | OIAD R1 - Assess Ministry IT security protocol compliance and protocols between Ministry and Service Delivery Partners for reporting and addressing IT Security Incidents in service delivery partners associated with interfacing Ministry applications. | MCCSS: To address the recommendations directed towards the Ministry of Children, Community and Social Services (MCCSS), the Child Welfare Operations Branch, the I&T Cluster, and the MGCS Cyber Security Division will meet and work together to determine: - The work that has already been undertaken relating to cyber security generally, and specifically for/in the child welfare sector - The opportunities that might exist to leverage ministry and OPS resources or knowledge - The opportunities for sector-led initiatives that may be brought forward Having the time to properly consult internally will allow us to engage our sector partners to develop a work plan, and define next steps, that can address the issues and recommendations presented during future OIAD follow-up activities. | Transform | Audit Recommendation | Project/initiative |  |  | CW - Child Welfare & Protection | CPIN;#mFTIS |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Acuna, Oscar (MCCSS);#35;#Hamilton, Jennifer (MCCSS);#17;#Kugendran, Shanmugathasan (MCCSS);#19;#Torrance, Tyler (He/Him) (MCCSS);#37;#Pawlowski, Walter (MCCSS);#36 | Kabiawu, Joachim (MCCSS) |  |  | CYIS - Child and Youth I&IT Solutions;#CWOB - Child Welfare Operations Branch | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | In Progress | Green | 6% | 100% | Review proposal from Native Child and Family Services | 60% | 10% | decision and implementation | 40% | 0% | [18 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B124 | Annual SAMS ITGC Audit | This is an annual audit regarding the SAMS ITGC Toolkit. The OAGO looks into the following: - IT Control Environment - Access Management - Change Management - Operations - SOC Reports - Interface The SAMS team is required to provide evidences, documentations and walkthroughs for this audit. | Run - Applications | Audit Recommendation | Annually recurring initiative |  |  | SA - Social Assistance |  |  | SAIS - Social Assistance I&IT Solutions | Hamilton, James (MCCSS);#33 | Syed, Aleem (MCCSS) |  |  |  | FALSE | FALSE | [5 empty] | Finishing in year |  |  |  | Complete/Operationalized | Complete | 25% | 100% | Q1 Report | 25% | 100% | Q2 Report | 25% | 0% | Q3 Report | 25% | 0% | Q4 Report | 25% | 0% | [12 empty] | New in 23/24 | Q2 update pending | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Approved | B125 | OPSdocs new file plan strategy/design | Regional Offices implemented OPSdocs in 2015 when there were two ministries. Regions filed into the two separate ministry structures in OPSdocs. When the ministries merged, the OPSdocs structures did not get amalgamated. This project is to create a new file plan/merge the legacy folder structures and support the transition. | Grow (Enhancements) |  | Project/initiative |  | To separate MCSS and MCYS OPSdocs file plans into one consolidated MCCSS file plan. | MCCSS - Ministry-wide |  |  | SCSI - Shared & Community Services I&IT Solutions | Grandchamp, Dan (MCCSS);#29 | Samuel, Sheena (MCCSS) |  |  | GSIC - Government Services Integration Cluster | FALSE | FALSE |  | Other | Unconfirmed |  |  | Finishing in year |  |  | Tentative - pending funding | In Progress | Green | 0% | 100% | TBD | 100% | 0% | [21 empty] | New in 23/24 | Q2 update ready for CMO validation | Not reviewed by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Remove/Merge | B126 | FRO Digital Document Modernization Project (DDMP) Business Case | Assist FRO with the creation of a business case for Phase 2 funding to move towards a paperless future through records digitization. | Transform | Business Modernization/Transformation | Project/initiative |  |  | FRO - Family Responsibility Office |  |  | SCSI - Shared & Community Services I&IT Solutions | Wright, Peter (MCCSS);#28;#Paquette, Stephanie (MCCSS);#76 | Samuel, Sheena (MCCSS) |  |  |  | FALSE | FALSE |  |  |  |  | September 21 - Stephanie Paquette: "FRO has chosen not to pursue funding so we can close this." | [5 empty] | Green | 0% | 0% | [24 empty] | New in 23/24 | Q1 CMO validated | Validated by CMO | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan
Pending | B127 | Ready Set Go Phase 1 | Deploy changes in CPIN that will support individual outcomes analysis and the ability to assess the overall effectiveness of the directive as it pertains to children leaving out of home care.​ Policy Directive CW003-23 came into effect on April 1, 2023, and prepares youth for successful transition from the care of Children’s Aid societies to adulthood, also known as Ready Set Go (RSG) Legislative changes were covered in the approved SPP. This is a Must Do Can't Fail item. | Grow (Enhancements) | Legislation | Project/initiative |  | Update CPIN to support the documentation and reporting of new business processes to improve planning for children leaving care. Phase 1: includes a new Case Type that will support individual outcomes analysis and the ability to assess the overall effectiveness of the directive as it pertains to children leaving out of home care.​ | CW - Child Welfare & Protection | CPIN |  | CYIS - Children & Youth I&IT Solutions | Wang, Cedric (MCCSS);#15;#Hamilton, Jennifer (MCCSS);#17;#Streef, Joseph (MCCSS);#148 | Kabiawu, Joachim (MCCSS) |  |  | IOB - I&IT Operations Branch;#ITS - Infrastructure Technology Services;#BIPD - Business Intelligence & Practice Division | TRUE | TRUE | Legislation | SPP/MYP | Confirmed | [5 empty] | Confirmed |  |  | 0% | 0% | [27 empty] | Item | sites/CYSSC202324OperationalPlanning/Lists/202324 Operational Plan